## 1st qtr (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1st QUARTER, CY 2015
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks (Date of Obligation)
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
repair/improvement of Farmer's Pavillion | Sta. Barbara, Pangasinan | 2973554 | [5 empty] | 1/28/2015 | 6911 | PR# 0082
Proposed Perimerer Fence | Ketegan E/S., Brgy. Ketegan, Bautista, Pangasinan | 1405947 | [5 empty] | 2015-03-04 | 6911 | PR# 1202
Construction of Slope Protection | along Calarian Creek, Nursery, Tebag, Sta. Barbara, Pangasinan | 1446450 | [5 empty] | 2015-03-04 | 6911 | PR#0614
2-Storey Multi-purpose Bldg. (ABC Building) Phase II, | Alvear Street, Lingayen, Pangasinan | 1861017 | [5 empty] | 2015-03-04 | 6911 | PR#0312
Construction of 1 unit 2-Storey Multi-Purpose Bldg., (Brgy. Hall), | Poblacion East, Bautista, Pangasinan | 2305855 | [5 empty] | 2015-03-04 | 6911 | PR#0763
Additional works of various of various buildings at EPDH, | Tayug, Pangasinan | 2238748 | [5 empty] | 2015-03-04 | 6911 | PR#0059
Renovation/Improvement of Pangasinan Internal Affair Service (PIAS) Building, PNP Headquarters, | Lingayen, Pangasinan | 1146662 | [5 empty] | 2015-03-04 | 6911 | PR#1237
installation of Reinforced Concrete Culvert Pipes (RCCP)), Nursery Compound, | Tebag, Sta. Barbara, Pangasinan | 217442 | [5 empty] | 2015-03-04 | 6911 | PR#0378
Improvement of CT Scan Room | Pangasinan Provincial Hospital | 388107 | [5 empty] | 2015-03-04 | 6911 | PR#0630
Rehabilitation/Concreting of Basement flooring of Malong and Palaris Buildings, Capitol Compound, | Lingayen, Pangasinan | 221234 | [5 empty] | 2015-03-04 | 6911 | PR#1187
construction of Philippine Affairs Office (Pangasinan Chapter), Capitol Compound, | Lingayen, Pangasinan | 1979401 | [5 empty] | 2015-03-12 | 6911 | PR#2456
Repair/Rehab of Repair Bay 1 and Office Building, Motorpool Compound, | Lingayen, Pangasinan | 2593367 | [5 empty] | 2015-03-12 | 6911 | PR#1916
396 MT Asphalt Pre-mix and 17 drums Emulsified Asphalt for the improvement of Road Network and Parking Area @ Bayambang Dist. Hospital, | Bayambang, Pangasinan | 2422800 | [5 empty] | 2015-03-23 | 6911 | PR#2621
construction of Multi-Purpose Bldg., (Brgy. Hall), | Brgy Mapolopolo, Basista, Pangasinan | 1198627 | [5 empty] | 2015-03-23 | 6911 | PR#1319
construction of Stone Masonry with Barriers along Mabilao-Binday Prov'l Road, | San Fabian, Pangasinan | 555185 | [5 empty] | 2015-01-28 | 8917-1 | PR#0211
repainting of various concrete bridges | 1st-6th Pangasinan Engineering Districts | 266039 | [5 empty] | 2015-02-27 | 8917-1 | PR#1204
construction of Stone masonry with barrier and concreting of Road Shoulder along Mabilao-Binday Road, | San Fabian, Pangasinan | 1371178 | [5 empty] | 2015-03-04 | 8917-1 | PR#1034
repainting of various Provicial Steel Bridges | around the Province of Pangasinan | 190261 | [5 empty] | 2015-03-23 | 8917-1 | PR#1142
Mr. Bernabe Cabrera Salayog- Financial Assistance, cost of tiling works of Sodality Road | Manaoag, Pangasinan | 500000 | [5 empty] | Paid Jan., 2015
repair of Sison Auditorium (Vice-Governor's Room), | Lingayen, Pangasinan | 187485 | [5 empty] | 2015-02-11 | 3917 | PR#0311
furnishing materials, labor, equipment and others- for the completion of 2-storey Multi-Purpose building (Brgy. Hall), | San Guillermo, San Jacinto, Pangasinan | 1397805 | [5 empty] | 2015-03-19 | 3917 | PR#2921
Economic Development
Asphalting and blocktopping of RHU and Municipal Hall Compound, | Urbiztondo, Pangasinan | 1505900 | [5 empty] | 2015-03-04 | 6911 | PR#0036
Asphalting of Victorio-Pangascasan (Sual Coastal Road), Victoria Sec., | Alaminos City | 644000 | [5 empty] | 2015-01-28 | 8917-1 | PR#0157
concreting of Brgy. Esperanza Road, | Sison, Pangasinan | 158774 | [5 empty] | 2015-02-11 | 8917-1 | PR#0253
Asphalting of Frank's Canteen Compound, | Lingayen, Pangasinan | 314800 | [5 empty] | 2015-02-11 | 8917-1 | PR#0212
Asphalt materials for the Proposed Blocktopping of Brgy. Buenlag Road, | Bugallon, Pangasinan | 4058900 | [5 empty] | 2015-03-04 | 8917-1 | PR#0060
blocktopping of Cervantes Road, | Brgy. Salomague Norte, Bugallon, Pangasinan | 648200 | [5 empty] | 2015-03-04 | 8917-1 | PR#0212
414 MT Asphalt Pre-Mix and 18 drums Emulsified Asphalt in Asphalting of Balangobong Road, | Alaminos, Pangasinan | 2536200 | [5 empty] | 2015-03-04 | 8917-1 | PR#1223
concreting and construction of slope protection (stone masonry) | Brgy. Poponto, Bautista, Pangasinan | 4175839 | [5 empty] | 2015-03-04 | 8917-1 | PR#0754
construction of stone masonry | Brgy. Macalong, Asingan, Pangasinan | 3652065 | [5 empty] | 2015-03-04 | 8917-1 | PR#0398
concreting of Tombor Road, Phase II, | Binmaley, Pangasinan | 1794383 | [5 empty] | 2015-03-04 | 8917-1 | PR#0691
blocktopping/patching of various Poblacion Roads | Manaoag, Pangasinan | 925800 | [5 empty] | 2015-03-04 | 8917-1 | PR#0631
asphalting of By-pass Road, Poblacion, | Manaoag, Pangasinan | 340200 | [5 empty] | 2015-03-16 | 8917-1 | PR#2106
259 MT Asphalt in Asphalting of Pinmilapil Road | Sison, Pangasinan | 1582900 | [5 empty] | 2015-03-16 | 8917-1 | PR#1879
Asphalting of Amagbagan Road, | Sison, Pangasinan | 1972600 | [5 empty] | 2015-03-16 | 8917-1 | PR#1917
Asphalting of Poblacion road | Dama de Noche St. and Cemetery road, Mapandan, Pangasinan | 563600 | [5 empty] | 2015-03-16 | 8917-1 | PR#2184
Asphalting of Brgy. Macalong Road, | Asingan, Pangasinan | 861900 | [5 empty] | 2015-03-23 | 8917-1 | PR#1796
asphalting of Pantal Road, | Bugallon, Pangasinan | 2597500 | [5 empty] | 2015-03-23 | 8917-1 | PR#2261
Asphalting of various streets | Bayambang, Pangasinan | 4755300 | [5 empty] | 2015-03-23 | 8917-1 | PR#2807
Asphalting various streets at | Bayambang, Pangasinan | 3591400 | [5 empty] | 2015-03-23 | 8917-1 | PR#2730
construction of slope protection (Gabions) of the eroded riverbank along Shahani Road, | Brgy. Toboy, Asingan, Pangasinan | 4076795 | [5 empty] | 2015-04-10 | 8917-1 | PR#0903
Proposed Concrete paving along San Jacinto-Pozorrubio Road, Lobong Section, | San Jacinto, Pangasinan | 2692805 | [5 empty] | 2015-04-10 | 8917-1 | PR#0693
concreting of Sitio Cupang Road, | Brgy. Umanday, Bugallon, Pangasinan | 545054 | [5 empty] | 2015-03-19 | 3917 | PR#0704
100 units diesel engine water pump with complete accessories |  | 2400000
Loans Granted to various Multi-Purpose Cooperatives and Associations |  | 1000000 | [6 empty] | 8915
Tools needed for 2 drilling Team @ Waterworks Section, | PEO, Lingayen, Pangasinan | 173570.78 | [5 empty] | 2015-02-25 | 8919-2 | PR#0632
construction of 1 unit Deepwell Handpump at | Nalsian - Bacayao, Calasiao, Pangasinan | 113118 | [5 empty] | 2015-03-09 | 8919-2 | PR#0247
construction of one unit Artesian Well at | Brgy. Leet, Sta. Barbara, Pangasinan | 139921 | [5 empty] | 2015-03-09 |  | PR#0379
Environmental Development

## 2nd qtr (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2015
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks (Date of Obligation)
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE |  |  | REFERENCES
Social Development
Proposed Perimerer Fence | Ketegan E/S., Brgy. Ketegan, Bautista, Pangasinan | 1405947 |  |  | 100% | 1400624.67 |  | 60% paid 5/2015 40% paid 6/2015 | 6911 | Ranger Design & Constn PR#1202
Asphalting and blocktopping of RHU and Municipal Hall Compound | Urbiztondo, Pangasinan | 1505900 |  |  | 100% | 1504565 |  | Controlled 6-19-15 | 6911 | BET C/S PR#0036
Construction of Slope Protection | along Calarian Creek, Nursery, Tebag, Sta. Barbara, Pangasinan | 1446450 |  |  | 100% | 1444560 |  | Controlled 6-19-15 | 6911 | Goodvibe Builders PR#0614
construction of 2-Storey Multi-purpose Bldg. (ABC Building) Phase II, | Alvear Street, Lingayen, Pangasinan | 1861017 |  |  | 100% | 1676824.7 |  | 50% paid 5/2015 50% paid 6/2015 | 6911 | CAD Constn PR#0312
Construction of 1 unit 2-Storey Multi-Purpose Bldg., (Brgy. Hall) | Poblacion East, Bautista, Pangasinan | 2305855 |  |  | 100% | 2294562.38 |  | 50% paid 5/2015 50% paid 6/2015 | 6911 | Zota Trdg. & Constn PR#0763
Additional works of various of various buildings at EPDH | Tayug, Pangasinan | 2238748 |  |  | 100% | 2230830.79 |  | Paid 5/2015 | 6911 | BET Constn & Supply PR#0059
Renovation/Improvement of Pangasinan Internal Affair Service (PIAS) Building, PNP Headquarters | Lingayen, Pangasinan | 1146662 |  |  |  | 1142327.13 |  | 60% paid 5/2015 40% paid 6/2015 | 6911 | PR#1237
Improvement of CT Scan Room at Pangasinan Provincial Hospital | San Carlos City | 388107 |  |  | 100% | 385768.45 |  | Paid 6/2015 | 6911 | MCB C/S PR#0630
Construction of Philippine Affairs Office (Pangasinan Chapter), | Capitol Compound, Lingayen, Pangasinan | 1979401 |  |  | 100% | 1974587.28 |  | 50% paid 5/2015 50% paid 6/2015 | 6911 | CAD Constn PR#2456
Repair/Rehab of Repair Bay 1 and Office Building | Motorpool Compound, Lingayen, Pangasinan | 2593367.1 |  |  | 100% | 2587043.07 |  | 50% paid 5/2015 50% paid 6/2015 | 6911 | Ranger Design & Constn PR#1916
Concreting between Power house and Main Building @ Pozorrubio Community Hospital, | Pozorrubio, Pangasinan | 53873.5 |  |  |  | 53873.5 |  | Obligated | 6911 | PR#2234
Construction of materials Testing and Quality Control Bldg., | Motorpool Compound, Lingayen, Pangasinan | 1638590 |  |  |  | 1638590 |  | Obligated | 6911 | PR#0748
Completion of Senior Citizen Bldg., and Reconstruction of Perimeter Fence with Steel Gate and Concreting of Parking Space | Lingayen, Pangasinan | 1236108 |  |  |  | 1236108 |  | Obligated | 6911 | PR#4025
Concreting of Sitio Cristobal Farm to Market Road, | Brgy. Cabilocaan, Calasiao, Pangasinan | 3268546 |  |  |  | 3268546 |  | Obligated | 6911 | PR#2259
Concreting of Brgy, Auditorium (Floor Slab) | Brgy. Bolaoen, Bugallon, Pangasinan | 1222074 |  |  |  | 1222074 |  | Obligated | 6911 | PR#3266
Construction of Multi-purpose Gym (Phase 1) | Brgy. Camantiles, Urdaneta, Pangasinan | 500000 |  |  |  | 500000 |  | Obligated | 6911 | PR#4149
Repair/rehabilitation of Outpost | Brgy. Nacalobasaan, Urdaneta, Pangasinan | 200000 |  |  |  | 200000 |  | Obligated | 6911 | PR#4221
Repair/improvement of Day Care Center | Brgy. Pinmaludpod, Urdaneta City, Pangasinan | 300000 |  |  |  | 300000 |  | Obligated | 6911 | PR#4026
Repair/Restoration of Bengson-Yuson Bldg., Phase III | Lingayen, Pangasinan | 3751791 |  |  |  | 3751791 |  | Obligated | 6911 | PR#5360
Construction of Provincial Records and Archives Center | Capitol Compound, Lingayen, Pangasinan | 1999787 |  |  |  | 1999787 |  | Obligated | 6911 | PR#1793
Repair/rehabilitation and Construction of Deep Well Source | Namatucan,Agno, Pangasinan | 94205 |  |  |  | 94205 |  | Obligated | 8919-2 | PR#3335
Construction of 1 unit deepwell Handpump Level 1 (Sleeve converted) | Brgy. Bical Sur, Bayambang, Pangasinan | 53771 |  |  |  | 53771 |  | Obligated | 8919-2 | PR#4256
Construction of 1 unit deepwell Handpump (Level 1) | Maasin, Mangaldan, Pangasinan | 35805 |  |  |  | 35805 |  | Obligated | 8919-2 | PR#4253
Construction of 1 unit deepwell Source with Deepwell Motorpump at Manaoag Community Hospital | Manaoag, Pangasinan | 171928 |  |  |  | 171928 |  | Obligated | 8919-2 | PR#2857
Construction of 1 unit deepwell Handpump (Level 1) | Brgy. Banzal, Sta. Barbara, Pangasinan | 33622 |  |  |  | 33622 |  | Obligated | 8919-2 | PR#4255
Repair/replacement of Motorpump at Provincial Social Welfare Dev't Office | Poblacion, Lingayen, Pangasinan | 97283 |  |  |  | 97283 |  | Obligated | 8919-2 | PR#3333
Construction of 3 units deepwell (Level 1) Artesian Well | Brgy. Cabuloan, Urdaneta City | 399302 |  |  |  | 399302 |  | Obligated | 8919-2 | PR#4071
Installation of G.I. Pipes with cylinder brass Pump Assembly | Brgy. Linoc, Binmaley, Pangasinan | 40520 |  |  |  | 40520 |  | Obligated | 8919-2 | PR#4308
150 pcs. Jetmatic Pumps and GI Pipes | Distributed to different Barangays in Pangasinan | 1500750 |  |  |  | 1500300 |  | Obligated | 8919-2 | Jonemy Trdg. PR#5685
Jetmatic Pumps and GI Pipes | Distributed to different Barangays in Pangasinan | 1500000 |  |  |  | 1499520 |  | Obligated | 8919-2 | Lark Trdg. PR#5684
Jetmatic Pumps and GI Pipes | Distributed to different Barangays in Pangasinan | 1652550 |  |  |  | 1651950 |  | Obligated | 8919-2 | F & N C/S PR#5683
Equipment for various Community Hospitals |  | 10227000 |  |  |  | 10227000 |  | Obligated | 4918-1 | PR#6321
Equipment for various District Hospitals |  | 15000000 |  |  |  | 15000000 |  | Obligated | 4918-1 | PR#6787
Equipment for various District Hospitals |  | 9645000 |  |  |  | 9645000 |  | Obligated | 4918-1 | PR#6627
Equipment for various District Hospitals |  | 15115000 |  |  |  | 15115000 |  | Obligated | 4918-1 | PR#7025
Amortization of Principal and Interest |  | 55336869.38 |  |  |  | 55336869.38 |  | Obligated | 9921-1
Provision of Boulder Bank Protection along Marusay Bridge, Phase III | Brgy. Quesban, Calasiao, Pangasinan | 480303.98 |  |  |  | 480303.98 |  | Obligated | 8912-4 | PR#4560
Installation of 2 units airconditon and 1 set computer with printer at Lingayen Capital Senior Citizen Federation Bldg. | Lingayen, Pangasinan | 330891.11 |  |  |  | 330891.11 |  | Obligated | 3917 | PR#4009
Various materials for materials Testing and Quality Control Division (Tools and Equipments) | Province of Pangasinan | 1020320 |  |  |  | 1020320 |  | Obligated | 8917-3 | PR#3402
Brand New Water Well Drill Machine for Construction/Repair/Rehabilitation of various waterworks projects | Province of Pangasinan | 37000000 |  |  |  | 37000000 |  | Obligated | 8917-3 | PR#3576
Economic Development
Asphalting of Victorio-Pangascasan (Sual Coastal Road), Victoria Sec. | Alaminos City | 644000 |  |  | 100% | 643430 |  | Controlled 6-19-15 | 8917-1 | BET C/S PR#0157
Asphalting of Frank's Canteen Compound, | Lingayen, Pangasinan | 314800 |  |  | 100% | 314600 |  | Controlled 6-26-15 | 8917-1 | BET C/S PR#0212
Concreting and construction of slope protection (stone masonry) | Brgy. Poponto, Bautista, Pangasinan | 4175839 |  |  | 100% | 4170057.2 |  | 60% paid 5/2015 40% Paid-6/2015 | 8917-1 | Safeway C/S PR#0754
Construction of stone masonry | Brgy. Macalong, Asingan, Pangasinan | 3652065 |  |  | 60% | 2185596.72 |  | 60% paid 6/2015 | 8917-1 | Ranger Design PR#0398
Concreting of Tombor Road, Phase II | Binmaley, Pangasinan | 1794383 |  |  | 100% | 1786151.25 |  | 60% paid 5/2015 40% paid 6/2015 | 8917-1 | W.M. Salayog PR#0691
Construction of slope protection (Gabions) of the eroded riverbank | along Shahani Road, Brgy. Toboy, Asingan, Pangasinan | 4076795 |  |  |  | 4076795 |  | Obligated | 8917-1 | PR#0903
Proposed Concrete paving along San Jacinto-Pozorrubio Road, | Lobong Section, San Jacinto, Pangasinan | 2692805 |  |  |  | 2692805 |  | Obligated | 8917-1 | PR#0693
Concreting of Brgy. Bolaen, | Bugallon, Pangasinan | 1096696 |  |  |  | 1096696 |  | Obligated | 8917-1 | PR#3163
Improvement/blocktopping of Salingcaoet Road | Poblacion, Bugallon, Pangasinan | 2464200 |  |  |  | 2464200 |  | Obligated | 8917-1 | PR#3906
Improvement (Asphalting and blocktopping of Manambong-San Gabriell-Paragos Road | Bayambang, Pangasinan | 5274600 |  |  |  | 5274600 |  | Obligated | 8917-1 | PR#2473
Asphalting of Bantugan-Malasin Road, | Brgy. Bantugan, Pozorrubio, Pangasinan | 1762300 |  |  |  | 1762300 |  | Obligated | 8917-1 | PR#2094
Asphalting of Bical Sur Road, | Bayambang, Pangasinan | 1701800 |  |  |  | 1701800 |  | Obligated | 8917-1 | PR#3511
Asphalting of Access Road and Peripheral Area for Banca Parada 2015 | Brgy. Banaga, Bugallon, Pangasinan | 790400 |  |  |  | 790400 |  | Obligated | 8917-1 | PR#
Construction of CHB Open Canal with Concrete Barrier | Brgy. Tombor, Binmaley, Pangasinan | 1918704 |  |  |  | 1918704 |  | Obligated | 8917-1 | PR#3739
Asphalting/blocktopping of Namolan Road | Lingayen, Pangasinan | 2802300 |  |  |  | 2802300 |  | Obligated | 8917-1 | PR#4279
Asphalting Sitio Maburac Road, Brgy. Capulaan | Villasis, Pangasinan | 872900 |  |  |  | 872900 |  | Obligated | 8917-1 | PR#4965
Improvement/Asphalt repair of various farm to Market Roads | Mapandan, Pangasinan | 5932350 |  |  |  | 5932350 |  | Obligated | 8917-1 | PR#4010
Asphalting of Linmansangan-Santiago Brgy. Road | Binalonan, Pangasinan | 4876500 |  |  |  | 4876500 |  | Obligated | 8917-1 | PR#4230
Asphalting(blocktopping) of Cemetery Road, | Poblacion, Binalonan, Pangasinan | 957500 |  |  |  | 957500 |  | Obligated | 8917-1 | PR#5054
Blocktopping of Access Road going to Cemetery | Poblacion, San Nicolas, Pangasinan | 325800 |  |  |  | 325800 |  | Obligated | 8917-1 | PR#5034
Construction of Stone masonry for Protection Wall | Brgy. Caloocan Norte, Binmaley, Pangasinan | 1227040 |  |  |  | 1227040 |  | Obligated | 8917-1 | PR#5130
Reconstruction of Tumao Bridge | Bayambang, Pangasinan | 9226000 |  |  |  | 9226000 |  | Obligated | 8917-1 | PR#5757
Rehab/Improvement of Dupo Bridge | Brgy. Dupo, Binmaley, Pangasinan | 19409216 |  |  |  | 19409216 |  | Obligated | 8917-1 | PR#5564
Concreting of Sitio Cupang Road | Brgy. Umanday, Bugallon, Pangasinan | 545054 |  |  |  | 545054 |  | Paid 4-16-15 | 3917 | BET Constn PR#0704
Loans Granted to various Multi-Purpose Cooperatives and Associations |  | 1975000 |  |  |  | 1975000 |  |  | 8915
Environmental Development
Various spare parts of Dredging Machine at PEO | Lingayen, Pangasinan | 1126019.03 |  |  |  | 1126019.03 |  | Obligated | 8912-4 | PR#4558
Materials for the Extension/Improvement of Side Slope/Riverbank protection | Brgy. Talibaew, Calasiao, Pangasinan | 3137237 |  |  |  | 3137237 |  | Obligated | 8912-4 | PR#6583
Construction of drainage canal for the newly constructed nursery propagation structures | Sta. Barbara Provincial Nursery | 112187 |  |  |  | 112187 |  | Obligated | 8919 | PR#5310

## 20% IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
For the 4th Quarter, CY 2015
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks (Date of Obligation)
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE |  |  | REFERENCES
Social Development
Repair/Restoration of Bengson-Yuson Bldg., Phase III, | Lingayen, Pangasinan | 3512056.7 | 2015-08-28 | 2015-09-30 | 60% | 2107234.02 |  | 60% paid 5/2015 40% paid 6/2015 | 6911 | Ranger Design & Constn PR#1202
construction of Mini Grandstand with Concrete Bleachers @ Camp Tito Abat, | Manaoag, Pangasinan | 1271879.07 | 2015-09-21 | 2015-11-11 | 100% | 1271879.07 |  | Obligated | 6911 | BET C/S PR#0036
Construction of Storage Bldg., at Rehabilitation Center Phase 2, | Lingayen, Pangasinan | 2637227.9 | 2015-09-15 | 2015-11-27 | 100% | 2637227.9 |  | Obligated | 6911 | Goodvibe Builders PR#0614
214 MT Asphalt Pre-mix, 10 drum E. Asphalt - Asphalting of Access Road and Parking Area at Camp Abat, | Manaoag, Pangasinan | 1319830 | Materials Only |  |  | 1319830 |  | Obligated | 6911 | Zota Trdg. & Constn PR#0763
construction of CHB Retaining Wall with Gabions | Brgy. Tombor, Binmaley, Pangasinan | 2310734.73 | 2015-07-07 | Nov. 2015 |  | 692091.65 |  | Obligated | 6911 | BET Constn & Supply PR#0059
construction of Slope protection and Installation of RCCP, | Sitio Bogtong Silag, Brgy. Sta Cruz, San Jacinto, Pangasinan | 4106733 | Labor and Materials Only |  | 100% | 4106733 |  | Obligated | 6911 | PR#0748
repair/improvement of Sison Auditorium Bldg., | Lingayen, Pangasinan | 3993590.1 | Labor and Materials Only |  | 60% | 2396154.06 |  | Obligated | 6911 | PR#4221
completion of Health Center Bldg., | Brgy. Anambongan, Basista, Pangasinan | 931471.26 | Labor and Materials Only |  | 100% | 931471.26 |  | Obligated | 6911 | PR#4026
proposed construction of kitchen/dining at Camp Lt. Tito Abat, | Manaoag, Pangasinan | 1099372 | Labor and Materials Only |  | 70% | 765668.05 |  | Obligated | 6911 | PR#1793
repair/rehabilitation of Motor pool guard house building, Capitol complex, | Lingayen, Pangasinan | 205443.5 | Labor and Materials Only |  |  | 205443.5 |  | Obligated | 8919-2 | PR#3335
construction of Multi-purpose Building (Brgy. Hall) in | Brgy. Lilimasan, San Carlos City, Pangasinan | 1098425 | Labor and Materials Only |  |  | 1098425 |  | Obligated | 8919-2 | PR#4253
construction of Multi-purpose Gym (evacuation Center) | Brgy. Lipit, San Fabian, Pangasinan | 4069000 | Labor and Materials Only |  |  | 4069000 |  | Obligated | 8919-2 | PR#2857
upgrading of feederline and main distribution panel at | Bayambang District Hospital, Bayambang | 452195 | Labor and Materials Only |  |  | 452195 |  | Obligated | 8919-2 | PR#3333
construction of CHB Open Canal with Cross drainage | Brgy. Gayaman, Binmaley, Pangasinan | 2007116 | Labor and Materials Only |  | 80% | 1602418.3 |  | Obligated | 8919-2 | Lark Trdg. PR#5684
construction of Stone Masonry | Samiley St., Magtaking, Bugallon, Pangasinan | 233672 | Labor and Materials Only |  |  | 233672 |  | Obligated | 8917-3 | PR#3576
construction of Stone Masonry at Palinar St., | Brgy. Magtaking, Bugallon, Pangasinan | 1320308 | Labor and Materials Only |  |  | 1320308 |  | Obligated
1 drum emulsified asphalt and 16 MT Asphalt Pre-mix for the asphalting of pathway at GSP Headquarter, | Capitol Compound, Lingayen, Pang. | 102400 | Materials Only |  |  | 102400 |  | Obligated
6 units chainsaw for repair and clearing of Provincial Roads | Around Pangasinan | 324000 | Materials Only |  |  | 324000 |  | Obligated
Various materials for repainting of various concrete bridges | Around Pangasinan | 289807 | Labor and Materials Only |  |  | 289807 |  | Obligated
additional works for the renovation/improvement of Pangasinan Internal Affair Service (PIAS) Building, PNP Headquarters, | Lingayen, Pangasinan | 116059.42 | Labor and Materials Only |  | 100% | 116059.42 |  | Obligated
construction of Multi-Purpose Bldg. (Brgy. Hall) | Brgy. Poblacion, San Nicolas, Pangasinan | 1061576 | Labor and Materials Only |  |  | 1061576 |  | Obligated
replacement of waterproofing membrane of Capitol Compound, | Lingayen, Pangasinan | 2072299.32 | Labor and Materials Only |  |  | 2072299.32 |  | Obligated
repair/improvement of Veteran's Park, Capitol complex, | Lingayen, Pangasinan | 728841 | Labor and Materials Only |  |  | 728841 |  | Obligated
upgrading of the existing single phase to 3-phase & installation of MCB Panel, ATS Panel, Underground Feeder line Electrical Wiring | Lingayen District Hospital, Lingayen, Pangasinan | 6686100 | Labor and Materials Only |  |  | 6686100 |  | Obligated
finishing works of Evacuation/Multi-Purpose Center, | Aguilar, Pangasinan | 4650220 | Labor and Materials Only |  |  | 4650220 |  | Obligated
Proposed Construction of Senior Citizen Bldg., | Brgy. Tulong, Urdaneta, Pangasinan | 637873 | Labor and Materials Only |  |  | 637873 |  | Obligated
construction of covered patchways w/ steel gate railings and Concrete benches at Senior Citizen Bldg., | Laguit Centro, Bugallon, Pangasinan | 249360 | Labor and Materials Only |  |  | 249360 |  | Obligated
construction of covered Court Phase I | Brgy. Galarin, Urbiztondo, Pangasinan | 2000000 | Labor and Materials Only |  |  | 2000000 |  | Obligated
Materials for the assistance for Canal Rehabilitation & Extension | Don Vicente Dam, Brgy. Bobonan, Pozorrubio | 299619 | Materials Only |  |  | 299619 |  | Obligated
rehab/improvement of 1 cl of existing 4 cl School Building | Ambonao Elem. School, Calasiao | 307645 | Materials Only |  |  | 307645 |  | Obligated
500 pcs. 20 mm x 30' corrugated steel bars for construction/expansion of facility of Dagupan City Jail | Dagupan City | 420000 | Labor and Materials Only |  |  | 420000 |  | Obligated
repair/improvement of one unit 1 CL SB at Calit E/S, | Binmaley, Pangasinan | 204034 | Labor and Materials Only |  |  | 204034 |  | Obligated
repair/improvement of one unit 2-CL SB at Carot NH/S, | Anda, Pangasinan | 204964 | Labor and Materials Only |  |  | 204964 |  | Obligated
Materials, labor, and other incidentals for the repainting of one 7-CL SB at Samson-Bengson E/S, Lingayen, Pangasinan |  | 134728 | Materials and Labor Only |  |  | 134728 |  | Obligated
repair/rehabilitation of school building at Bolo E/S, 1 unit 3-CL SB, 1 unit, 5-CL SB | San Jacinto, Pangasinan, | 447017 | Labor and Materials Only |  |  | 447017 |  | Obligated
improvement/extension of covered court at Lasip E/S, | Lingayen, Pangasinan | 486151 | Labor and Materials Only |  |  | 486151 |  | Obligated
repair/improvement of Grade III at Tampog E/S, | Bayambang, Pangasinan | 314837 | Labor and Materials Only |  |  | 314837 |  | Obligated
raising of flood prone Area At Tandoc NH/S, | San Carlos City, Pangasinan | 370042 | Labor and Materials Only |  |  | 370042 |  | Obligated
construction of stone masonry | Brgy. Macalong, Asingan, Pangasinan | 325781 | Labor and Materials Only |  |  | 325781 |  | Obligated
construction of Artesian Well at Brgy. Calanutan, | San Nicolas, Pangasinan | 232000 | Labor and Materials Only |  |  | 232000 |  | Obligated
construction of Artesian Well | Brgy. Labit East, Urdaneta, Pangasinan | 130300 | Labor and Materials Only |  |  | 130300 |  | Obligated
pest control treatment of Sison Auditorium Bldg., Lingayen, GSP Bldg., BSP Bldg., Lingayen, Dasol Community Hospital | Lingayen, and Dasol,Pangasinan | 469932 | Materials Only |  |  | 469932 |  | Obligated
Extension of 1-Phase Line & Installation of 1-25 KVA DX Transformer and Electrical Service (Sole User) for Aplaya Housing Project | Pangapisan North, Lingayen | 252252.55 | Labor and Materials Only |  |  | 252252.55 |  | Obligated
construction of 3 units Housing for electric Motor Power System | San Gonzales, San Quintin | 845760 | Labor and Materials Only |  | 80% | 672927.4 |  | Obligated
Extensin/Improvement of Side Slope/Riverbank protection | Brgy. Talibaew, Calasiao, Pangasinan | 3121632 | Labor and Materials Only |  | 100% | 3121632 |  | Obligated
provision of Boulder Bank Protection along Marusay Bridge, Phase III, (part of P4,496,227.00 - continuing) | Brgy. Quesban, Calasiao, Pangasinan | 480303.98 | Labor and Materials Only |  |  | 480303.98 |  | Obligated
construction of one unit Artesian Well | Brgy. Leet, Sta. Barbara, Pangasinan | 139051.7 | Labor and Materials Only |  |  | 139051.7 |  | Obligated
repair/rehabilitation and Construction of Deep Well Source, | Namatucan,Agno, Pangasinan | 94105 | Labor and Materials Only |  |  | 94105 |  | Obligated
construction of 1 unit deepwell Handpump Level 1 (Sleeve converted) | Brgy. Bical Sur, Bayambang, Pangasinan | 53721 | Materials Only |  |  | 53721 |  | Obligated
construction of 1 unit deepwell Handpump (Level 1) | Maasin, Mangaldan, Pangasinan | 35730 | Materials Only |  |  | 35730 |  | Obligated
construction of 1 unit deepwell Handpump (Level 1) | Brgy. Banzal, Sta. Barbara, Pangasinan | 33522 | Materials Only |  |  | 33522 |  | Obligated
construction of 3 units deepwell (Level 1) Artesian Well | Brgy. Cabuloan, Urdaneta City | 370777.77 | Materials Only |  |  | 370777.77 |  | Obligated
Economic Development | [7 empty] | Obligated
184 M.T. Asphalt Pre-Mix, 6 drums Emulsified Asphalt for the Proposed Blocktopping of hacienda Brgy. Road, | Bugallon, Pangasinan | 1097420 | Materials Only |  | 100% | 1097420 |  | Obligated | 8919-2 | PR#4071
483 MT Asphalt Pre-mix and 15 drums E. Asphalt - proposed Patching and blocktopping of Brgy. Road and Brgy. San Isidro Norte | Binmaley, Pangasinan | 2869935 | Materials Only |  | 100% | 2869935 |  | Obligated | 8919-2 | PR#4308
concreting of Camanang Road, | Urdaneta City, Pangasinan | 1210999.6 |  |  | 100% | 1210999.6 |  | Obligated | 8919-2 | F & N C/S PR#5683
236 MT Asphalt Pre-mix and 7 drums E. Asphalt - blocktopping | Everlasting St., Mapandan, Pangasinan | 1397550 | Materials Only |  | 100% | 1397550 |  | Obligated | 4918-1 | PR#6787
300 MT Asphalt Pre-mix and 18 drums E. Asphalt - Routinary Maintenance (Patching & blocktopping) of Capitol Cmpd. Road Network, | Lingayen, Pangasinan | 1907520 | Materials Only |  | 100% | 1907520 |  | Obligated | 4918-1 | PR#6627
7 drums E. Asphalt, 162 MT Asphalt Pre-mix for the Asphalting of Road leading to PSWDO Bldg., LDH Cmpd., | Lingayen, Pangasinan | 990920 | Materials Only |  | 100% | 990920 |  | Obligated | 4918-1 | PR#7025
327 MT Asphalt Pre-mix and 14 drums e. Asphalt - Asphalting of Road Network at OPAG Cmpd., | Sta. Barbara, Pangasinan | 1998325 | Materials Only |  | 100% | 1998325 |  | Obligated | 9921-1
Improvement/Widening/Concreting of farm to market road, | Brgy. Anonang, San Fabian, Pangasinan | 4152556 |  |  | 50% | 2074799.19 |  | Obligated | 8912-4 | PR#4560
Asphalting/blocktopping of various roads, | Mangaldan, Pangasinan | 5033110 |  |  | 100% | 5033110 |  | Obligated | 3917 | PR#4009
18 drums Emulsified Asphalt and 587 Asphalt Pre-mix for the proposed asphalting/blocktopping of Municipal/ Brgy. Streets, | Urbiztondo, Pangasinan | 3487700 | Materials Only |  |  | 3487700 |  | Obligated | 8917-3 | PR#3402
Materials, labor and equipment and other incidentals necessary for the restoration of Damaged foot path | Brgy. Turac East, San Carlos City | 690370 | Labor and Materials Only |  |  | 690370 |  | Obligated
Materials, labor and other incidentals for the riprapping of Aroo Br. Approach along Malasiqui-Catablan Rd., | Bolaoet, Malasiqui, Pangasinan | 1988069.01 | Labor and Materials Only |  |  | 1988069.01 |  | Obligated
3 drums E. Asphalt and 92 MT Asphalt Pre-mix for the proposed blocktopping of Brgy. Road | Talostang, Malasiqui, Pangasinan | 549200 | Materials Only |  |  | 549200 |  | Obligated
101 MT Asphalt Pre-mix, 3 drums E. Asphalt in the improvement/blocktopping of Brgy. Vacante Rd. | Binalonan, Pangasinan | 598700 | Materials Only |  |  | 598700 |  | Obligated
12 drums Emulsified Asphalt,405 MT Asphalt Pre-Mix |  | 2400300 | Materials Only |  |  | 2400300 |  | Obligated
30 drums E. Asphalt, 658 MT Asphalt Pre-mix in Asphalting/blocktopping of Baay Road, | Lingayen, Pangasinan | 4051000 | Materials Only |  |  | 4051000 |  | Obligated
22 drums E. Asphalt and 512 MT asphalt Pre-mix in the asphalting of Capandanan Road, | Lingayen, Pangasinan | 3132800 | Materials Only |  |  | 3132800 |  | Obligated
16 drums E. Asphalt, 383 M.T. Asphalt Pre-mix in Asphalting of Cabacaraan Road, | San Manuel, Pangasinan | 2336900 | Materials Only |  |  | 2336900 |  | Obligated
16 drums E. Asphalt, 535 M.T. Asphalt Pre-mix in blocktopping of various streets, | Poblacion, Aguilar, Pangasinan | 3172900 | Materials Only |  |  | 3172900 |  | Obligated
23 drums E. Asphalt, 518 MT Asphalt Pre-mix for the asphalting of Tagudin Rd., | Brgy. Tagudin, Mabini, Pangasinan | 3180200 | Materials Only |  |  | 3180200 |  | Obligated
10 drums Emulsified asphalt and 227 MT Asphalt Pre-mix for the Proposed Asphalting of various Roads | Brgy. Don Pedro, Malasiqui, Pangasinan | 1392500 | Materials Only |  |  | 1392500 |  | Obligated
459 MT Asphalt Pre-mix, for the asphalt overlay of Parking Area of Palaris Bldg., ( fronting LTO) & nrscc Complex, | Lingayen, Pangsinan | 2524500 | Materials Only |  |  | 2524500 |  | Obligated
12 drums E. Asphalt and 395 MT Asphalt Pre-mix for the proposed blocktopping at Sitio Samiley-Pandel Road, | Domalandan East, Lingayen, Pangasinan | 2345300 | Materials Only |  |  | 2345300 |  | Obligated
construction of RCCP drainage canal | Burgos St., Poblacion, Binmaley, Pangasinan | 1607645 |  |  |  | 1607645 |  | Obligated
Improvement/rehabilitation of Mapandan-Urdaneta Rd., | Mapandan | 201795.23 |  |  |  | 201795.23 |  | Obligated
concreting of Urdaneta-Asingan-Tayug Rd., Ariston East, West, | Asingan | 1530509.47 |  |  |  | 1530509.47 |  | Obligated
3 drums E. Asphalt and 115 MT Asphalt Pre-mix for the improvement/patching blocktopping of San Carlos-Aguilar Road (Aguilar Section), Bocboc East, | Aguilar, Pangasinan | 675700 | Materials Only |  |  | 675700 |  | Obligated
23 drums E. Asphalt, 592 MT Asphalt Pre-mix for the asphalting/blocktopping of Asan Norte Road, Pinmilapil Road (going to Cemetery) and Esperanza Road, | Sison, Pangasinan | 3587200 | Materials Only |  |  | 3587200 |  | Obligated
17 drums Emulsified asphalt and 552 MT Asphalt pre-mix in blocktopping of San Miguel-San Macario Road, | Natividad, Pangasinan | 3280800 | Materials Only |  |  | 3280800 |  | Obligated
concreting of Brgy. Road, | San Miguel, Calasiao, Pangasinan | 2192634 |  |  |  | 2192634 |  | Obligated
115 MT Asphalt Pre-mix, 4 drums E. Asphalt - blocktopping | Brgy. Gais-Guipe Road, Dasol, Pangasinan | 690100 | Materials Only |  |  | 690100 |  | Obligated
concreting of Parian - Bantocaling - Bantay Road, | Mangatarem, Pangasinan | 185911 |  |  |  | 185911 |  | Obligated
improvement/rehabilitation of Bued-Ambonao Road, | Calasaiao | 56731.97 |  |  |  | 56731.97 |  | Obligated
590 MT Asphalt Pre-mix and 24 drums E. Asphalt for the asphalting/blocktopping | San Antonio Road, Alaminos City, Pangasinan | 3590600 | Materials Only |  |  | 3590600 |  | Obligated
520 MT Asphalt Pre-mix and 19 drums E. Asphalt for the asphalting | San Agustin Rd., Sto. Tomas, Pangasinan | 3133600 | Materials Only |  |  | 3133600 |  | Obligated
518 MT Asphalt Pre-mix and 23 drums Emulsified Asphalt for asphalting | Quibuar Road, Alaminos City | 3180200 | Materials Only |  |  | 3180200 |  | Obligated
13 drums E. Asphalt and 299 MT Asphalt Pre-mix for the asphalting | Sta. Maria Norte Road, Binalonan, Pangasinan | 1831700 | Materials Only |  |  | 1831700 |  | Obligated
100 units diesel engine water pump with complete accessories |  | 2396800 | Materials Only |  |  | 2396800 |  | Obligated
construction of Reinforced Concrete Deck Girder (RCDG) Bridge | Brgy. Bolo, San Jacinto, Pangasinan | 7041673.85 |  |  | 60% | 4225004.31 |  | Obligated | 6911 | PR#2234
Loans Granted to various Multi-Purpose Cooperatives and Associations |  | 4725000 | Loans Only |  |  | 4725000 |  | Obligated | 8917-1 | BET C/S PR#0157
construction/installation of 20 units STWIP | various barangays/municipalities/cities of San Carlos, Bugallon, and Aguilar, Pangasinan | 4762382 | Materials Only |  |  | 4762382 |  | Obligated | 8917-1 | BET C/S PR#0212
construction/installation of 17 units STWIP in | various barangays/municipalities of Mangaldan, Manaoag, Sn. Fabian, San Jacinto, Laoac, Pangasinan | 4048024.7 | Materials Only |  |  | 4048024.7 |  | Obligated | 8917-1 | Safeway C/S PR#0754
construction/installation of 15 units STWIP | various barangays in Bautista, Pangasinan | 3571786.5 | Materials Only |  |  | 3571786.5 |  | Obligated | 8917-1 | Ranger Design PR#0398
construction/installation of 17 units STWIP | various barangays and municipalities of Urbiztondo and Basista, Pangasinanj | 4048024.7 | Materials Only |  |  | 4048024.7 |  | Obligated | 8917-1 | W.M. Salayog PR#0691
construction/installation of 20 units STWIP | various barangays and municipalities of Bayambang, San Carlos City, and Malasiqui, Pangasinan | 4762382 | Materials Only |  |  | 4762382 |  | Obligated | 8917-1 | PR#0903
construction/installation of 18 units STWIP | various barangays of Urbiztondo and Basista, Pangasinan | 4286143.8 | Materials Only |  |  | 4286143.8 |  | Obligated | 8917-1 | PR#0693
construction/installation of 19 units STWIP in | various barangays and municipalities of Agno, Bolinao, Sual, Dasol and Alaminos, Pangasinan | 4524262.9 | Materials Only |  |  | 4524262.9 |  | Obligated | 8917-1 | PR#3163
construction/installation of 16 units STWIP | various barangays and municipalities of Alcala, Binalonan and Pozorrubio, Pangasinan | 3809905.6 | Materials Only |  |  | 3809905.6 |  | Obligated | 8917-1 | PR#3906
Various materials, construction/installation of 16 units STWIP | various barangays and municipalities of Sison, Sto. Tomas, Villasis, Sta. Maria, San Quintin, Umingan, San Nicolas and Tayug, Pangasinan | 3809905.6 | Materials Only |  |  | 3809905.6 |  | Obligated | 8917-1 | PR#2473
Rehabilitation/Improvement of Dupo Bridge, | Brgy. Dupo, Binmaley, Pangasinan | 18196139.21 |  |  | 15% | 1807050 |  | Obligated | 8917-1 | PR#2094
improvement/rehabilitation of Bued-Ambonao Road, | Calasiao, Pangasinan | 2740559 |  |  | 70.09% | 2732634.1 |  | Obligated | 8917-1 | PR#3511
concreting of Mabini Breeding Station Road, | Mabini, Pangasinan | 6290200 |  |  | 15% | 941550 |  | Obligated | 8917-1 | PR#
Improvement/rehabilitation of Mapandan - Urdaneta Road, | Mapandan, Pangasinan | 29926788 |  |  | 100% | 29926788 |  | Obligated | 8917-1 | PR#3739
concreting of Road and construction of drainage canal along Casantamarian - Dipalo Road, | San Quintin, Pangasinan | 16769372 |  |  | 40.1% | 6720100 |  | Obligated | 8917-1 | PR#4279
concreting of Parian - Bantocaling - Bantay Road, | Mangatarem, Pangasinan | 7439300 |  |  | 90% | 6685254.5 |  | Obligated | 8917-1 | PR#4965
Improvement/rehabilitation of Calasiao - Railroad Station, | Calasiao, Pangasinan | 1786750 |  |  | 15% | 267000 |  | Obligated | 8917-1 | PR#4010
pment and other incidentals for the Improvement/rehabilitation of Manaoag - Mapandan Road, | Manaoag, Pangasinan | 36583500 |  |  | 15% | 5482500 |  | Obligated | 8917-1 | PR#4230
concreting of Olo - Naguilayan Road, | Mangatarem, Pangasinan | 16095600 | 03-24-14 |  | 50.98% | 8196722.03 |  | Obligated
Materials, labor, equipment and other incidentals for the concreting of Urdaneta - Asingan - Tayug Road, Ariston East and West, | Asingan, Pangasinan | 16274141 | Labor and Materials Only |  | 90% | 14633965.44 |  | Obligated
219 MT Asphalt Pre-mix 7 drums E. Asphalt - Asphalting of Dangley- Aloleng - Mamio Road, | Agno, Pangasinan | 1305300 | Materials Only |  | 15% | 195000 |  | Obligated
1524 MT Asphalt Pre-mix, 66 drums E. Asphalt - Asphalting of Rajal - Esmeralda Road, | Balungao, Pangasinan | 9332400 | Materials Only |  | 15% | 1398618 |  | Obligated
2547 MT Asphalt Pre-mix and 95 drums E. Asphalt - Improvement/Rehabilitation of Bani - Mabini Road, | Bani and Mabini, Pangasinan | 15376500 | Materials Only |  | 15% | 2304422.25 |  | Obligated
1642 MT Asphalt Pre-mix and 71 drums E. Asphalt - Improvement/Rehabilitation of Poponto - Villanueva Road, | Bautista, Pangasinan | 10053400 | Materials Only |  | 15% | 1506672 |  | Obligated
1150 MT Asphalt Pre-mix and 50 drums E. Asphalt - Improvement/rehabilitation of Bayambang - Urbiztondo Road, | Bayambang, Pangasinan | 7045000 | Materials Only |  | 15% | 1055812.5 |  | Obligated
1398 MT Asphalt Pre-mix and 61 drums E. Asphalt - Improvement/rehabilitation of Binalonan-San Manuel Road, | Binalonan, Pangasinan | 8567400 | Materials Only |  | 15% | 1283970 |  | Obligated
1806 MT Asphalt Pre-mix, 79 drums E. Asphalt Asphalting of Burgos-Iliw-Iliw Road, | Burgos, Pangasinan | 11070600 | Materials Only |  | 15% | 1659117 |  | Obligated
690 MT Asphalt Pre-mix, 30 drums E. Asphalt - Asphalting of Patar - Capandanan Road, | Mabini, Pangasinan | 4227000 | Materials Only |  | 15% | 633487.5 |  | Obligated
621 MT Asphalt Pre-mix, 27 drums E. Asphalt - Improvement/rehabilitation of Mapandan-Urdaneta Road, | Manaoag, Pangasinan | 3804300 | Materials Only |  | 15% | 570000 |  | Obligated
1518 MT Asphalt Pre-mix and 66 drums E. Asphalt - Improvement/rehabilitation of Pao-Pozorrubio Road, | Manaoag, Pangasinan | 9299400 | Materials Only |  | 15% | 1393672.5 |  | Obligated
621 MT Asphalt Pre-mix, and 19 drums E. asphalt - blocktopping of Licsi-Manaoag Sugar Central Road, | Manaoag, Pangasinan | 3689100 | Materials Only |  | 100% | 3685805 |  | Obligated
1719 MT Asphalt Pre-mix and 52 drums E. Asphalt - Improvement/rehabiitation (blocktopping) of Mapandan-Manaoag Road, | Mapandan, Pangasinan | 10203300 | Materials Only |  | 15% | 1529127.75 |  | Obligated
806 MT Asphalt Pre-mix and 35 drums E. Asphalt - Improvement/blocktopping of Mapandan-Urdaneta road, | Mapandan, Pangasinan | 4937000 | Materials Only |  | 15% | 739893 |  | Obligated
1380 MT Pre-mix and 60 drums E. Asphalt - Improvement/rehabilitation of San Jacinto-Pozorrubio Road, | Pozorrubio, Pangasinan | 8454000 | Materials Only |  | 15% | 1266975 |  | Obligated
966 MT Asphalt Pre-mix and 42 drums E. Asphalt - Improvement/rehabilitation of Pozorrubio-Sogcong Road, | Pozorrubio, Pangasinan | 5917800 | Materials Only |  | 15% | 886882.5 |  | Obligated
966 MT Asphalt Pre-mix and 42 drums E. Asphalt - Improvement/rehabilitation of Salvacion-San Vicente Road, Rosales, Pangasinan |  | 5917800 | Materials Only |  | 15% | 886882.5 |  | Obligated
1725 MT Asphalt Pre-mix and 75 drums E. Asphalt -Asphalting of Urbiztondo-San Carlos Road, | San Carlos City | 10567500 | Materials Only |  | 15% | 1583718.75 |  | Obligated
690 MT Asphalt Pre-mix, and 30 drums E. Asphalt - Improvement/rehabilitation of Asingan-San Manuel-Agno Gorge Road, | San Manuel, Pangasinan | 4227000 | Materials Only |  | 15% | 632949 |  | Obligated
414 MT Asphalt and 14 drums E. Asphalt - Improvement/rehabilitation of Poblacion Natividad-Salud-Sta. Maria Road, | Natividad,Pangasinan | 2478600 | Materials Only |  | 15% | 371458.5 |  | Obligated
380 MT Asphalt Pre-mix and 17 drums E. Asphalt - Improvement/rehabilitation of Batakil-Sison Road, | Sison, Pangasinan | 2334800 | Materials Only |  | 15% | 349500 |  | Obligated
828 MT Asphalt Pre-mix, 36 drums E. Asphalt - Asphalting of Cabatuan-Nampalcan Road, | Umingan, Pangasinan | 5072400 | Materials Only |  | 15% | 760185 |  | Obligated
2422 MT Asphalt Pre-mix, 104 drums E. Asphalt - Asphalting of San Juan-Resurreccion Road, Umingan, Pangasinan |  | 14818600 | Materials Only |  | 15% | 2220817.5 |  | Obligated
828 MT Asphalt Pre-mix, 36 drums E. Asphalt - Asphalting of Villabantog-Calitlitan Road, | Umingan, Pangasinan | 5072400 | Materials Only |  | 15% | 760185 |  | Obligated
472 MT Asphalt Pre-mix, 21 drums E. Asphalt - Asphalting of Cadamortisan-Diket Road, | Umingan, Pangasinan | 2898400 | Materials Only |  | 15% | 434374.5 |  | Obligated
1472 MT Asphalt Pre-mix and 64 drums E. Asphalt - Improvement/rehabilitation of Nancalobasaan-Cabalitian Road, Umingan, Pangasinan | Umingan, Pangasinan | 9017600 | Materials Only |  | 15% | 1351440 |  | Obligated
1035 MT Asphalt Pre-mix and 45 drums E. Asphalt - Improvement/rehabilitation of Urbiztondo-Bayambang Road, | Urbiztondo, Pangasinan | 6340500 | Materials Only |  | 15% | 950231.25 |  | Obligated
1104 MT Asphalt Pre-mix and 48 drums E. Asphalt - Improvement/rehabilitation of Urdaneta-Manaoag Rd., | San Vicente, Urdaneta, Pangasinan | 6763200 | Materials Only |  | 15% | 1013580 |  | Obligated
621 MT Asphalt Pre-mix and 27 drums E. Asphalt - Improvement/rehabilitation of Urdaneta-Asingan Road, via Calepaan, | Urdaneta City, Pangasinan | 3804300 | Materials Only |  | 100% | 3800000 |  | Obligated
690 MT Asphalt Pre-mix and 30 drums E. Asphalt - Improvement/rehabilitation of Urdaneta-Cili Jct. Road, | Urdaneta City, Pangasinan | 4227000 | Materials Only |  | 100% | 4223250 |  | Obligated
1265 MT Asphalt Pre-mix, 39 drums E. Asphalt - blocktopping of Tayug - Natividad Road (with Exemptions), | Natividad, Pangasinan | 7519100 | Materials Only |  | 100% | 1126857.75 |  | Obligated
Materials, labor, and other incidentals for the new construction of Lokeb RCDG ( to replace , existing Bridge), | Malasiqui, Pangasinan | 23270274 | Labor and Materials Only |  |  |  |  | Obligated
Materials for materials Testing and Quality Control Division in the Province (Tools and Equipments) |  | 1019500 | Materials Only |  | 100% | 1019500 |  | Obligated | 8917-1 | PR#5054
Materials, labor and other incidentals for proposed concrete paving of Brgy. Balingasay Rd., | Bolinao, Pangasinan | 12010567 | Labor and Materials Only |  | 55.99% | 6718283.72 |  | Obligated | 8917-1 | PR#5034
Obligated
Environmental Development | [7 empty] | Obligated
Materials for the construction of drainage canal for the newly constructed nursery propagation structures at the Sta. Barbara Provincial Nursery | Sta. Barbara, Pangasinan | 112087 | Materials Only |  |  | 112087 |  | Obligated | 8912-4 | PR#4558
40000 pcs. Mangrove propagules ( Bakawan Babae, Bakawan Lalaki, Baowan Bato) propagation of Mangrove, Bolinao Prov'l Mangrove Nursery, Arnedo, 3rd Qtr, CY 2015 | Bolinao, Pangasinan | 58800 | Materials Only |  |  | 58800 |  | Obligated | 8912-4 | PR#6583
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
AMADO T. ESPINO, JR.
Governor

## STATEMENT OF DEBT.SERVICE
FDP Form 2 - Statement of Debt Service
(DBM-LBP Form No. 6)
ANNEX "F"
Republic of the Phillippines
Province of Pangasinan
General Fund
For the Year 2016
| Date |  | Principal | Previous Payment |  |  | Amount Due |  |  | Balance of the
Creditor | Contracted | Term | Amount |  | Made |  | (Budget Year) |  |  | Principal
|  |  |  | Principal | Interest | Total | Principal | Interest | Total
Land Bank of the | 2008-06-23 | 5 years | 343544988.37 | 343544988.37 | 88617084.83 | 432162073.2 | - | - | - | -
Philippines | 2008-08-19 | 7 years | 79249686 | 79249686 | 26126922.25 | 105376608.25 | 11321384 | 1033076.11 | 12354460.11 | 0
Dagupan Branch | 2009-12-11 | 10 years | 149942779.08 | 81827605.42 | 34929903.32 | 116757508.74 | 17029043.48 | 6556181.72 | 23585225.2 | 68115173.66
| 2010-05-14 | 7 years | 97255640 | 76415145.66 | 22899284.89 | 99314430.55 | 11908853.9 | 2917669.2 | 14826523.1 | 20840494.34
| 2010-02-19 | 5 years | 75437000 | 75437000 | 8197117.81 | 83634117.81 | 16143606.49 | 1695078.68 | 17838685.17 | 0
| 2009-12-17 | 10 years | 143108017.99 | 75276322.05 | 31750517.23 | 107026839.28 | 17370319.08 | 6687572.85 | 24057891.93 | 67831695.94
| 2010-06-28 | 8 years | 185854705 | 154877920 | 50210910.14 | 205088830.14 | 30975534 | 5265951.37 | 36241485.37 | 30976785
| 12//2012 | 10 years | 50228784.65 | 11161952.24 | 8381512.09 | 19543464.33 | 5580976.12 | 3320680.76 | 8901656.88 | 39066832.41
| 12//2012 | 10 years | 116914066.26 | 24803853.1 | 16996188.52 | 41800041.62 | 15439322.62 | 7835456.23 | 23274778.85 | 92110213.16
| 2014-03-28 | 10 years | 12300000 | 1025000.01 | 709882.73 | 1734882.74 | 1366666.67 | 676500 | 2043166.67 | 11274999.99
|  |  | 6058050 | 0 | 167052.8 | 167052.8 | 10374666.67 | 5135460 | 15510126.67 | 6058050
|  |  | 6657000 | 0 | 183569.05 | 183569.05 | 4931111.11 | 2440900 | 7372011.11 | 6657000
|  |  | 154619368.64 | 0 | 614410.18 | 614410.18 | 1321428.57 | *8,250,000.00 | 9571428.57 | 154619368.64
|  |  | 1807050 | 0 | 0 | 0 | 0 | * | 0 | 1807050
|  |  | 776047.9 | 0 | 0 | 0 | 0 | * | 0 | 776047.9
|  |  | 36950000 | 1319642.86 | 506670.55 | 1826313.41 | 0 | 2035000 | 2035000 | 35630357.14
| TOTAL |  | 1460703183.89 | 924939115.71 | 290291026.39 | 1215230142.1 | 143762912.71 | 53849526.92 | 197612439.63 | 535764068.18
* The Interest Annual Amortization for 2015 from the approved OTLF2
We hereby certify that we have reviewed the contents and hereby attest to the veracity and
correctness of the data or information contained in this document.
ARTURO V. SORIANO | [7 empty] | AMADO T. ESPINO, JR.
Provincial Accountant | [7 empty] | Governor

## LDRRMC
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
For the Quarter OCTOBER - DECEMBER, CY 2015
Province of Pangasinan
LDRRMF
Particulars | Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 43528583.4 | 101566694.6 |  |  |  | 145095278
Continuing Appropriation | [5 empty] | 0
Previous Year's Appropriation transferred to the Special Trust Fund |  | 45024785.74 |  |  |  | 45024785.74
Transfers/Grants | [5 empty] | 0
Others ( Please specify) | [5 empty] | 0
Total Funds Available | 43528583.4 | 146591480.34 | 0 | 0 | 0 | 190120063.74
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies |  | 262400 |  |  |  | 262400
Office Supplies |  | 315550 |  |  |  | 315550
Repair of Evacuation Center | [5 empty] | 0
Institutional/Capacity Development ( Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses | 7040010 | 61458714.7 |  |  |  | 68498724.7
Traveling Expense |  | 184422.98 |  |  |  | 184422.98
Training Expense |  | 10000 |  |  |  | 10000
IT Equipment & Software |  | 492487.5 |  |  |  | 492487.5
Motor Vehicles | [5 empty] | 0
Other Machineries and Equipment |  | 2076000 |  |  |  | 2076000
Watercrafts |  | 8460840
Other Property, Plant and Equipment | [5 empty] | 0
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment | [5 empty] | 0
Gasoline, Oil, Lubricants |  | 789538.29 |  |  |  | 789538.29
Furniture & Fixtures |  | 76800 |  |  |  | 76800
Donations | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. |  | 22842547 |  |  |  | 22842547
Repair & Maintenance-Motor Vehicles |  | 164532.5 |  |  |  | 164532.5
Total Utilization | 7040010 | 97133832.97 | 0 | 0 | 0 | 104173842.97
Unutilized Balance | 36488573.4 | 49457647.37 | 0 | 0 | 0 | 85946220.77
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information containedin this document.
ARTURO V. SORIANO
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending December 31, 2015
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 366019411.97
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
125194523.75
Capital Outlay
87566889.56
Financial Expenses
-0-
Sub-total |  |  |  | 212761413.31
Balance |  |  |  | 153257998.66
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
AMADO T. ESPINO, JR.
Governor

## CASH.FLOWS
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
Statement of Cash Flows
General Fund
For the Year Ended December 31,2015
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers | 214309594.13
|  | Share from Internal Revenue Allotment | 2441069275
|  | Receipts from business/service income | 326828665.88
|  | Interest Income | 3734385.11
|  | Dividend Income | 0
|  | Other Receipts | 610258057.11
|  | Total Cash Inflow | 3596199977.23
Cash Outflows:
|  | Payment of expenses | 1346429230.52
|  | Payment to suppliers and creditors | 452034517.45
|  | Payment to employees | 661100108.37
|  | Interest Expenses | 31055163.34
|  | Other Expenses | 173230196.03
|  | Total Cash Outflow | 2663849215.71
| Net Cas Flows from Operating Activities |  |  | 932350761.52
Cash Flows from Investing Activities:
Cash Inflows:
|  | Proceeds from Sale of Investment Property | 0
|  | Proceeds from Sale/Disposal of Property, Plant and | 0
Equipment
|  | Proceeds from Sale of Non-Current Investments | 0
|  | Collection of Principal on Loans to other Entities | 8816240
|  | Total Cash Inflow | 8816240
Cash Outflows:
|  | Purchase / Construction of Investment Property | 0
|  | Purchase / Construction of Property, Plant and | 545806247.57
Equipment
|  | Investment | 38797500.23
|  | Purchase of Bearer Biological Assets | 0
|  | Purchase of Intangible Assets | 0
|  | Grant of Loans | 5990000
|  | Total Cash Outflow | 590593747.8
| Net Cash Flows from Investing Activities |  |  | -581777507.8
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Issuance of Bonds | 0
|  | Proceeds from Loans | 213203616.54
|  | Total Cash Inflow | 213203616.54
Cash Outflows:
|  | Payment of Long-Term Liabilities | 0
|  | Retirement/Redemption of debt securities | 0
|  | Payment of Loan Amortization | 119235464.52
|  | Total Cash Outflow | 119235464.52
| Net Cash Flows from Financing Activities |  |  | 93968152.02
Total Cash Provided by Operating,Investing and |  |  |  | 444541405.74
Financing Activities
Add:Cash at Beginning of the Year |  |  |  | 647024193.61
Cash at the End of the Year |  |  |  | 1091565599.35
Certified Correct:
ARTURO V. SORIANO, CPA
Provincial Accountant

## TRUST.FUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE OCTOBER - DECEMBER QUARTER, CY 2015
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
payment of 50% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING OF Pogo-Diaz Farm-to-Market Road at Bautista, Pangasinan | Pogo-Diaz, Bautista, Pangasinan | 1473750 | Labor and Materials Only |  | 50% | 1473750 |  | fund from the Department of Agriculture
payment of 50% work accomplishment for the concreting of Primicias Farm-to-Market Road, Bautista, Pangasinan | Primicias, Bautista, Pangasinan | 2146025.63 | 2015-07-22 | 2015-09-04 | 50% | 2146025.63 |  | fund from the Department of Agriculture
payment of 50% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the concreting of Asingan-San Manuel-Agno Gorge Road, Asingan, Pangasinan | Asingan, Pangasinan | 4868678.34 | Labor and Materials Only |  | 50% | 4868678.34 |  | fund from the DPWH-SLRF
payment of 50% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the concreting of Olo-Naguilayan Road, Mangatarem, Pangasinan | Mangatarem, Pangasinan | 5209468.68 | Labor and Materials Only |  | 50% | 5209468.68 |  | fund from the DPWH-SLRF
TOTAL | [5 empty] | 13697922.65
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO | [5 empty] | HON. AMADO T. ESPINO, JR.
Provincial Accountant | [5 empty] | Provincial Governor

## UNLIQUIDATED.CASH
FDP Form 12- Unliquidated Cash Advances
966
As of December 31, 2015
Province, City or Municipality:
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Rommel Cardinoza | 0 | 2014-01-16
Cornel V. dela Cruz | 0 | 2014-01-16
Gerardo R. Santos | 0 | 2014-01-09
Aurora L. Bacay | 0 | 2014-01-09
Edwin B. Sison | 0 | 2014-01-08
Maria Luisa A. Elduayan | 14665.7 | 2015-09-04 | Maria Luisa A. Elduayan(PR#9673) - cash advance to defray expenses for the 1st Pangasinan Tourism Quiz Bee |  | 14665.7
Atty. Verna T. Nava-Perez | 82699.66 | 2015-09-14 | Atty. Verna T. Nava-Perez - Traveling Expenses, Registration fees of Board Members, Sept. 16-18, 2015, Prov'l Board Member League of the Philippines, Cagayan de Oro City |  | 82699.66
Hon.Mojamito R. Libunao,Jr. | 40000 | 2015-04-22 | Hon.Mojamito R. Libunao,Jr. -Travelling Expense/Reg.Fee for the 25th National Convention of the Prov'l Board Members League of the Phils. (PBMLP) to be held at Century Park Hotel, Manila on April 28-30,2015 |  |  | 40000
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
Rodolfo M. Cortez | 30000 | 1997-04-10 | [6 empty] | 30000
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Rodolfo M. Cortez | 20000 | 1996-06-20 | [6 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Total | 254965.36 |  |  |  | 97365.36 | 40000 |  |  | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA |  |  |  |  | AMADO T. ESPINO, JR
Provincial Accountant |  |  |  |  | Governor