## 2ndQTR
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2ND QUARTER, CY 2017
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
OBLIGATED
Improvement/rehabilitation of existing Bachelor Officers Quarter (BOQ) into Senior Officers Quarter (SOQ) | Avenida Rizal, Lingayen | 6111593 | 2017-05-25 | On Going | 50% | 2441183.78 |  | OBLIGATED | 40% | Cont. 7/20/17
Improvement/extension of Day Care Center | Brgy. Sto. Tomas, San Jacinto | 504156 | 2017-07-14 | On Going | 30% | 151246.8 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the waterproofing of NRSCC Grandstand Bleachers | NRSCC Cmpd (Area-1867 sq.m.) Lingayen | 4437467 | 2017-05-15 | On Going | 68% | 3017477.56 |  | OBLIGATED | 51.89% | Cont. 7/3/17
Labor, materials, equipment and other incidentals for the construction of Senior Citizen Bldg. | Brgy. Bacag, Villasis | 900350 | 2017-05-22 | On Going | 55% | 495192.5 |  | OBLIGATED | 84.15% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the provision of fixed cover and manhole for drainage canal | Capitol Cmpd., Lingayen | 523163 | On Going |  | 40% | 209265.2 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the concreting of as per Extra Work No. 2 | Malasiqui-Catablan Road, Malasiqui, Pangasinan | 20311.65 | Not Yet Started |  |  | 20311.65 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the improvement of Bautista Municipal Plaza, | Poblacion East, Bautista | 3000000 | Not Yet Started |  |  | 3000000 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the construction of Power house and Installation of MCB Panel, Main Feeder Line at Burgos Rehabilitation Center, | Burgos, Pangasinan | 950807.11 | 2017-07-17 | On Going | 7.84% | 74543.2774 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the reconstruction of Gymnasium at PPH Bolingit, | San Carlos city | 2233078 | 2017-07-26 | On Going | 25% | 558269.5 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the extension of swimming pool warm up area w/ shade at NRSCC Cmpd, | Lingayen | 1131044 | 2017-07-03 | On Going | 74.85% | 846586.434 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the the proposed construction of drainage canal at Pozorrubio Com. Hospital, | Pozorrubio | 729856 | Not Yet Started |  |  | 729856 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the relocation of pole and installation 37.5 KVA of private distribution transformer | San Vicente, Burgos | 164799.84 | Not Yet Started |  |  | 164799.84 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the additional work for the repair/rehabilitation of Multi-Purpose Hall | Brgy. Ketegan, Bautista | 162935 | 2017-07-25 | 2015-08-08 | 100% | 161814.91 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the repair/rehabilitation of Goat Shed 7m x 18m at OPVET San Quintin Breeding Station, | San Quintin | 552931 | Not Yet Started |  |  | 552931 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the construction of Provincial Bus Terminal at , as per Extra Work Order No.1 | Motorpool Cmpd., Lingayen | 202528.47 | Not Yet Started |  |  | 202528.47 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the repair/renovation of Old Female Cell Bldg. #1 & Fabrication of Steel Gate at | Pang. Provincial Jail, Lingayen | 448989 | Not Yet Started |  |  | 448989 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the proposed Hall of Fame Bldg., , as per Extra Work #1 | Capitol Complex, Lingayen | 315472.79 | Not Yet Started |  |  | 315472.79 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the construction of Multi-Purpose Bldg. | Brgy. Palma, Basista | 2167431 | 2017-05-25 | On Going | 40% | 865535.5 |  | OBLIGATED | 100% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the construction of Facilitators' Quarters | Brgy. San Vicente, Burgos | 1524013 | 2017-05-23 | On Going | 62.53% | 865535.5 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the completion of Senior Citizen Bldg., | Brgy. Nibaliw Norte, Bautista | 706598 | 2017-07-17 | On Going | 15% | 865535.5 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the construction of Pathway infront of Brgy. Hall | Palaming, San Carlos City | 226814 | 2017-05-12 | 2017-05-29 | 100% | 226814 |  | OBLIGATED | 100% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the proposed construction of CR (Male & Female) | Brgy. Nibaliw Norte, Bautista | 253895 | 2017-05-18 | 2017-06-30 | 100% | 253895 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the proposed street lights | Brgy. Burgos-Padlan, San Carlos City | 400217 | 2017-06-11 | 2017-06-28 | 100% | 400217 |  | OBLIGATED | 100% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the concreting of Multi-Purpose Pavement (Solar Dryer) | Brgy. Cabalitian, Asingan | 363484 | 2017-05-04 | 2017-05-15 | 100% | 363484 |  | OBLIGATED | 100% | Cont. 6/6/17
Labor, materials, equipment and other incidentals for the construction of stage beside open court | Brgy. Galarin, Urbiztondo | 396110 | 2017-05-23 | 2017-06-23 | 100% | 396110 |  | OBLIGATED | 100% | Cont. 7/17/17
Various materials for repainting of water Tank Bldg., | Motor Pool Cmpd., Lingayen | 94132 | Not Yet Started |  |  | 94132 |  | OBLIGATED |  | Obligated
Labor, materials, and other incidentals for the construction of Drainage Canal | Motor Pool Cmpd., Lingayen | 260876 | 2017-05-23 | 2017-06-05 | 100% | 258110.5 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the construction/installation of Street lights at | Brgy. Turko, Laoac | 219600 | Not Yet Started |  |  |  |  | OBLIGATED |  | Obligated
Labor, materials, and other incidentals for the improvement/rehabilitation of Municipal Hall, , as per Extra Work Order No. 1 | Bugallon | 379886.96 | Labor and Materials Only |  |  |  |  | OBLIGATED |  | Obligated
100 units 7 HP air cooled diesel engine couple w/ 3" diameter pump with accessories | Province of Pangasinan | 2400000 | Not Stated |  | 100% | 2398000 |  | OBLIGATED | 100% | Cont. 6/13/17
Engine pumpset and other incidentals for the installation of 20 units STWIP (Open Well) | Province of Pangasinan | 704550 | Materials Only |  |  |  |  | OBLIGATED | 100% | Cont. 7/13/17
Labor, materials, equipment and other incidentals for the installation of 57 units of STWIP of | various barangays and Municipality of Pangasinan, District I-IV | 4170996.09 | Not Stated |  | 100% | 4164429.69 |  | OBLIGATED | 100% | Cont. 5/26/17
3 sets of diesel engine | Province of Pangasinan | 159000 | Materials Only |  |  |  |  | OBLIGATED |  | Obligated
rehabilitation/construction of SIKLING DAM, | Brgy. Bongalon, Labrador | 1733459.53 | Not Stated |  | 20% | 865535.5 |  | OBLIGATED |  | Obligated
construction of New Water Sourc | Dasol Community Hosp., Dasol | 790700 | 2017-06-07 | 2017-08-04 | 100% |  |  | OBLIGATED
construction of 1 Artesian Well at | Sitio Tebag, Brgy. Diaz, Umingan | 63559 | Not Yet Started |  |  | 63559 |  | OBLIGATED
drilling/construction of well sourc (w/ pumpng machinery and elevated stell tank) | Baluyot, Bautista | 1818453.7 | Not Yet Started |  |  | 1818453.7 |  | OBLIGATED
construction of two (2) units Artesian Well (w/ excavation) at | San Eugenio, Natividad | 183100 | Not Yet Started |  |  | 183100 |  | OBLIGATED
2 and 10 rolls 1" dia. PE Pipe SDR 11 and 3/4" dia. PE Pipe SDR 11, respectively, for the provision of PE Pipe for connection of potable drinking water at | Brgy. Babuyan, Infanta | 79500 | Not Yet Started |  |  | 79500 |  | OBLIGATED
construction of Well Source (6" diam casing 120 M depth) (A) Drilling works and well development at | Dasol Community Hospital | 54000 | Not Yet Started |  |  | 54000 |  | OBLIGATED
construction of 10 Artesian Wells w/ jetmatic Pumphead at | Brgy. Binabalian, Bolinao | 133115 | 2017-07-04 | 2017-07-28 | 100% | 133115 |  | OBLIGATED
concreting of Sitio Senenche Extension Farm to Market Road | Brgy. Pogonsili, Aguilar | 2218823 | 2017-05-25 | 2017-07-04 | 100% | 2210648 |  | OBLIGATED | 100% | Cont. 6/20/17, 7/11/17
13 drums Emulsified Asphalt and 428 MT Asphalt Pre-mix in blocktopping | Brgy. Luyan Road (Acacia Ave. & Chico Ave.), Mapandan | 2541200 | 2017-04-20 | 2017-04-25 | 100% | 2534455 |  | OBLIGATED | 100% | Cont. 6/20/17
rehabilitation of Taculit Bridge II (Super Structure Only) at , as per extra work #1 | San Fabian | 134438.05 | - |  |  |  |  | OBLIGATED |  | Obligated
rehabilitation of Taculit Bridge I (Super Structure Only) at , as per extra work #1 | San Fabian | 134438.05 | - |  |  |  |  | OBLIGATED |  | Obligated
concreting of Carmay West Brgy. Road, | Rosales | 1082600 | Not Yet Started |  |  | 1082600 |  | OBLIGATED |  | Obligated
retrofitting of Ramos Bridge, | Urbiztondo | 10000000 | 2017-06-19 | On Going | 70% | 5997142.39 |  | OBLIGATED | 60% | Cont. 7/18/17
retrofitting of Zaragosa Bridge (L=18 mtrs.) | Bolinao | 5800000 | 2017-07-22 | On Going | 20% |  |  | OBLIGATED |  | Obligated
asphalting of Angarian-Banaga Section, | Bugallon | 671500 | Not Yet Started |  |  | 671500 |  | OBLIGATED | 100% | Cont. 7/18/17
asphalting of Sitio Nankumpapueyan Road at | Brgy. Laoag, Aguilar | 2041500 | 2017-06-15 | 2017-06-19 | 100% | 2041500 |  | OBLIGATED |  | Obligated
blocktopping of Brgy. Road | Brgy. Matalava, Lingayen | 811100 | 2017-06-29 | 2017-06-30 | 100% | 811100 |  | OBLIGATED | 100% | Cont. 7/18/17
blocktopping of Municipal Cemetery Road, | Bautista | 908000 | 2017-05-09 | 2017-05-10 | 100% | 908000 |  | OBLIGATED |  | Obligated
asphalting/blocktopping of | Sitio IdolIdol Road, Calasiao | 1131400 | 2017-05-24 | 2017-05-25 | 100% | 1131400 |  | OBLIGATED |  | Obligated
blocktopping of Sitio Calay at | Brgy. Lomboy, Binmaley | 957500 | 2017-03-21 | 2017-03-22 | 100% | 957500 |  | OBLIGATED | 100% | Cont. 7/18/17
Asphalting of Brgy. Sumabnit, | Binalonan | 2676464 | 2017-06-15 | 2017-06-21 | 100% | 2676464 |  | OBLIGATED |  | Obligated
asphalting of Angela Valdez Ramos NH/S, | Asingan | 889400 | 2017-05-18 | 2017-05-23 | 100% | 889400 |  | OBLIGATED |  | Obligated
constructuon of Hanging Bridge, as per Extra Work #1 | Brgy. Garrita, Bani | 130135.43 | [5 empty] | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the construction of drainage system at Don Canuto St., | Brgy. Domalandan West, Lingayen | 1077654 | 2017-06-27 | On Going | 90% | 858789.28 |  | OBLIGATED |  | Obligated
Labor, materials, equipment and other incidentals for the improvement/rehabilitation of Kinabalutan Bridge, Superstructure only (flat slab) at | Brgy. Matulong, Manaoag | 1770551 | Not Yet Started |  |  | 1770551 |  | OBLIGATED |  | Obligated
costruction of CHB Drainage | Brgy. Poblacion, Binmaley | 2360049 | 2017-06-27 | On Going | 60% | 1177790.6 |  | OBLIGATED | 50% | Cont. 7/17/17
concreting of Sito Beros | Brgy. Lokeb Este, Malasiqui | 2124109 | Not Yet Started |  |  | 2124109 |  | OBLIGATED |  | Obligated
repair/maintenance of Provincial Roads | w/in the Province | 500000 | - |  |  |  |  | OBLIGATED |  | Obligated
reconstruction of Baritao Bridge, | Brgy. Baritao, Manaoag | 6198991 | Not Yet Started |  |  | 6198991 |  | OBLIGATED |  | Obligated
Asphalt of Brgy. Allabon Road, | Agno | 1972600 | Not Yet Started |  |  | 1972600 |  | OBLIGATED |  | Obligated
Asphalting of Langka St., | Brgy. San Jose, Alaminos City | 1268100 | Not Yet Started |  |  | 1268100 |  | OBLIGATED |  | Obligated
concreting of Beleng Rd., | Brgy. Beleng, Bayambang | 1911221 | Not Yet Started |  |  | 1911221 |  | OBLIGATED |  | Obligated
concreting of Macayo-cayo, | Bayambang | 1810000 | Not Yet Started |  |  | 1810000 |  | OBLIGATED |  | Obligated
Asphalting/blocktopping of Brgy. Mancasuy Rd., | Binalonan | 1411100 | Not Yet Started |  |  | 1411100 |  | OBLIGATED |  | Obligated
Asphalting of Brgy. Catalina Rd., | Binalonan | 936820 | Not Yet Started |  |  | 936820 |  | OBLIGATED |  | Obligated
blocktopping of Brgy. Cili Rd. | Binalonan | 1316300 | Not Yet Started |  |  | 1316300 |  | OBLIGATED |  | Obligated
asphalting of access road of Dasol Community Hospital and Dasol Breeding Station, | Dasol | 925800 | Not Yet Started |  |  | 925800 |  | OBLIGATED |  | Obligated
blocktopping/patching of Brgy. Road, Brgy. Butao, | Malasiqui | 1774100 | Not Yet Started |  |  | 1774100 |  | OBLIGATED |  | Obligated
concreting of Sitio Bay-bay Rd. | Brgy. Banaoang, Malasiqui | 2071229 | Not Yet Started |  |  | 2071229 |  | OBLIGATED |  | Obligated
blocktopping of Teofilo Visperas to Meliton Enriquez Rd., | Brgy. Banaoang, Mangaldan | 1892200 | Not Yet Started |  |  | 1892200 |  | OBLIGATED |  | Obligated
10 drums E. Asphalt and 322 MT Asphalt Pre-mix for blocktopping of Siti Ragas | Brgy. Andangin, Mangatarem | 1915000 | Not Yet Started |  |  | 1915000 |  | OBLIGATED |  | Obligated
Blocktopping of Brgy. Magsaysay Rd., | San Jacinto | 1742400 | Not Yet Started |  |  | 1742400 |  | OBLIGATED |  | Obligated
Concreting of Brgy. Barangobong Rd., | Tayug | 610802 | Not Yet Started |  |  | 610802 |  | OBLIGATED |  | Obligated
Concreting of Purok 1 Rd., | Brgy. Trenchera, Tayug | 487000 | Not Yet Started |  |  | 487000 |  | OBLIGATED |  | Obligated
Concreting of Purok 1 and 3 Road., | Brgy. Libertad, Tayug | 542498 | Not Yet Started |  |  | 542498 |  | OBLIGATED |  | Obligated
Concreting of Brgy. Amistad Rd., | Brgy. Amistad, Tayug | 667800 | Not Yet Started |  |  | 667800 |  | OBLIGATED |  | Obligated
Concreting of Brgy. Evangelista Rd., | Tayug | 476766 | Not Yet Started |  |  | 476766 |  | OBLIGATED |  | Obligated
Asphalting of Carosalesan-Aloo Road, | Umingan | 2818000 | Not Yet Started |  |  | 2818000 |  | OBLIGATED |  | Obligated
Concreting of Sitio Valdez Rd., | Brgy. Dalanguiring, Urbiztondo | 2047666 | Not Yet Started |  |  | 2047666 |  | OBLIGATED |  | Obligated
Concreting of Sitio Pinac-Bato Rd., | Brgy. Baug, Urbiztondo | 1823233 | Not Yet Started |  |  | 1823233 |  | OBLIGATED |  | Obligated
Asphalting/blocktopping of Brgy. Dilan Paurino, | Urdaneta City | 2229800 | Not Yet Started |  |  | 2229800 |  | OBLIGATED |  | Obligated
Economic Development
Environmental Development
TOTAL |  | 120483259.67 |  |  |  | 94431905.8714
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor

## LDRMM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
For The Quarter April to June 2017
Province of Pangasinan
Particulars | LDRRMF
| Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 52614739.5 | 122767725.5 |  |  |  | 175382465
Continuing Appropriation | [5 empty] | 0
Previous Year's Appropriation transferred to the Special Trust Fund |  | 97152215.91 |  |  |  | 97152215.91
Transfers/Grants | [5 empty] | 0
Others ( Please specify) | [5 empty] | 0
Total Funds Available | 52614739.5 | 219919941.41 | 0 | 0 | 0 | 272534680.91
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies |  | 623450 |  |  |  | 623450
Office Supplies | [5 empty] | 0
Repair of Evacuation Center | [5 empty] | 0
Disaster Response & Rescue Equipment |  | 5494500 |  |  |  | 5494500
Institutional/Capacity Development ( Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Capital Outlay - Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses |  | 5181900.55 |  |  |  | 5181900.55
Traveling Expense |  | 99324 |  |  |  | 99324
Training Expense |  | 89566.5 |  |  |  | 89566.5
IT Equipment & Software | [5 empty] | 0
Motor Vehicles | [5 empty] | 0
Other Machineries and Equipment | [5 empty] | 0
Watercrafts |  | 6586977 |  |  |  | 6586977
Other Property, Plant and Equipment | [5 empty] | 0
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment |  | 5947229 |  |  |  | 5947229
Gasoline, Oil, Lubricants |  | 494145.2 |  |  |  | 494145.2
Furniture & Fixtures |  | 3277500 |  |  |  | 3277500
Donations | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. |  | 7087169.36 |  |  |  | 7087169.36
Repair & Maintenance- Building & Other Structures |  | 2169407.31 |  |  |  | 2169407.31
Repair & Maintenance- Motor Vehicles |  | 55779 |  |  |  | 55779
Honorarium | [5 empty] | 0
Office Equipment |  | 168445
Furnitures & Fixtures | [5 empty] | 0
Other Structures |  | 2122290
Other Transportation |  | 8048800 |  |  |  | 8048800
Total Utilization | 0 | 47446482.92 | 0 | 0 | 0 | 47446482.92
Unutilized Balance | 52614739.5 | 172473458.49 | 0 | 0 | 0 | 225088197.99
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information containedin this document.
ARTURO V. SORIANO, CPA
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending June 30, 2017
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 144896166.29
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
18349045.18
Capital Outlay
30264740.03
Financial Expenses
-0-
Sub-total |  |  |  | 48613785.21
Balance |  |  |  | 96282381.08
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
HON. AMADO I. ESPINO, III
Governor
Note on I11: Pangasinan Accounting:

## CASHFLOWS
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
Statement of Condensed Cash Flows
GENERAL FUND
For the Second Quarter Ending June 30,2017
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 75529562.46
|  | Share from Internal Revenue Allotment |  | 740407314
|  | Receipts from business/service income |  | 87168704.12
|  | Interest Income |  | 1100181.13
|  | Other Receipts |  | 384695097.08
|  | Total Cash Inflow |  | 1288900858.79
Cash Outflows:
|  | Payment of expenses |  | 335562663.8
|  | Payment to suppliers and creditors |  | 119350804.51
|  | Payment to employees |  | 212395838.78
|  | Interest Expenses |  | 12216027.73
|  | Other Expenses |  | 366430661.6
|  | Total Cash Outflow |  | 1045955996.42
| Net Cas Flows from Operating Activities |  |  | 242944862.37
Cash Flows from Investing Activities:
Cash Inflows:
|  | Proceeds from Sale of Investment Property |  | 0
|  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 0
|  | Proceeds from Sale of Biological Assets |  | 70000
|  | Collection of Principal on Loans to other Entities |  | 1663850
|  | Total Cash Inflow |  | 1733850
Cash Outflows:
|  | Purchase / Construction of Investment Property |  | 0
|  | Purchase / Construction of Property, Plant and Equipment |  | 145873640.69
Purchase of Bearer Biological Assets
|  | Grant of Loans |  | 2500000
|  | Total Cash Outflow |  | 148373640.69
| Net Cash Flows from Investing Activities |  |  | -146639790.69
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Loans |  | 36651020.76
|  | Total Cash Inflow |  | 36651020.76
Cash Outflows:
|  | Payment of Long-Term Liabilities |  | 0
|  | Payment of Loan Amortization |  | 40013998.55
|  | Total Cash Outflow |  | 40013998.55
| Net Cash Flows from Financing Activities |  |  | -3362977.79
Total Cash Provided by Operating,Investing and
|  | Financing Activities |  | 92942093.89
Add:Cash at Beginning of the Quarter |  |  |  | 1254794683.42
Cash at the End of the Quarter |  |  |  | 1347736777.31
Certified Correct:
ARTURO V. SORIANO,CPA
Provincial Accountant

## TRUSTFUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE APRIL - JUNE QUARTER, CY 2017
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
payment of 90% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the Rehabilitation/Improvement/Upgrading of URBIZTONDO-SAN CARLOS ROAD | Urbiztondo, Pangasinan | 37001910.5 |  |  | 90% | 33301719.45 |  | fund from the Department of Interior and Local Government
payment of 40% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the Rehabilitation/Improvement/Upgrading of BURGOS-ILIW ILIW ROAD | Burgos, Pangasinan | 54973255.125 |  |  | 40% | 21989302.05 |  | fund from the Department of Interior and Local Government
payment for 504 sacks of rice delivered at Provincial Employment Services Office for the implementation of the Bigasang Bayani in Mangaldan, San Jacinto and Manaoag, Pangasinan | Mangaldan, San Jacinto and Manaoag, Pangasinan | 655200 |  |  | 100% | 655200 |  | fund from the Department of Labor and Employment
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor

## UNLIQUIDATED
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of June 30, 2017
Province, City or Municipality: | PANGASINAN
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Advances for Officers and Employees
HAZEL G. SISON | 61300 | 2017-06-06 | to cash advance the amount to defray expenses in attending the 3rd Philippine Ecotourism 201 Seminar on June 29-30, 2017 at the Bayfront Hotel, Cebu City | 61300
Mona S. Alavazo | 61800 | 2017-06-15 | cash advance re: Attend the Regional Seminar on the Role of Local government unit (LGUs) in Empowering Women for a Disaster Resilient Community at Asturias Hotel, Puerto Princesa City, Palawan June 20-22, 2017 | 61800
Joan Jenny M. Garacho | 78500 | 2017-06-15 | cash advance re: Seminar on Community Based Treatment and Continuum of Care for Drugs Use and Dependence June 27-29, 2017 | 78500
Nestor P. Quiambao | 10000 | 2017-06-16 | cash advance of expenses in attending the 2nd Quarter Regional Conference and Seminar / workshop with theme "Excellent Local Fiscal Governance is served by competent Treasurers and Assessors June 20-23, 2017 at Hotel Supreme, Magsaysay Avenue Baguio City | 10000
Loida Q. Alamar | 10000 | 2017-06-16 | cash advance of expenses in attending the 2nd Quarter Regional Conference and Seminar / workshop with theme "Excellent Local Fiscal Governance is served by competent Treasurers and Assessors June 20-23, 2017 at Hotel Supreme, Magsaysay Avenue Baguio City | 10000
Jennifer D. Cruz | 15000 | 2017-06-16 | cash advance to defray expenses to attend the Training on International Quality Audit (Based on ISO 9001:2015) June 20-21, 2017 at the Philippine Trade Training Center (PTTC) Building, Sen. Gil J. Puyat Ave. Cor. Roxas Boulevard, Pasay City | 15000
LOUIE F. OCAMPO | 24800 | 2017-06-20 | to cash advance of registration fee, transportation expenses hotel accomodation & per diems to assist in the Preparation of the Provincial Government of Pangasinan during the LGU Quality Summit- The ISO Certification Journey of the Province of Pangasinan at Cebu City on June 29-30, 2017 | 24800
LYNDON P. FELIX | 31300 | 2017-06-20 | to cash advance of registration fees, transportation expenses hotel accomodation & per diems to attend the 1. Training on Internal Quality Audit (based on ISO 9001:2015 Standard) needed for the ISO Certification on June 20-21, 2017 at the Philippine Trade Training Center, Roxas Blvd., Pasay City and 2. To assist in the Preparation of the Provincial Government of Pangasinan during the LGU Quality Summit- The ISO Certification Journey of the Province of Pangasinan at Cebu City on June 29-30, 2017 | 31300
KATHLYN JOY DC. TORRES | 24800 | 2017-06-20 | to Cash Advance of Registration fee, transportation expenses hotel accomodation & per diems to assist in the Preparation of the Provincial Government of Pangasinan during the LGU Quality Summit- "The ISO Certification Journey of the Province of Pangasinan at Cebu City on June 29-30, 2017 | 24800
MARIA VIRGINIA JAILE G. DE LEON | 14700 | 2017-06-22 | to cash advance of Registration free, transportation expenses and per diems in attendance to the training on Public Sector HR Symposium with the theme "Shaping Change" required by the Civil Commission on July 4-6, 2017 at Pasay City | 14700
Jesusa C. Lagota | 14700 | 2017-06-22 | cash advance of Registration fee, transportation expenses and per diems in attendance to the training on Public sector HR symposium with the theme "Shaping Change" July 4-6, 2017 at Pasay City | 14700
DOMINGO LEO. A SORIANO | 4500 | 2017-06-29 | to cash advance the payment of Registration Fee for Annual Convention and Scientific Meeting at Marriot Hotel, Newport Pasay City on July 1-2, 2017 | 4500
JT JUNIO | 4500 | 2017-06-29 | to cash advance the payment of registration fee for Annual Convention and Scientific Meeting at Marriot Hotel, Newport Pasay City on July 1-2, 2017 | 4500
KRISTEL IRIS GALSIM | 4500 | 2017-06-29 | to cash advance the payment of registration fee for Annual Convention and Scientific Meeting at Marriot Hotel, Newport Pasay City on July 1-2, 2017 | 4500
MARY ROSE ANN DE GUZMAN | 4500 | 2017-06-29 | to cash advance the payment of registration fee for Annual Convention and Scientific Meeting at Marriot Hotel, Newport Pasay City on July 1-2, 2017 | 4500
Atty. Verna T. Nava-Perez | 127450 | 2017-05-22 | cash advance of travelling expenses and registration fee to attend the 7th ECO Forum on May 25 to May 27, 2017 | 127450
Mr. Antonio C. Cagampan | 21100 | 2017-05-24 | cash advance pymt of Travelling expenses p, per diems, accomodation and regular fee | 21100
Dr. Aurelio O. Cariño | 23100 | 2017-05-24 | cash advance pymt of Travelling expenses, per diems, accomodation and regular fee | 23100
David Ben E. Gurion | 10828.57 | 2017-05-24 | cash advance for pymt of the Travelling and Training expenses of EPDH | 10828.57
Arnulfo L. Olivar | 10828.57 | 2017-05-24 | cash advance for pymt of the Travelling and Training expenses of EPDH | 10828.57
Renato M. Sison | 10828.57 | 2017-05-24 | cash advance for pymt of the Travelling and Training expenses of EPDH | 10828.57
Jofrey A.Bautista | 10828.57 | 2017-05-24 | cash advance for pymt of the Travelling and Training expenses of EPDH | 10828.57
Aileen Tiu | 10828.57 | 2017-05-24 | cash advance for pymt of the Travelling and Training expenses of EPDH | 10828.57
Roman L. Vila, Jr | 14800 | 2017-04-27 | cash advance of Registration fees, transportation expenses, & per diems in attendance to the Trainings | 14800
Ramilyn N. Saumat | 11600 | 2017-04-27 | cash advance of registration fee, transportation expenses, & per diems in attendance to the Training on Internal Control System for Property and Supply Management (Appraisal and Disposal ) May 17-9, 2017 at Hotel Kimberly #770 Pedro Gil St. Malate , Manila | 11600
Camille M. Estrada | 24100 | 2017-04-27 | cash advance of registration fees, transportation expenses & per diems in attendance to the Training | 24100
Vivian U. Oamil | 7560 | 2017-03-23 | cash advance expenses to be incurred in attending the 16th Regional Mining Summit March 29-31, 2017 at the Puerto de San Juan Resort Hotel, Ili Sur, San Juan La Union |  | 7560
Juliet F. Robina | 7560 | 2017-03-23 | cash advance expenses to be incurred in attending the 16th Regional Mining Summit March 29-31, 2017 at the Puerto de San Juan Resort Hotel, Ili Sur, San Juan La Union |  | 7560
Mixon D. Flores | 7560 | 2017-03-23 | cash advance expenses to be incurred in attending the 16th Regional Mining Summit March 29-31, 2017 at the Puerto de San Juan Resort Hotel, Ili Sur, San Juan La Union |  | 7560
Evelyn C. Dismaya | 94200 | 2017-03-23 | cash advance re:Community Based Drug Demand Reduction, Treatment, Rehabilitation and After Case Services |  | 94200
Elmar Z. De Guzman | 7560 | 2017-03-27 | cash advance expenses to be incurred in attending the 16th Regional mining summit March 29-31, 2017 at the Puerto De San Juan resort Hotel, Ili Sur, San Juan La Union |  | 7560
Hon. Jeanne Jinky C. Zaplan | 30000 | 2017-02-08 | cash advance of registration fee/travelling expenses to attend the 27th National Convention of the Prov'l Board member League of the Philippines on Feb. 27 to March 1, 2017 |  | 30000
Hon. Clemente B. Arboleda, Jr. | 30000 | 2017-02-08 | cash advance of registration fee/Travelling expenses to attend the 27th National Convention of the Prov'l League of the Philippines on Feb 27 to March 1, 2017 |  | 30000
Hon. Generoso D. Tulagan, Jr. | 30000 | 2017-02-10 | cash advance of registration fee/travelling expenses to attend the 27th National Convention of the prov'l Board members league of the Philippines Feb. 27 to March 1, 2017 |  | 30000
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Sub-total | 923232.85 |  |  | 641192.85 | 214440 | 0 | 0 | 0 | 67600 | 923232.85
Advances to Special Disbursing
MA. RICHELLE M. RAGUINDIN | 28450 | 2017-06-02 | payment of cash advance to defray expenses for the snacks, lunch etc. during the conduct of Capability Enhancement training on Anti-Illegal Recruitment and Trafficking in Persons and Productivity training for business establishments in the 2nd district of Pangasinan on June 21, June 23 and June 30, 2017 | 28450
Rachel Jose | 37500 | 2017-06-20 | cash advance to defray expenses for the conduct of Blessing and Ribbon cutting of the Bigasang Bayani project store of the OFW family associations in Mangaldan San Jacinto & Manaoag | 37500
ELLSWORTH G. GONZALES | 112000 | 2017-06-23 | to cash advance for the Expenses of the Mid-Year Program Review and Planning Workshop on July 6-7, 2017 | 112000
Atty. Verna T. Nava- Perez | 120000 | 2017-05-08 | cash advance of miscellaneous expenses incurred for the use at the SOPA 2017 | 120000
Alex F. Ferrer | 65000 | 2017-05-09 | cash advance to defray expenses for the business licenses & permit and rentals of 1stone space for 3 months of the Bigasang bayani project | 65000
Bellla B. De Quintos | 65460 | 2017-05-25 | cash advance to defray expenses for the lunch, snacks and tokens during the conduct of Orientation on the Bigasang Bayani project and training on Basic financial management & simple bookeeping capability enhancement training May 26, 31 and June 7, 2017 | 65460
Wilfreda Vicente | 32450 | 2017-05-30 | cash advance to defray expenses for the snacks, lunch etc. during the Job's Fair, Skills Enhancement training and consultation meeting with stakeholders | 32450
Irmina B. Francisco | 563200 | 2017-04-20 | cash advance the amount to defray expenses to be incurred in the conduct of 1st Pangasinan Unity Games (Inter-LGU Basketball and Volleyball Tournament) | 563200
Marife P. Acerit | 29500 | 2017-04-21 | cash advance to be incurred in the conduct of 8th Gov. Amado Espino Boxing Cup April 28, 2017 | 29500
Atty. Verna T. Nava-Perez | 264000 | 2017-04-24 | cash advance of miscellaneous expenses 2017 | 264000
Dr. Cielo E. Almoite | 140000 | 2017-04-25 | cash advance of meals & snacks to be served during the conduct of Municipal Program Implementation Review (MPIR) at selected 20 LGUs April-May 2017 | 140000
Orpheus M. Velasco | 174000 | 2017-04-28 | cash advance for publicity and promotion of Pistaý Dayat 2017 | 174000
Maria Luisa Amor-Elduayan | 130200 | 2017-03-15 | cash advance to defray expenses for Commemorative Program during the Agew n Pangasinan 2017 |  | 130200
Maria Luisa Amor-Elduayan | 392800 | 2017-03-15 | cash advance to defray expenses for the celebration of 10th Pangasinan Tourism & Trade Expo during the Pista'y Dayat 2017 |  | 392800
Orpheus M. Velasco | 56840 | 2017-03-27 | (PR#2369, 3/16/2017)- cash advance for Agew Na Pangasinan 2017 celebration |  | 56840
Orpheus M. Velasco | 169800 | 2017-03-27 | cash advance for Umaani Expo 2017 celebration |  | 169800
Atty. Verna T. Nava-Perez | 305000 | 2017-03-29 | cash advance miscellaneous expenses for the Celebration of Agew Na Pangasinan |  | 305000
Rodolfo M. Cortez | 30000 | 1996-06-20 | [6 empty] | 30000
Rodolfo M. Cortez | 20000 | 1997-04-10 | [6 empty] | 20000
Sub-total | 2736200 |  |  | 1631560 | 1054640 | 0 | 0 | 0 | 50000 | 2736200
Advances for Operating Expenses
Irmina B. Francisco | 50000 | 2017-06-16 | cash advance to defray miscellaneous expenses in the PGO | 50000
IRMINA B. FRANCISCO, Ed. D. | 100000 | 2017-06-20 | to cash advance of financial assistance for sports activities to be given to different constituents of the Province of Pangasinan | 100000
IRMINA B. FRANCISCO, Ed. D. | 100000 | 2017-06-20 | Chief Adm. Officer - to cash advance of financial assistance for medication to be given to different constituents of the Province of Pangasinan | 100000
IRMINA B. FRANCISCO, Ed. D. | 100000 | 2017-06-20 | to cash advance of financial assistance for cultural presentation to be given to different constituents of the Province of Pangasinan | 100000
Engr. Antonieta C. Delos Santos | 200000 | 2017-06-21 | cash advance for the repair and maintenance of various provincial buildings | 200000
Engr. Wilma D. Quimosing | 200000 | 2017-06-21 | cash advance to be used for the repair and maintenance of vraious provincial vehicles and equipment | 200000
EMILIO P. SAMSON JR. RSW | 50000 | 2017-06-29 | to cash advance of financial assistance for petty cash | 50000
Irmina B. Francisco | 100000 | 2017-05-03 | cash advance of financial assistance for cultural presentation to be given to diff constituents |  | 100000
Edwin B. Sison | 243.6 | 2017-04-10 | cash advance to be used in pymt of annual registration fees of various motor vehicles with plate numbers ending in five(5) and six(6) |  | 243.6
Sub-total | 900243.6 |  |  | 800000 | 100243.6 | 0 | 0 | 0 | 0
GRAND TOTAL | 4559676.45 |  |  | 3072752.85 | 1369323.6 |  |  |  | 117600 | 4559676.45
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA |  |  |  |  | HON. AMADO I. ESPINO, III
Provincial Accountant |  |  |  |  | Governor