## 1QTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2017
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | TOTAL COST | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[6 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Improvement/rehabilitation of existing Bachelor Officers Quarter (BOQ) into Senior Officers Quarter (SOQ) Avenida Rizal, | 6111593 | Lingayen
Improvement/extension of Day Care Center at Brgy. Sto. Tomas, | 504156 | San Jacinto
Waterproofing of NRSCC Grandstand Bleachers at NRSCC Cmpd (Area-1867 sq.m.) | 4437467 | Lingayen
Construction of Senior Citizen Bldg. at | 900350 | Brgy. Bacag, Villasis
Improvement of Bautista Municipal Plaza, | 3000000 | Poblacion East, Bautista
Construction of Power house and Installation of MCB Panel, Main Feeder Line at Burgos Rehabilitation Center, | 950807.11 | Burgos, Pangasinan
Reconstruction of Gymnasium at PPH Bolingit, | 2233078 | San Carlos city
Extension of swimming pool warm up area w/ shade at NRSCC Cmpd, | 1131044 | Lingayen
Proposed construction of drainage canal at Pozorrubio Com. Hospital, | 729856 | Pozorrubio
Repair/rehabilitation of Multi-Purpose Hall | 162935 | Brgy. Ketegan, Bautista
Repair/rehabilitation of Goat Shed 7m x 18m at OPVET San Quintin Breeding Station, | 552931 | San Quintin
Repair/renovation of Old Female Cell Bldg. #1 & Fabrication of Steel Gate at Pang. Provincial Jail, | 448989 | Lingayen
Construction of Multi-Purpose Bldg. at | 2167431 | Brgy. Palma, Basista
Construction of Facilitators' Quarters | 1524013 | Brgy. San Vicente, Burgos
Completion of Senior Citizen Bldg., at | 706598 | Brgy. Nibaliw Norte, Bautista
Construction of Pathway infront of Brgy. Hall at Palaming, | 226814 | San Carlos City
Proposed construction of CR (Male & Female) | 253895 | Brgy. Nibaliw Norte, Bautista
Proposed street lights at Brgy. Burgos-Padlan, | 400217 | San Carlos City
Concreting of Multi-Purpose Pavement (Solar Dryer) Brgy. Cabalitian, | 363484 | Asingan
Construction of stage beside open court at | 396110 | Brgy. Galarin, Urbiztondo
Repainting of water Tank Bldg., Motor Pool Cmpd., | 94132 | Lingayen
Construction of Drainage Canal a tCasa Real Cmpd. (back of Prov'l Jai), | 260876 | Lingayen
Construction of Drainage Canal a tCasa Real Cmpd. (back of Prov'l Jai), | 234871 | Lingayen
Construction of concrete battery cages and replacement of solar streetlights battery at Capitol Beachfront, | 465409 | Lingayen
Construction/installation of Street lights | 219600 | Brgy. Turko, Laoac
Improvement/rehabilitation of Municipal Hall, , as per Extra Work Order No. 1 | 379886.96 | Bugallon
Labor, materials, equipment and other incidentals for the construction of New Water Sourc at Dasol Community Hosp., | 790700 | Dasol
Construction of 1 Artesian Well at Sitio Tebag, Brgy. Diaz, | 63559 | Umingan
Drilling/construction of well sourc (w/ pumpng machinery and elevated stell tank) at Baluyot, | 1818453.7 | Bautista
Construction of two (2) units Artesian Well (w/ excavation) at San Eugenio, | 183100 | Natividad
Provision of PE Pipe for connection of potable drinking water at Brgy. Babuyan, | 79500 | Infanta
Construction of Well Source (6" diam casing 120 M depth) (A) Drilling works and well development at Dasol Community Hospital | 54000 | Dasol
Construction of 10 Artesian Wells w/ jetmatic Pumphead at Brgy. Binabalian, | 133115 | Bolinao
Construction of drainage system at Don Canuto St., | 1077654 | Brgy. Domalandan West, Lingayen
Waterproofing of walls and floor topping of GSO Basement Area, Capitol Bldg., Lingayen | 1300000 | Lingayen
Retrofitting of Capitol Basement Area (double layer), Capitol Bldg., | 7000000 | Lingayen
Construction of Provincial Shuttle Bus Terminal, Motorpool Cmpd., Lingayen | 8200000 | Lingayen
Construction of Hall of Fame- Capitol | 2500000 | Lingayen
construction of Training Center #2, Capitol | 6300000 | Lingayen
Economic Development
Asphalting of Bonifacio St., Poblacion, | 525100 | Lingayen
Asphalting of Farm to Market Road, Brgy. Tebag, | 389700 | Mangaldan
Asphalting blocktopping of Soriano St., Poblacion, | 259800 | Lingayen
Blocktopping/patching of Brgy. Ingalagala, Brgy. Road, | 626200 | Malasiqui
locktopping of Nicanor St., | 499700 | Poblacion, Lingayen
Patching/blcoktopping of Dulag Road, | 1915000 | Binmaley
Asphalting of Abalos St., Brgy. Estanza, | 735400 | Lingayen
Concreting of Sitio Guillermo Lamsen Road at Domalandan East, | 371804 | Lingayen
Concreting of Sitio Senenche Extension Farm to Market Road at Brgy. Pogonsili, | 2218823 | Aguilar
blocktopping of Brgy. Luyan Road (Acacia Ave. & Chico Ave.), | 2541200 | Mapandan
Rehabilitation of Taculit Bridge II (Super Structure Only) , as per extra work #1 | 134438.05 | San Fabian,
Rehabilitation of Taculit Bridge I (Super Structure Only) at , as per extra work #1 | 134438.05 | San Fabian
Rehabilitation/construction of SIKLING DAM, | 1733459.53 | Brgy. Bongalon, Labrador
Concreting of Carmay West Brgy. Road, | 1082600 | Rosales
Retrofitting of Ramos Bridge, | 10000000 | Urbiztondo
Retrofitting of Zaragosa Bridge (L=18 mtrs.) | 5800000 | Bolinao
Asphalting of Angarian-Banaga Section, | 671500 | Bugallon
Asphalting of Sitio Nankumpapueyan Road at | 2041500 | Brgy. Laoag, Aguilar
blocktopping of Brgy. Road at Brgy. Matalava, | 811100 | Lingayen
Blocktopping of Municipal Cemetery Road, | 908000 | Bautista
Asphalting/blocktopping of Sitio IdolIdol Road, | 1131400 | Calasiao
blocktopping of Sitio Calay at | 957500 | Brgy. Lomboy, Binmaley
Asphalting of Brgy. Sumabnit, | 2676464 | Binalonan
Asphalting of Angela Valdez Ramos NH/S, | 889400 | Asingan
Constructuon of Hanging Bridge at , as per Extra Work #1 | 130135.43 | Brgy. Garrita, Bani
improvement/rehabilitation of Kinabalutan Bridge, Superstructure only (flat slab) | 1770551 | Brgy. Matulong, Manaoag
Costruction of CHB Drainage | 2360049 | Brgy. Poblacion, Binmaley
concreting of Sito Beros at | 2124109 | Brgy. Lokeb Este, Malasiqui
Repair/maintenance of Provincial Roads | 500000 | w/in the Province
Asphalting/blocktopping of Brgy. Mancasuy Rd., | 1411100 | Binalonan
Reconstruction of Baritao Bridge, | 6198991 | Brgy. Baritao, Manaoag
Asphalt of Brgy. Allabon Road, | 1972600 | Agno
Asphalting of Langka St., | 1268100 | Brgy. San Jose, Alaminos City
Concreting of Beleng Rd., Brgy. Beleng, | 1911221 | Bayambang
Concreting of Macayo-cayo, | 1810000 | Bayambang
Asphalting of Brgy. Catalina Rd., | 936820 | Binalonan
Blocktopping of Brgy. Cili Rd., | 1316300 | Binalonan
Asphalting of access road of Dasol Community Hospital and Dasol Breeding Station, | 925800 | Dasol
Blocktopping/patching of Brgy. Road, | 1774100 | Brgy. Butao, Malasiqui
Concreting of Sitio Bay-bay Rd. at | 2071229 | Brgy. Banaoang, Malasiqui
Blocktopping of Teofilo Visperas to Meliton Enriquez Rd., | 1892200 | Brgy. Banaoang, Mangaldan
10 drums E. Asphalt and 322 MT Asphalt Pre-mix for blocktopping of Siti Ragas at | 1915000 | Brgy. Andangin, Mangatarem
Blocktopping of Brgy. Magsaysay Rd., | 1742400 | San Jacinto
Concreting of Brgy. Barangobong Rd., | 610802 | Tayug
Concreting of Purok 1 Rd., | 487000 | Brgy. Trenchera, Tayug
Concreting of Purok 1 and 3 Road., | 542498 | Brgy. Libertad, Tayug
Concreting of Brgy. Amistad Rd., | 667800 | Brgy. Amistad, Tayug
Concreting of Brgy. Evangelista Rd., | 476766 | Tayug
Asphalting of Carosalesan-Aloo Road, | 2818000 | Umingan
Concreting of Sitio Valdez Rd., | 2047666 | Brgy. Dalanguiring, Urbiztondo
Concreting of Sitio Pinac-Bato Rd., | 1823233 | Brgy. Baug, Urbiztondo
Asphalting/blocktopping of Brgy. Dilan Paurino | 2229800 | Urdaneta City
Amortization of Principal and Interest on Loan to the LBP | 96683454.99
Loans Granted to Multi-Purpose Cooperative/ Livelihood Associations | 3730000
Environmental Development

## 2ndQTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2017
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Improvement/rehabilitation of existing Bachelor Officers Quarter (BOQ) into Senior Officers Quarter (SOQ) | Avenida Rizal, Lingayen | 6111593 | [6 empty] | 2441183.78 | 40% | Cont. 7/20/17
Improvement/extension of Day Care Center | Brgy. Sto. Tomas, San Jacinto | 504156 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the waterproofing of NRSCC Grandstand Bleachers | NRSCC Cmpd (Area-1867 sq.m.) Lingayen | 4437467 | [6 empty] | 2299212.73 | 51.89% | Cont. 7/3/17
Labor, materials, equipment and other incidentals for the construction of Senior Citizen Bldg. | Brgy. Bacag, Villasis | 900350 | [6 empty] | 754501.15 | 84.15% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the provision of fixed cover and manhole for drainage canal | Capitol Cmpd., Lingayen | 523163 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the concreting of as per Extra Work No. 2 | Malasiqui-Catablan Road, Malasiqui, Pangasinan | 20311.65 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the improvement of Bautista Municipal Plaza, | Poblacion East, Bautista | 3000000 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of Power house and Installation of MCB Panel, Main Feeder Line at Burgos Rehabilitation Center, | Burgos, Pangasinan | 950807.11 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the reconstruction of Gymnasium at PPH Bolingit, | San Carlos city | 2233078 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the extension of swimming pool warm up area w/ shade at NRSCC Cmpd, | Lingayen | 1131044 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the the proposed construction of drainage canal at Pozorrubio Com. Hospital, | Pozorrubio | 729856 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the relocation of pole and installation 37.5 KVA of private distribution transformer | San Vicente, Burgos | 164799.84 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the additional work for the repair/rehabilitation of Multi-Purpose Hall | Brgy. Ketegan, Bautista | 162935 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the repair/rehabilitation of Goat Shed 7m x 18m at OPVET San Quintin Breeding Station, | San Quintin | 552931 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of Provincial Bus Terminal at , as per Extra Work Order No.1 | Motorpool Cmpd., Lingayen | 202528.47 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the repair/renovation of Old Female Cell Bldg. #1 & Fabrication of Steel Gate at | Pang. Provincial Jail, Lingayen | 448989 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the proposed Hall of Fame Bldg., , as per Extra Work #1 | Capitol Complex, Lingayen | 315472.79 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of Multi-Purpose Bldg. | Brgy. Palma, Basista | 2167431 | [6 empty] | 865535.5 | 100% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the construction of Facilitators' Quarters | Brgy. San Vicente, Burgos | 1524013 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the completion of Senior Citizen Bldg., | Brgy. Nibaliw Norte, Bautista | 706598 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of Pathway infront of Brgy. Hall | Palaming, San Carlos City | 226814 | [6 empty] | 224895.84 | 100% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the proposed construction of CR (Male & Female) | Brgy. Nibaliw Norte, Bautista | 253895 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the proposed street lights | Brgy. Burgos-Padlan, San Carlos City | 400217 | [6 empty] | 397767.9 | 100% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the concreting of Multi-Purpose Pavement (Solar Dryer) | Brgy. Cabalitian, Asingan | 363484 |  |  | 100% | 360176.25 |  |  | 360176.25 | 100% | Cont. 6/6/17
Labor, materials, equipment and other incidentals for the construction of stage beside open court | Brgy. Galarin, Urbiztondo | 396110 | [6 empty] | 393699.75 | 100% | Cont. 7/17/17
Various materials for repainting of water Tank Bldg., | Motor Pool Cmpd., Lingayen | 94132 | [8 empty] | Obligated
Labor, materials, and other incidentals for the construction of Drainage Canal | Casa Real Cmpd. (back of Prov'l Jai), Lingayen | 260876 | [8 empty] | Obligated
Labor, materials, and other incidentals for the construction of Drainage Canal | Casa Real Cmpd. (back of Prov'l Jai), Lingayen | 234871 |  |  | 100% | 232892.59 |  |  | 232892.59 | 100% | Cont. 6/28/17
Labor, materials, equipment and other incidentals for the construction/installation of Street lights at | Brgy. Turko, Laoac | 219600 | [8 empty] | Obligated
Labor, materials, and other incidentals for the improvement/rehabilitation of Municipal Hall, , as per Extra Work Order No. 1 | Bugallon | 379886.96 | [8 empty] | Obligated
100 units 7 HP air cooled diesel engine couple w/ 3" diameter pump with accessories | Province of Pangasinan | 2400000 |  |  | 100% | 2398000 |  |  | 2398000 | 100% | Cont. 6/13/17
Engine pumpset and other incidentals for the installation of 20 units STWIP (Open Well) | Province of Pangasinan | 704550 | [6 empty] | 701736 | 100% | Cont. 7/13/17
Labor, materials, equipment and other incidentals for the installation of 57 units of STWIP of | various barangays and Municipality of Pangasinan, District I-IV | 4170996.09 |  |  | 100% | 4164429.69 |  |  | 4164429.69 | 100% | Cont. 5/26/17
3 sets of diesel engine | Province of Pangasinan | 159000 | [8 empty] | Obligated
rehabilitation/construction of SIKLING DAM, | Brgy. Bongalon, Labrador | 1733459.53 | [8 empty] | Obligated
construction of New Water Sourc | Dasol Community Hosp., Dasol | 790700
construction of 1 Artesian Well at | Sitio Tebag, Brgy. Diaz, Umingan | 63559
drilling/construction of well sourc (w/ pumpng machinery and elevated stell tank) | Baluyot, Bautista | 1818453.7
construction of two (2) units Artesian Well (w/ excavation) at | San Eugenio, Natividad | 183100
2 and 10 rolls 1" dia. PE Pipe SDR 11 and 3/4" dia. PE Pipe SDR 11, respectively, for the provision of PE Pipe for connection of potable drinking water at | Brgy. Babuyan, Infanta | 79500
construction of Well Source (6" diam casing 120 M depth) (A) Drilling works and well development at | Dasol Community Hospital | 54000
construction of 10 Artesian Wells w/ jetmatic Pumphead at | Brgy. Binabalian, Bolinao | 133115
concreting of Sitio Senenche Extension Farm to Market Road | Brgy. Pogonsili, Aguilar | 2218823 | [6 empty] | 2210648 | 100% | Cont. 6/20/17, 7/11/17
13 drums Emulsified Asphalt and 428 MT Asphalt Pre-mix in blocktopping | Brgy. Luyan Road (Acacia Ave. & Chico Ave.), Mapandan | 2541200 |  |  | 100% | 2534455 |  |  | 2534455 | 100% | Cont. 6/20/17
rehabilitation of Taculit Bridge II (Super Structure Only) at , as per extra work #1 | San Fabian | 134438.05 | [8 empty] | Obligated
rehabilitation of Taculit Bridge I (Super Structure Only) at , as per extra work #1 | San Fabian | 134438.05 | [8 empty] | Obligated
concreting of Carmay West Brgy. Road, | Rosales | 1082600 | [8 empty] | Obligated
retrofitting of Ramos Bridge, | Urbiztondo | 10000000 | [6 empty] | 5997142.39 | 60% | Cont. 7/18/17
retrofitting of Zaragosa Bridge (L=18 mtrs.) | Bolinao | 5800000 | [8 empty] | Obligated
asphalting of Angarian-Banaga Section, | Bugallon | 671500 | [6 empty] | 671173 | 100% | Cont. 7/18/17
asphalting of Sitio Nankumpapueyan Road at | Brgy. Laoag, Aguilar | 2041500 | [8 empty] | Obligated
blocktopping of Brgy. Road | Brgy. Matalava, Lingayen | 811100 | [6 empty] | 810689 | 100% | Cont. 7/18/17
blocktopping of Municipal Cemetery Road, | Bautista | 908000 | [8 empty] | Obligated
asphalting/blocktopping of | Sitio IdolIdol Road, Calasiao | 1131400 | [8 empty] | Obligated
blocktopping of Sitio Calay at | Brgy. Lomboy, Binmaley | 957500 | [6 empty] | 956856 | 100% | Cont. 7/18/17
Asphalting of Brgy. Sumabnit, | Binalonan | 2676464 | [8 empty] | Obligated
asphalting of Angela Valdez Ramos NH/S, | Asingan | 889400 | [8 empty] | Obligated
constructuon of Hanging Bridge, as per Extra Work #1 | Brgy. Garrita, Bani | 130135.43 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of drainage system at Don Canuto St., | Brgy. Domalandan West, Lingayen | 1077654 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the improvement/rehabilitation of Kinabalutan Bridge, Superstructure only (flat slab) at | Brgy. Matulong, Manaoag | 1770551 | [8 empty] | Obligated
costruction of CHB Drainage | Brgy. Poblacion, Binmaley | 2360049 | [6 empty] | 1177790.6 | 50% | Cont. 7/17/17
concreting of Sito Beros | Brgy. Lokeb Este, Malasiqui | 2124109 | [8 empty] | Obligated
repair/maintenance of Provincial Roads | w/in the Province | 500000 | [8 empty] | Obligated
reconstruction of Baritao Bridge, | Brgy. Baritao, Manaoag | 6198991 | [8 empty] | Obligated
Asphalt of Brgy. Allabon Road, | Agno | 1972600 | [8 empty] | Obligated
Asphalting of Langka St., | Brgy. San Jose, Alaminos City | 1268100 | [8 empty] | Obligated
concreting of Beleng Rd., | Brgy. Beleng, Bayambang | 1911221 | [8 empty] | Obligated
concreting of Macayo-cayo, | Bayambang | 1810000 | [8 empty] | Obligated
Asphalting/blocktopping of Brgy. Mancasuy Rd., | Binalonan | 1411100 | [8 empty] | Obligated
Asphalting of Brgy. Catalina Rd., | Binalonan | 936820 | [8 empty] | Obligated
blocktopping of Brgy. Cili Rd. | Binalonan | 1316300 | [8 empty] | Obligated
asphalting of access road of Dasol Community Hospital and Dasol Breeding Station, | Dasol | 925800 | [8 empty] | Obligated
blocktopping/patching of Brgy. Road, Brgy. Butao, | Malasiqui | 1774100 | [8 empty] | Obligated
concreting of Sitio Bay-bay Rd. | Brgy. Banaoang, Malasiqui | 2071229 | [8 empty] | Obligated
blocktopping of Teofilo Visperas to Meliton Enriquez Rd., | Brgy. Banaoang, Mangaldan | 1892200 | [8 empty] | Obligated
10 drums E. Asphalt and 322 MT Asphalt Pre-mix for blocktopping of Siti Ragas | Brgy. Andangin, Mangatarem | 1915000 | [8 empty] | Obligated
Blocktopping of Brgy. Magsaysay Rd., | San Jacinto | 1742400 | [8 empty] | Obligated
Concreting of Brgy. Barangobong Rd., | Tayug | 610802 | [8 empty] | Obligated
Concreting of Purok 1 Rd., | Brgy. Trenchera, Tayug | 487000 | [8 empty] | Obligated
Concreting of Purok 1 and 3 Road., | Brgy. Libertad, Tayug | 542498 | [8 empty] | Obligated
Concreting of Brgy. Amistad Rd., | Brgy. Amistad, Tayug | 667800 | [8 empty] | Obligated
Concreting of Brgy. Evangelista Rd., | Tayug | 476766 | [8 empty] | Obligated
Asphalting of Carosalesan-Aloo Road, | Umingan | 2818000 | [8 empty] | Obligated
Concreting of Sitio Valdez Rd., | Brgy. Dalanguiring, Urbiztondo | 2047666 | [8 empty] | Obligated
Concreting of Sitio Pinac-Bato Rd., | Brgy. Baug, Urbiztondo | 1823233 | [8 empty] | Obligated
Asphalting/blocktopping of Brgy. Dilan Paurino, | Urdaneta City | 2229800 | [8 empty] | Obligated
Economic Development
Environmental Development

## UNLIQUIDATED
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of September 30, 2017
Province, City or Municipality: | PANGASINAN
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Advances for Officers and Employees
Catherine M. Gordovez | 18447 | 2017-09-18 | cash advance for her travelling expenses to the 18th Association of Tourism Officers of the Philippines (ATOP) National Convention in Iloilo City October 4-7, 2017 | 18447
G.R J. Cañas | 18447 | 2017-09-18 | cash advance his travelling expenses to the 18th Association of Tourism Officers of the Philippines (ATOP) National Convention in Iloilo City October 4-7, 2017 | 18447
Hazel G. Sison | 18447 | 2017-09-18 | cash advance her travelling expenses to the 18th Association of Tourism Officers of the Philippines (ATOP) National Convention in Iloilo city October 4-7, 2017 | 18447
Marife P. Acerit | 18447 | 2017-09-18 | cash advance her terminal expenses to the 18th Association of Tourism Officers of the Philippines (ATOP) National Convention in Iloilo City October 4-7, 2017 | 18447
Zenaida A. Gonzales | 18447 | 2017-09-18 | cash advance for her travelling expenses to the 18th Association of Tourism Officer of the Philippines (ATOP) National Convention in Iloilo City October 4-7, 2017 | 18447
Ma. Luisa A. Elduayan | 16900 | 2017-09-14 | cash advance to defray expenses to the 18th Association of Tourism Officers of the Philippines (ATOP) National Convention in Iloilo City October 4-7, 2017 | 16900
Engr. Antonieta C. Delos Santos | 906000 | 2017-09-13 | cash advance for pymt of per diems and miscellaneous expenses for Lakbay Aral Within Manila Sept. 22, 29 October 6, 13, 2017 | 906000
Modesto R. Singson | 1600 | 2017-08-29 | cash advance per diems and travelling allowance of 39 MISO and ITAX-RPTA employees, two (2) drivers and three (3) PSWDO staffs in attending official travel |  | 1600
Donnie Y. Bautista | 9250 | 2017-08-15 | cash advance Hotel & Food Accomodation and other accidental expenses for the National Blood Services Act of 1994 " Blood Safety:Sustaining the Advocacy, Sharing the Responsibility " will be holding its 34th Annual Convention on August 23-25, 2017 at Mandaluyong City, 1650 Metro manila |  | 9250
Patrick John L. Rosario | 9250 | 2017-08-15 | cash advance Hotel and Food Accomodation and other accidental expenses for the National Blood Services Act of 1994 "Blood Safety" Sustaining the Advocacy, Shairng the Responsibility" will be holding its 34th Annual Convention August 23-25, 2017 |  | 9250
Arjohn Jewel Macaraeg | 7640 | 2017-08-08 | cash advance for pymt of the travelling and training expenses of eastern Pangasinan DH |  | 7640
Lloyd C. Ortiz | 7640 | 2017-08-08 | cash advance for pymt for the Travelling and Training expenses of EPDH |  | 7640
Jonathan L. Castro | 14700 | 2017-08-02 | cash advance per diems and travelling allowance in attending the "SOPHOS NEXT-Gen Secxurity Seminar" to be held on August 24, 2017 at New World Makati Hotel, makati Ciuty Philippines |  | 14700
Darell M. Fernandez | 33120 | 2017-07-20 | cash advance to defray expenses in attending the 92nd Philippine Heart center Critical Course July 24-September 15, 2017 |  | 33120
Kimberly D. Galicia- | 33120 | 2017-07-20 | cash advance to defray expenses in attending the 92nd Philippine Heart Center Critical Care Course July 24- September 15, 2017 |  | 33120
Paul Albert R. Fabiona | 33120 | 2017-07-20 | cash advance to defray expenses in attending the 92nd Philippine Heart Center Critical Care Course July 24- September 15, 2017 |  | 33120
Andrea Rowena C. Camacho | 33120 | 2017-07-20 | cash advance to defray expenses in attending the 92nd Philippine Heart Center Critical Care Course July 24- September 15, 2017 |  | 33120
Rebekah Jane F. Barroga | 33120 | 2017-07-20 | cash advance to defray expenses in attending the 92nd Philippine Heart Center Critical Care Course July 24- September 15, 2017 |  | 33120
LOUIE F. OCAMPO | 24800 | 2017-06-20 | to cash advance of registration fee, transportation expenses hotel accomodation & per diems to assist in the Preparation of the Provincial Government of Pangasinan during the LGU Quality Summit- The ISO Certification Journey of the Province of Pangasinan at Cebu City on June 29-30, 2017 |  | 24800
LYNDON P. FELIX | 31300 | 2017-06-20 | to cash advance of registration fees, transportation expenses hotel accomodation & per diems to attend the 1. Training on Internal Quality Audit (based on ISO 9001:2015 Standard) needed for the ISO Certification on June 20-21, 2017 at the Philippine Trade Training Center, Roxas Blvd., Pasay City and 2. To assist in the Preparation of the Provincial Government of Pangasinan during the LGU Quality Summit- The ISO Certification Journey of the Province of Pangasinan at Cebu City on June 29-30, 2017 |  | 31300
KATHLYN JOY DC. TORRES | 24800 | 2017-06-20 | to Cash Advance of Registration fee, transportation expenses hotel accomodation & per diems to assist in the Preparation of the Provincial Government of Pangasinan during the LGU Quality Summit- "The ISO Certification Journey of the Province of Pangasinan at Cebu City on June 29-30, 2017 |  | 24800
Dr. Aurelio O. Cariño | 23100 | 2017-05-24 | cash advance pymt of Travelling expenses, per diems, accomodation and regular fee |  |  | 23100
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Sub-total | 1402415 |  |  | 1015135 | 296580 | 23100 |  |  | 67600
Advances to Special Disbursing
Irmina B. Francisco | 30000 | 2017-09-26 | cash advance to defray expenses for the maintenance & various sports activities | 30000
Rhodyn Luchinvar O. Oro | 20000 | 2017-09-20 | cash advance to deffay expenses for the Traing Kits/materials of the paticipants and other miscillaneous expenses during the 4-day Live-in Contingency Plan Formulation Workshop | 20000
Judith V. Cabilio | 56840 | 2017-09-18 | cash advance re: 7th International deaf day w/ the theme "Full Inclusion w/ Sign Language" Sept. 29-30, 2017 at Cauayan City, Isabela | 56840
Marife P. Acerit | 169800 | 2017-09-18 | cash advance to defray expenses for ASIA CEO Awards Night in Marriot Hotel Manila October 16-17, 2017 | 169800
Irmina B. Francisco | 174000 | 2017-09-08 | cash advance to defray expenses to be incurred in the conduct of 1st Pangasinan Inter-Agency Baskteball Tournament | 174000
Cielo E. Almoite | 120000 | 2017-08-01 | cash advance expenses for the conduct of BUNTIS CONGRESS August 2017 (PR#5298, 6/8/2017) |  | 120000
Atty. Verna T. Nava- Perez | 85000 | 2017-05-08 | cash advance of miscellaneous expenses incurred for the use at the SOPA 2017 |  | 85000
Orpheus M. Velasco | 25000 | 2017-04-28 | cash advance for publicity and promotion of Pistaý Dayat 2017 |  |  | 25000
Orpheus M. Velasco (PR#2369, 3/16/2017) | 196000 | 2017-03-27 | cash advance for Agew Na Pangasinan 2017 celebration |  |  | 196000
Orpheus M. Velasco | 50000 | 2017-03-27 | cash advance for Umaani Expo 2017 celebration |  |  | 50000
Rodolfo M. Cortez | 300000 | 1997-04-10 | [6 empty] | 300000
Rodolfo M. Cortez | 55800 | 1996-06-20 | [6 empty] | 55800
Sub-total | 1282440 |  |  | 450640 | 205000 | 271000 |  |  | 355800
Advances for Operating Expenses
Edwin B. Sison | 100000 | 2017-09-15 | cash advance the amount of ONE HUNDRED THOUSAND PESOS ONLY (P 100,000.00)to be used in payment of Annual Registration Fees of various motor vehicels with plate numbers ending in nine(9) and zero(0) as per supporting papers | 100000
Engr. Antonieta C. Delos Santos | 200000 | 2017-09-29 | cash advance to be used for the repair and maintenance of various Prov'l Buildings and Hospitals | 200000
Irmina B. Francisco | 100000 | 2017-09-06 | cash advance of financial assistance for cultural presentation to be given to different constituents of the Province of Pangasinan | 100000
Irmina B. Francisco | 150000 | 2017-09-12 | cash advance of financial assistance for medication to be given to different constituents of the province of Pangasinan | 150000
Irmina B. Francisco | 50000 | 2017-06-16 | cash advance to defray miscellaneous expenses in the PGO |  | 50000
Engr. Wilma D. Quimosing | 200000 | 2017-06-21 | cash advance to be used for the repair and maintenance of vraious provincial vehicles and equipment |  | 200000
EMILIO P. SAMSON JR. RSW | 50000 | 2017-06-29 | to cash advance of financial assistance for petty cash |  | 50000
Sub-total | 850000 |  |  | 550000 | 300000 | 0 | 0 | 0 | 0
GRAND TOTAL | 3534855 |  |  | 2015775 | 801580 | 294100 |  |  | 423400
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor

## TRUST FUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE JULY - SEPTEMBER QUARTER, CY 2017
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Rehabilitation of Malasiqui - Catablan Road @ Malasiqui and Sta. Barbara, Pangasinan | Malasiqui and Sta. Barbara, Pangasinan | 82640535.64 | Aug. 1, 2017 | On Going | 15% | 12396080.35 |  | Fund from the Department of Interior and Local Government - CMGP
Rehabilitation of Banaoang - Mapandan Road @ Sta. Barbara and Mapandan, Pangasinan | Sta. Barbara and Mapandan, Pangasinan | 45009579.52 | Aug. 14, 2017 | On Going | 15% | 6751436.93 |  | Fund from the Department of Interior and Local Government - CMGP
Rehabilitation of Urbiztondo - Basista Road @ Urbiztondo and Basista, Pangasinan | Urbiztondo and Basista, Pangasinan | 37338032.56 | July 11, 2017 | On Going | 15% | 5600704.88 |  | Fund from the Department of Interior and Local Government - CMGP
Payment of 90% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the Rehabilitation/Improvement/Upgrading of Urbiztondo - San Carlos Road |  | 37001910.51 | March 21, 2016 | Jan. 25, 2017 | 100% | 37001910.51 |  | Fund from the Department of Interior and Local Government - CMGP
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor

## CASH FLOW
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
Statement of Condensed Cash Flows
GENERAL FUND
For the Third Quarter Ending September 30,2017
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 26477997.32
|  | Share from Internal Revenue Allotment |  | 740407314
|  | Receipts from business/service income |  | 102975047.96
|  | Interest Income |  | 1103221.69
|  | Other Receipts |  | 79688294.52
|  | Total Cash Inflow |  | 950651875.49
Cash Outflows:
|  | Payment of expenses |  | 243533018.77
|  | Payment to suppliers and creditors |  | 135539570.51
|  | Payment to employees |  | 177513729.85
|  | Interest Expenses |  | 12099491.03
|  | Other Expenses |  | 78728444.78
|  | Total Cash Outflow |  | 647414254.94
| Net Cas Flows from Operating Activities |  |  | 303237620.55
Cash Flows from Investing Activities:
Cash Inflows:
|  | Proceeds from Sale of Investment Property |  | 0
|  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 0
|  | Proceeds from Sale of Biological Assets |  | 50000
|  | Collection of Principal on Loans to other Entities |  | 1651400
|  | Total Cash Inflow |  | 1701400
Cash Outflows:
|  | Purchase / Construction of Investment Property |  | 0
|  | Purchase / Construction of Property, Plant and Equipment |  | 225263398.16
Purchase of Bearer Biological Assets
|  | Grant of Loans |  | 3030000
|  | Total Cash Outflow |  | 228293398.16
| Net Cash Flows from Investing Activities |  |  | -226591998.16
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Loans |  | 20925621.7
|  | Total Cash Inflow |  | 20925621.7
Cash Outflows:
|  | Payment of Long-Term Liabilities |  | 0
|  | Payment of Loan Amortization |  | 37268527.29
|  | Total Cash Outflow |  | 37268527.29
| Net Cash Flows from Financing Activities |  |  | -16342905.59
Total Cash Provided by Operating,Investing and
|  | Financing Activities |  | 60302716.8
Add:Cash at Beginning of the Quarter |  |  |  | 1347736777.31
Cash at the End of the Quarter |  |  |  | 1408039494.11
Certified Correct:
ARTURO V. SORIANO,CPA
PROVINCIAL ACCOUNTANT

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending September 30, 2017
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 159640000.27
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
29271691.29
Capital Outlay
51031563.44
Financial Expenses
-0-
Sub-total |  |  |  | 80303254.73
Balance |  |  |  | 79336745.54
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
HON. AMADO I. ESPINO, III
Governor
Note on I11: Pangasinan Accounting:

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
As of September 2017
Province of Pangasinan
LDRRMF
Particulars | Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 52614739.5 | 122767725.5 |  |  |  | 175382465
Continuing Appropriation | [5 empty] | 0
Previous Year's Appropriation transferred to the Special Trust Fund |  | 97152215.91 |  |  |  | 97152215.91
Transfers/Grants | [5 empty] | 0
Others (Please specify) | [5 empty] | 0
Total Funds Available | 52614739.5 | 219919941.41 | 0 | 0 | 0 | 272534680.91
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies |  | 2673680 |  |  |  | 2673680
Office Supplies | [5 empty] | 0
Repair of Evacuation Center | [5 empty] | 0
Disaster Response & Rescue Equipment |  | 5749500 |  |  |  | 5749500
Institutional/Capacity Development ( Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Capital Outlay - Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses |  | 6361028.35 |  |  |  | 6361028.35
Traveling Expense |  | 207704.5 |  |  |  | 207704.5
Training Expense |  | 163566.5 |  |  |  | 163566.5
IT Equipment & Software | [5 empty] | 0
Motor Vehicles | [5 empty] | 0
Other Machineries and Equipment | [5 empty] | 0
Watercrafts |  | 8328643.5 |  |  |  | 8328643.5
Other Property, Plant and Equipment | [5 empty] | 0
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment |  | 20160985 |  |  |  | 20160985
Gasoline, Oil, Lubricants |  | 780947.74 |  |  |  | 780947.74
Drugs and Medicines |  | 3277500 |  |  |  | 3277500
Donations | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. |  | 7087169.36 |  |  |  | 7087169.36
Repair & Maintenance - Building & Other Structures |  | 2169407.31 |  |  |  | 2169407.31
Repair & Maintenance-Motor Vehicles |  | 583115.72 |  |  |  | 583115.72
Honorarium | [5 empty] | 0
Office Equipment |  | 168445 |  |  |  | 168445
Furnitures & Fixtures | [5 empty] | 0
Other Structures |  | 2122290 |  |  |  | 2122290
Other Transportation |  | 15978500 |  |  |  | 15978500
Total Utilization | 0 | 75812482.98 | 0 | 0 | 0 | 75812482.98
Unutilized Balance | 52614739.5 | 144107458.43 | 0 | 0 | 0 | 196722197.93
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information contained in this document.
ARTURO V. SORIANO
Provincial Accountant

## 20%ira
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2017
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Construction of covered court Gymnasium w/ 0.4m Floor Elevation | Brgy. San Leon Umingan | 2523679 | 2017-08-29 | On-Going | 48% | 1211365.92 |  | On-going
Improvement/interior design for Hall of Fame Building | Capitol Complex, Lingayen | 5866581 | 2017-08-24 | On-Going | 40% | 2342591.86 |  | On-going
13000 bags cement |  | 3900000 | [5 empty] | -
Completion/improvement of Municipal Hall | Calasiao, Pangasinan | 2715184 | [5 empty] | NYS
Improvement/rehabilitation of OR/DR and OB Gyne Ward at WPDH | Alaminos City | 4386528 | 2017-08-24 | On-Going | 50% | 2162662.67 |  | On-going
Construction of covered court | Brgy. Tombod, Villasis, Pangasinan | 2135007 | [5 empty] | NYS
Construction of covered court (Gymnasium, Concrete Post) Palisoc | Brgy. Palisoc, Bautista, Pangasinan | 2102206 | [5 empty] | NYS
Construction of Municipal Stage, Calasiao Municipal Plaza | Calasiao, Pangasinan | 2858490 | 2017-08-24 | On-Going | 80% | 2146790.85 |  | On-going
Proposed construction of Multi-Purpose Bldg., | Brgy. San Jose, Alaminos City | 1609006 | 2017-09-04 | 2017-10-20 | 100% | 1565814.05 |  | completed
Construction of Multi-Purpose Hall with covered pathway at NBI Office | Dagupan City | 1169970 | 2017-08-14 | On-Going | 95% | 1111471.5 |  | On-going
Construction and Rehabilitation of Drainage Canal at Mangaldan Public Market, | Mangaldan, Pangasinan | 1185322 | [5 empty] | NYS
Construction of Multi-purpoose Bldg. (covered court) at Sagud Bahley, San Fabian | San Fabian, Pangasinan | 2392170.94 | 2017-03-19 | 2017-05-08 | 100% | 2392170.94 |  | completed
Construction of Bleacher at the Municipal Plaza | Calasiao, Pangasinan | 4089571.2 | 2017-03-19 | 2017-07-13 | 100% | 4089571.2 |  | completed
Rehabilitation of Bleachers, shower rooms, comfort rooms and fence at swimming pool, NRSCC | Lingayen, Pangasinan | 1879825.97 | 2017-04-06 | 2017-07-14 | 100% | 1879825.97 |  | completed
Rehabilitation and repair of Drainage and elevation of concrete pavement at Zone 4, Pangapisan Sur | Lingayen, Pangasinan | 2344069.25 | 2017-06-27 | On-Going | 40% | 937627.7 |  | On-going
Construction of cover court in Brgy. Plaza at Brgy. Carosuca Sur, | Asingan, Pangasinan | 2325964.11 | 2017-04-06 | 2017-07-13 | 100% | 2325964.11 |  | completed
Construction of Multi-purpose Hall 2-Storey Bldg. at Brgy. Labney | San Jacinto | 1543985.3 | 2017-05-14 | 2017-08-14 | 100% | 1543985.3 |  | completed
Improvement of 2-storey Multi-Purpose Bldg., (Brgy. Hall) at Brgy. Magallanes (Phase 1) | Tayug, Pangasinan | 2094367.42 | 2017-05-14 | 2017-09-20 | 100% | 2094367.42 |  | completed
Improvement/extension of Municipal Hall Bldg. | Bugallon, Pangasinan | 6373046.81 | 2017-05-14 | On-Going | 50% | 2613442.85 | w/ extra work order | On-going
Labor, materials, equipment andother incidentals for the improvement/rehabilitation of existing Bachelor Officers Quarter (BOQ) into Senior Officers Quarter (SOQ) Avenida Rizal | Lingayen, Pangasinan | 6102959.46 | 2017-05-25 | On-Going | 70% | 4272071.62 |  | On-going
Extension of swimming pool warm up area w/ shade at NRSCC Cmpd, Lingayen , @100%, part of 294,651.78 is charged to 3917, Revised CP:1195956.06 | Lingayen, Pangasinan | 1126630.36 | 2017-07-03 | Oct. 2017 | 100% | 1126630.36 |  | completed
Repair/rehabilitation of Goat Shed 7m x 18m at OPVET San Quintin Breeding Station | San Quintin, Pangasinan | 549779.26 | 2017-07-13 | 2017-08-25 | 100% | 549779.26 |  | completed
Construction/rehab of various facilities for Drug Rehabilitation Center | Brgy. San Vicente, Burgos, Pangasinan | 2274320.35 | 2017-03-09 | 2017-09-12 | 100% | 2274320.35 |  | completed
Construction of Multi-Purpose Bldg. | Brgy. Palma, Basista, Pangasinan | 2163838.76 | 2017-05-25 | 2017-10-20 | 100% | 2163838.76 |  | completed
Construction of Facilitators' Quarters at Brgy. San Vicente, | Burgos, Pangasinan | 1519183.56 | 2017-05-25 | 2017-07-26 | 100% | 1519183.56 |  | completed
Construction/installation of Street lights at Brgy. Turko, | Laoac, Pangasinan | 217492.87 | 2017-08-02 | 2017-08-18 | 100% | 217492.87 |  | completed
Construction of Day Care Center | San Bonifacio, San Manuel, Pangasinan | 737523.02 | 2017-08-22 | 2017-09-14 | 100% | 737523.02 |  | completed
Repair and rehabilitation of Building at OPAG Field Office | Brgy. Mamabobo, Mangatarem, Pangasinan | 306008.2 |  |  | 100% | 306008.2 |  | completed
Construction of 2 units deep well with jetmatic pumpheads | Brgy. Mantacdang, Umingan, Pangasinan | 113746.07 | 2017-08-14 | 2017-08-24 | 100% | 113746.07 |  | completed
Construction of stone masonry | Brgy. Guibel, San Jacinto | 674179.31 | 2017-05-04 | 2017-05-23 | 100% | 674179.31 |  | completed
Asphalting of Angela Valdez Ramos NH/S | Asingan, Pangasinan | 888962 | 2017-05-18 | 2017-05-23 | 100% | 888962 |  | completed
Costruction of CHB Drainage at Brgy. Poblacion, | Binmaley, Pangasinan | 2355581.2 | 2017-06-21 | 2017-09-08 | 100% | 2355581.2 |  | completed
Labor, materials, equipment and other incidentals for the construction of Drainage Canal (CHB) w/ RCCP | Brgy. Calit, Binmaley, Pangasinan | 1723800 | [5 empty] | nys
Improvement (Raising and Concreting) of Brgy. Gayaman Road (L=200m;W=4.0) | Binmaley, Pangasinan | 2001600 | Sept. 2017 | On-Going | 60% | 1178596.79 |  | On-going
Waterproofing of walls and floor topping of GSO Basement Area, Capitol Bldg. | Lingayen, Pangasinan | 1296540 | 2017-04-06 | 2017-06-01 | 100% | 1296540 |  | completed
Construction of Provincial Shuttle Bus Terminal, Motorpool Cmpd., | Lingayen, Pangasinan | 8188336.39 | 2017-02-17 | On-Going | 90% | 7369502.75 |  | on-going
Labor, materials, equipment and other incidentals for the construction of Training Center #2, Capitol | Lingayen, Pangasinan | 6294300.89 | 2017-05-17 | 2017-07-27 | 100% | 6294300.89 |  | completed
Economic Development
Asphalting of Abalos St., Brgy. Estanza | Lingayen, Pangasinan | 734928 | 2017-08-18 | 2017-08-29 | 100% | 734928 |  | completed
Construction of hanging bridge | Brgy. Garrita, Bani, Pangasinan | 2166649.13 | 2017-04-16 | 2017-08-21 | 100% | 2166649.13 |  | completed
Concreting of Brgy. Pita Road | Brgy. Pita Road, Infanta, Pangasinan | 1496568.25 | 2017-04-16 | 2017-06-23 | 100% | 1496568.25 |  | completed
Concreting of farm to market road, | Brgy. Dorongan Sawat, Mangatarem, Pangasinan | 2539924.54 | 2017-04-16 | 2017-07-03 | 100% | 2539924.54 |  | completed
Concreting of Maligaya-Sitio Banaolan Rd., Brgy. Palaming | San Carlos City | 2217194.75 | 2017-04-16 | 2017-07-03 | 100% | 2217194.75 |  | completed
Concreting of Brgy. Panakol Road | Aguilar, Pangasinan | 1917898.95 | 2017-04-16 | 2017-06-14 | 100% | 1917898.95 |  | completed
Asphalting of Baruan Road, Brgy. Baruan, | Agno, Pangasinan | 3931340 | 2017-06-21 | 2017-07-04 | 100% | 3931340 |  | completed
Concreting of Porok Ilang-ilang Road, Dahlia Road, Rosal Road at Brgy. Buer | Aguilar, Pangasinan | 2145847.44 | 2017-05-14 | 2017-06-27 | 100% | 2145847.44 |  | completed
Concreting of Farm to Market Road Sitio Guilig, Guevara Road, Brgy. Guesang | Mangaldan, Pangasinan | 1922337.75 | 2017-05-14 | 2017-07-17 | 100% | 1922337.75 |  | completed
Improvement (patching/blocktopping) of various provincial Roads | Pangasinan | 10009970 |  |  | 100% | 10009970
Improvement (concreting) of road at Mendoza St. | Brgy. Libsong West, Lingayen | 1924508.74 | 2017-05-14 | On-Going | 90% | 1571712.97 |  | on-going
Concreting of Sitio Senenche Extension Farm to Market Road | Brgy. Pogonsili, Aguilar | 2210648 | 2017-05-25 | 2017-07-04 | 100% | 2210648 |  | completed
Retrofitting of Ramos Bridge | Urbiztondo, Pangasinan | 9995237.32 | 2017-06-19 | 2017-09-05 | 100% | 9995237.32 |  | completed
Retrofitting of Zaragosa Bridge (L=18 mtrs.) | Bolinao, Pangasinan | 5795773.79 | 2017-06-27 | 2017-08-08 | 100% | 5795773.79 |  | completed
Asphalting of Angarian-Banaga Section | Bugallon, Pangasinan | 671173 | 2017-05-03 | 2017-05-09 | 100% | 671173 |  | completed
Blocktopping of Brgy. Road at Brgy. Matalava, Lingayen | Lingayen, Pangasinan | 810689 | 2017-06-29 | 2017-06-30 | 100% | 810689 |  | completed
Blocktopping of Sitio Calay at Brgy. Lomboy | Binmaley, Pangasinan | 956856 | 2017-03-21 | 2017-03-22 | 100% | 956856 |  | completed
Concreting of Sitio Bay-bay Rd. | Brgy. Banaoang, Malasiqui, Pangasinan | 2067818.84 | 2017-08-20 | 2017-10-02 | 100% | 2067818.84 |  | completed
Concreting of Brgy. Barangobong Rd., | Tayug, Pangasinan | 608271.15 | 2017-08-02 | 2017-08-21 | 100% | 608271.15 |  | completed
Concreting of Brgy. Evangelista Rd., | Tayug, Pangasinan | 475666.07 | 2017-08-02 | 2017-08-14 | 100% | 475666.07 |  | completed
Blocktopping of Ignacio St., at Brgy. Poblacion West, | Asingan, Pangasinan | 576700 | 2017-08-07 | 2017-08-17 | 100% | 576409 |  | completed
Concreting of Farm to Market Road Located at Purok 7 Brgy. Bactad East | Urdaneta City | 1999054 | 2017-08-24 | 2017-09-30 | 100% | 1997883 |  | completed
Concreting of Joves Farm to Market Road w/ RCCP | Brgy. Macabito, Calasiao | 1878336 | [5 empty] | nys
Asphalting/blocktopping of Road (Circumferential Area) | Brgy. Poblacion, Anda, Pangasinan | 2541700 | [5 empty] | nys
Construction of Sitio Don Juan Extension Farm to Market Road w/ RCCP | Brgy. Cabiocaan Calasiao, Pangasinan | 1931720 | 2017-09-18 | On-Going | 30% | 579516 |  | on-going
Asphalting of Rose Street and Caimito St., | Mapandan, Pangasinan | 2807800 | [5 empty] | nys
Concreting of Sitio Centro-Sitio Talsi Road, Brgy. Antipangol | San Carlos City | 2247008 | 2017-09-11 | On-Going | 70% | 674102.4 |  | on-going
Patching/blocktopping of Anda Tori-Tori Road | Anda, Pangasinan | 1837200 | [5 empty] | nys
Asphalting of Access Road at NRSCC, Lingayen | Lingayen, Pangasinan | 270800 | 2017-09-04 | 2017-09-18 | 100% | 270624 |  | completed
500 MT Asphalt Pre-mix and 25 drums E. Asphalt 9(SS-1) for use in the maintenance/repair of various provincial roads and bridges | Pangasinan | 3110000
Asphalting/blocktopping of Duyala St. | Mangaldan, Pangasinan | 2130000 | 2017-07-20 | 2017-07-21 | 100% | 2130000 |  | completed
Environmental Development
TOTAL |  | 167959374.42 |  |  |  | 122230948.7
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.