## 20%ira
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2018
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | TOTAL COST | LOCATION | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Repair/improvement of Sison Auditorium | 2552943.75 | Lingayen, Pangasinan | 2018-03-12 | 2018-04-10 | 100% | 2552943.75 |  | OBLIGATED
Repainting works at NRSCC, Lingayen | 785197.88 | Lingayen, Pangasinan |  |  | 100% | 785197.88 |  | OBLIGATED
Improvement of Sport Ground at Alaminos City National High School | 1702815 | Alaminos City | 2018-01-27 | 2018-02-01 | 100% | 1702815 |  | OBLIGATED
Replacement of roofing in rewiring of Main Bldg., Phase II, Mapandan Community Hospital | 6300682.88 | Mapandan, Pangasinan | 2018-03-12 | on-going | 46.25% | 2520273.15 |  | OBLIGATED
Construction of perimeter fence at Dasol Community Hospital | 2147139 | Dasol, Pangasinan | 2018-03-05 | on-going | 26% | 558256.14 |  | OBLIGATED
Completion of Training Center II, Capitol Complex | 15979311 | Lingayen, Pangasinan | 2018-03-13 | on-going | 43.34% | 6925433.3874 |  | OBLIGATED
Proposed construction of Wharf | 2433133 | Brgy. Tori-Tori, Anda | 2018-03-19 | on-going | 40% | 973253.2 |  | OBLIGATED
Construction of drainage canal with concrete cover & CHB canal w/ stiffener | 5849415 | Arellano St., Bautista, Pangasinan | 2018-03-19 | on-going | 39.11% | 2287706.2065 |  | OBLIGATED
Construction of covered court (gymnasium | 3003950 | Brgy. San Felipe East, San Nicolas | NTP - 3/21/18 | on-going | 65.32% | 1962180.14 |  | OBLIGATED
Upgrading of Electrical System at PPH, Phase I | 15090761.88 | San Carlos City | 2018-03-19 | on-going | 48% | 6037438.75 |  | OBLIGATED
Construction of 2-storey Bldg. for Health Center & Conference hall | 1775860 | Brgy. Cacandongan, Bautista, Pangasinan | 2018-03-27 | on-going | 64.67% | 1148448.662 |  | OBLIGATED
Upgrading/construction of Pedia Ward & Isolation Room Bldgs. At Lingayen Dist. Hospital | 5496891.71 | Lingayen, Pangasinan | 2018-01-02 | on-going | 98.33% | 5405093.6184 |  | OBLIGATED
Completion of municipal hall Bldg., | 7417774 | Bugallon, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Asphalt for PNHS, Lingayen Compound | 569100 | Lingayen, Pangasinan | 2018-04-10 | 2018-04-10 | 100% | 569100 |  | OBLIGATED
Ground improvement of Reformation Center Compound (Landscaping) | 666878.66 | San Vicente, Burgos | 2018-02-13 | 2018-03-05 | 100% | 666878.66 |  | OBLIGATED
Construction of 3 units Guard Post and Installation of Lightings at Beachfront | 999732 | Lingayen, Pangasinan | NTP - 2/19/18 |  |  |  |  | OBLIGATED
Construction of Main Guard house and First Aide Post at the Beachfront, Capitol, Lingayen | 829448 | Lingayen, Pangasinan | NTP - 2/19/18 | on-going | 50% | 414724 |  | OBLIGATED
Repair of old Isolation Room into CSSR, fabrication of tables and cabinets at Asingan Community Hospital | 261818.84 | Asingan, Pangasinan | 2018-04-16 | on-going | 25% | 65454.71 |  | OBLIGATED
Labor, materials and other incidentals for the improvement of Main Bldg. at Umingan Community Hospital | 732260.91 | Umingan, Pangasinan | 2018-03-24 | on-going | 17.53% | 128365.3375 |  | OBLIGATED
Construction of Multi-Purpose Hall | 1824727 | Brgy. Bayoyong, Basista | NTP - 3/21/18 | on-going | 3% | 54741.81 |  | OBLIGATED
Extension of concrete ditch at Motorpool Cmpd. | 961405 | Lingayen, Pangasinan | 2018-03-12 | on-going | 39% | 374947.95 |  | OBLIGATED
Rehabilitation of of Processing Bldg./Center at PAGO | 422618.98 | Sta. Barbara, Pangasinan | 2018-03-12 | 2018-03-23 | 100% | 422618.98 |  | OBLIGATED
Construction of 2 units basketball board and flagpole at Pangasinan Reformation Center | 417990.83 | Burgos, Pangasinan | 2018-03-12 | 2018-03-29 | 100% | 417990.83 |  | OBLIGATED
Renovation/improvement of various facilities at Pangasinan Reformation Center | 931556.94 | Brgy. San Vicente, Burgos, Pangasinan | 2018-03-05 | 2018-04-12 | 100% | 931556.94 |  | OBLIGATED
Construction of covered court | 2284443.14 | Pogonsili, Aguilar | 2018-04-10 | on-going | 90% | 2284443.14 |  | OBLIGATED
Completion of Pangasinan Corn Coordinating Center | 1392888 | San Gonzalo, San Quintin | NOT YET STARTED |  |  |  |  | OBLIGATED
Construction of Power House at Pangasinan Provincial Hospital | 924592 | San Carlos City | NTP - 4/2/18 | on-going | 55.67% | 514720.3664 |  | OBLIGATED
Electrical connection at Finance, Malong and ABC Bldgs., in the Province | 766576.75 | Lingayen, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Construction of 3-storey Multi-Purpose Bldg., (Phase 1) at Capitol Cmpd., Lingayen | 17000000 | Lingayen, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Construction of GSO Warehouse (Phase 1) at Capitol Cmpd., Lingayen | 23700000 | Lingayen, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Construction/Rehabilitation of various facilities at OPAG/OPVET | 6708120 | Brgy. Macabobo, Mangatarem | NOT YET STARTED |  |  |  |  | OBLIGATED
Construction of road at OPAG/OPVET at,(with Stone Masonry) | 3074849 | Brgy. Macabobo, Mangatarem | NOT YET STARTED |  |  |  |  | OBLIGATED
Construction of 3 units Artesian Well, | 195000 | San Vicente, San Manuel | 2018-04-20 |  | 10% | 19500 |  | OBLIGATED
Constrruction of 2 units Dug well | 339779.1 | Palapad, San Fabian | 2018-03-23 | 2018-04-19 | 100% |  |  | OBLIGATED
Constrruction of 2 units Dug well, | 310000 | Malokiat, Pozorrubio | 2018-03-14 | on-going | 75% | 232500 |  | OBLIGATED
Construction of 1 unit deep well | 491703.02 | Dulag, Binmaley | 2018-03-12 | 2018-04-18 | 100% | 491703.02 |  | OBLIGATED
Construction of 2 units dug well | 303000 | Anda, Pangasinan | 2018-03-13 | on-going | 93% | 281790 |  | OBLIGATED
Various supplies/materials for the construction of 2 units Artesian Well | 56525 | Parac parac, San Fabian | NOT YET STARTED |  |  |  |  | OBLIGATED
Various supplies/materials for the construction of 2 units Artesian Well | 43052 | San Andres, Umingan | NOT YET STARTED |  |  |  |  | OBLIGATED
Various supplies/materials for the construction of 2 units Artesian Well | 56525 | Sagud Baley, San Fabian | NOT YET STARTED |  |  |  |  | OBLIGATED
Various materials for the construction of 2 units Artesian Well | 49371 | Cayanga, San Fabian | NOT YET STARTED |  |  |  |  | OBLIGATED
Construction of 2 units dug well | 224000 | Sitio San Pedro, San Macario, at Natividad | 2018-04-10 | on-going | 85% | 190400 |  | OBLIGATED
Construction of 2 units Artesian Well | 105354 | Brgy. San Pablo, Umingan | NOT YET STARTED |  |  |  |  | OBLIGATED
OBLIGATED
Economic Development | [7 empty] | OBLIGATED
Asphalt for Access Road, at Reformation Center | 1449180 | San Vicente, Burgos | 2017-12-12 | 2017-12-16 | 100% | 1449180 |  | OBLIGATED
Asphalt for OPAG Main Entrance and Compound | 1316215 | Bolinao, Pangasinan | 2018-01-22 | 2018-01-23 | 100% | 1316215 |  | OBLIGATED
Asphalt for the improvemet/blocktopping of municipal Roads sorrounding Auditorium | 2213300 | Poblacion, Burgos | 2017-12-16 | 2017-12-20 | 100% | 2213300 |  | OBLIGATED
Construction of 1 unit 2-barrel RCBC, Centro Pangapisan | 1171913 | Sual, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Concreting of Antipangal-Pangascasan Road | 1998000 | Bugallon, Pangasinan | 2018-03-20 | on-going | 80% | 1598400 |  | OBLIGATED
Repair/Improvement of Balingasay Bridge | 2192575 | Bolinao, Pangasinan | 2018-03-08 | on-going | 45% | 986658.75 |  | OBLIGATED
Concreting of Fulgosino Road | 2897840 | Umingan, Pangasinan | 2018-03-19 | on-going |  |  |  | OBLIGATED
Improvement of Brgy. Road, Wawa | 2602800 | Lingayen, Pangasinan | 2018-03-20 | on-going | 86% | 2238408 |  | OBLIGATED
Concreting of Brgy. Legaspi Road | 685708.41 | Tayug, Pangasinan | 2018-02-18 | 2018-03-02 | 100% | 685708.41 |  | OBLIGATED
Asphalt for Blocktopping of Brgy. D. Alarcio Road | 1920890 | Laoac, Pangasinan | 2018-02-21 | 2018-02-17 | 100% | 1920890 |  | OBLIGATED
Concreting of Villalon Rd., Zone 1 Flores | 2073074 | San Manuel, Pangasinan | 2018-03-19 | 2018-04-04 | 100% | 2073074 |  | OBLIGATED
Asphalt for blocktopping of Malilion, Sto. Tomas, Canangguan Road | 1898950 | San Nicolas, Pangasinan | 2018-02-28 | 2018-03-02 | 100% | 1898950 |  | OBLIGATED
Construction of 1 unit 3-barrel RCBC, Brgy. Pangascasan | 1445335 | Sual, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Asphalt for the improvemet/blocktopping of Anambongan | 2600275 | Basista, Pangasinan | 2018-03-14 | 2018-03-19 | 100% | 2600275 |  | OBLIGATED
Concreting of San Jacinto, Pozzorubio Road | 3769130 | Pozorrubio, Pangasinan | 2018-03-19 | on-going | 10% | 376913 |  | OBLIGATED
Concreting of Bantocaling w/ slope protection and RCCP | 4812365 | Mangatarem, Pangasinan | 2018-03-19 | on-going | 35% | 1684327.75 |  | OBLIGATED
Concreting of Macarang-Nancalasan Road | 4901369.54 | Mangatarem, Pangasinan | 2018-03-19 | on-going | 40% | 1960547.82 |  | OBLIGATED
Asphalt for blocktopping of Ballag Bridge, | 195900 | Bani, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Asphalt for blocktopping of Pauline Bridge | 314800 | Sta. Barbara, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Asphalt for blocktopping along Sn. Fabian Camp One Rd., | 2497200 | San Fabian, Pangasinan | 2018-01-31 | 2018-02-19 | 100% | 2497200 |  | OBLIGATED
Asphalt for Sito Digap Rd., Fulgosino, | 1826890 | Umingan, Pangasinan | 2018-02-26 | 2018-03-06 | 100% | 1826890 |  | OBLIGATED
Asphalt for blocktopping of Matic-matic Section, Maronong Road | 2497200 | Sta. Barbara, Pangasinan | 2018-02-09 | 2018-02-21 | 100% | 2497200 |  | OBLIGATED
Concreting of Austria St., Dorongan | 215081.49 | Lingayen, Pangasinan | 2018-03-12 | 2018-03-19 | 100% | 215081.49 |  | OBLIGATED
Embarkment, backfilling of Access Road | 1319076 | Sitio Calay, Binmaley | 2018-03-19 |  | 56.2% | 741320.712 |  | OBLIGATED
Concreting Nalsian-Bacayao Road | 2891534 | Calasiao, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Construction of Balucay Bridge, | 6889938 | San Jacinto, Pangasinan | 2018-04-07 |  | 6% | 413396.28 |  | OBLIGATED
Concreting of Sitio Moguing at Brgy. San Felipe West | 3766246 | San Nicolas, Pangasinan | 2018-03-23 |  | 100% | 3766246 |  | OBLIGATED
Improvement/blocktoping of Tayug-Natividad Road | 3079400 | Tayug, Pangasinan | 2018-03-13 | 2018-03-22 | 100% | 3079400 |  | OBLIGATED
Blocktopping of Laguit Centro Road | 2014000 | Brgy. Laguit Centro, Bugallon, Pangasinan | 2018-02-19 | 2018-02-26 | 100% | 2014000 |  | OBLIGATED
Concreting of Salapingao Road | 3425300 | Binmaley, Pangasinan | 2018-04-09 | on-going | 15% | 513795 |  | OBLIGATED
Construction of 1 unit RCBC Castillo St. | 896451 | Lingayen, Pangasinan | 2018-01-24 | on-going | 68% | 609586.68 |  | OBLIGATED
Construction of Drainage Canal with cover | 1564609 | Hermoza, Dasol, Pangasinan | 2018-04-02 | on-going | 39% | 610197.51 |  | OBLIGATED
Concreting of Purok Agnanayon, Aloleng, Agno | 2668917 | Agno, Pangasinan | 2018-04-10 | on-going | 17.25% | 460388.1825 |  | OBLIGATED
Concreting of Brgy. Road | 2458718 | Buayaen, Bayambang, Pangasinan | 2018-04-12 | on-going | 11.43% | 281031.4674 |  | OBLIGATED
Labor, materials, equipment and othe incidentals for the construction of Stone Masonry along Mapandan-Banaoang Road | 990491 | Sta. Barbara, Pangasinan | NTP - 4/2/18 |  |  |  |  | OBLIGATED
Asphalt for bloctopping of Balagan Rd. | 2014000 | Binmaley, Pangasinan | 2018-03-01 | 2018-03-07 | 100% | 2014000 |  | OBLIGATED
Asphalt for blocktopping of Dupo Road | 2693100 | Binmaley, Pangasinan | 2018-02-08 | 2018-02-17 | 100% | 2693100 |  | OBLIGATED
Asphalt for blocktopping of Pozorrubio- Sugcong Rd., (Imbalbalatong Section) | 1098400 | Pozorrubio, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Labor, materials, and other incidentals for the Rehabilitation of Urdaneta Community Bridge, Superstructure | 8728822 | Urdaneta City | NTP - 4/23/17 |  |  |  |  | OBLIGATED
Labor, materials, and other incidentals for the concreting of Sitio Centro, San Jose | 1260449 | Alaminos, Pangasinan | NOT YET STARTED |  |  |  |  | OBLIGATED
Labor, materials, and other incidentals for the rehab of Casabar Brdg., | 2532869 | San Manuel, Pangasinan | 2018-04-12 | on-going | 10% | 253286.9 |  | OBLIGATED
Environmental Development
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA |  |  |  |  | HON. AMADO I. ESPINO, III
Provincial Accountant |  |  |  |  | Governor

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
As of March 31, 2018
Province of Pangasinan
LDRRMF
Particulars | Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 57827134.3 | 134929980.06 |  |  |  | 192757114.36
Continuing Appropriation |  | 8319413.5 |  |  |  | 8319413.5
Previous Year's Appropriation transferred to the Special Trust Fund |  | 152629229.35 |  |  |  | 152629229.35
Transfers/Grants | [5 empty] | 0
Others Interest Income (Trust Fund) | [5 empty] | 0
Total Funds Available | 57827134.3 | 295878622.91 | 0 | 0 | 0 | 353705757.21
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies | [5 empty] | 0
Office Supplies | [5 empty] | 0
Repair of Evacuation Center | [5 empty] | 0
Disaster Response & Rescue Equipment |  | 2125000 |  |  |  | 2125000
Institutional/Capacity Development (Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Capital Outlay - Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses |  | 65165 |  |  |  | 65165
Traveling Expense | [5 empty] | 0
Training Expense |  | 175196 |  |  |  | 175196
IT Equipment & Software | [5 empty] | 0
Motor Vehicles | [5 empty] | 0
Other Machineries and Equipment | [5 empty] | 0
Watercrafts | [5 empty] | 0
Other Property, Plant and Equipment | [5 empty] | 0
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment | [5 empty] | 0
Gasoline, Oil, Lubricants |  | 223855.41 |  |  |  | 223855.41
Drugs and Medicines | [5 empty] | 0
Donations | [5 empty] | 0
Repair & Maintenance-Motor Vehicles |  | 619650 |  |  |  | 619650
Honorarium | [5 empty] | 0
Office Equipment | [5 empty] | 0
Furnitures & Fixtures | [5 empty] | 0
Other Structures |  | 12676905 |  |  |  | 12676905
Other Transportation | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. (Trust Fund) | [5 empty] | 0
Repair & Maintenance - Building & Other Structures (Trust Fund) | [5 empty] | 0
Bank Charges (Trust Fund) | [5 empty] | 0
Reversion to General Fund of the Unutilized LDRRMF - TRUST FUND CY 2012 |  | 3963903.78 |  |  |  | 3963903.78
Reversion to General Fund of the Unutilized LDRRMF - TRUST FUND CY 2011 |  | 2286348.08 |  |  |  | 2286348.08
Total Utilization | 0 | 15885771.41 | 0 | 0 | 0 | 15885771.41
Unutilized Balance | 57827134.3 | 279992851.5 | 0 | 0 | 0 | 337819985.8
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information contained in this document.
ARTURO V. SORIANO
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending March 31, 2018
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 104204417.45
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
13522366.53
Capital Outlay
10504147.33
Financial Expenses
-0-
Sub-total |  |  |  | 24026513.86
Balance |  |  |  | 80177903.59
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
HON. AMADO I. ESPINO, III
Governor
Note on I11: Pangasinan Accounting:

## SCF
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
Statement of Condensed Cash Flows
GENERAL FUND
For the First Quarter Ending March 31,2018
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 77339507.08
|  | Share from Internal Revenue Allotment |  | 794203254
|  | Receipts from business/service income |  | 71362832.68
|  | Interest Income |  | 1107612.41
|  | Other Receipts |  | 26851977.67
|  | Total Cash Inflow |  | 970865183.84
Cash Outflows:
|  | Payment of expenses |  | 211357948.08
|  | Payment to suppliers and creditors |  | 175311980.75
|  | Payment to employees |  | 210833575.19
|  | Interest Expenses |  | 11475591.26
|  | Other Expenses |  | 70325380.39
|  | Total Cash Outflow |  | 679304475.67
| Net Cas Flows from Operating Activities |  |  | 291560708.17
Cash Flows from Investing Activities:
Cash Inflows:
Proceeds from Sale of Investment Property
Proceeds from Sale/Disposal of Property, Plant and Equipment
|  | Collection of Principal on Loans to other Entities |  | 3645800
|  | Total Cash Inflow |  | 3645800
Cash Outflows:
Purchase / Construction of Investment Property
|  | Purchase / Construction of Property, Plant and Equipment |  | 170456847.84
Purchase of Bearer Biological Assets
|  | Grant of Loans |  | 1645000
|  | Total Cash Outflow |  | 172101847.84
| Net Cash Flows from Investing Activities |  |  | -168456047.84
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Loans |  | 103009882.47
|  | Total Cash Inflow |  | 103009882.47
Cash Outflows:
Payment of Long-Term Liabilities
|  | Payment of Loan Amortization |  | 38082313.13
|  | Total Cash Outflow |  | 38082313.13
| Net Cash Flows from Financing Activities |  |  | 64927569.34
Total Cash Provided by Operating,Investing and
|  | Financing Activities |  | 188032229.67
Add:Cash at Beginning of the Quarter |  |  |  | 1449454262.81
Cash at the End of the Quarter |  |  |  | 1637486492.48
Certified Correct:
ARTURO V. SORIANO,CPA
Provincial Accountant

## TRUSTFUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE JANUARY - MARCH QUARTER, CY 2018
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Rehabilitation of Malasiqui - Catablan Road @ Malasiqui and Sta. Barbara, Pangasinan | Malasiqui-Sta. Barbara, Pangasinan | 82640535.64 |  |  | 90% | 74376482.076 |  | fund from the Department of Interior and Local Government-CMGP
Construction of Hall of Fame Building @ Capitol Compound, Lingayen, Pangasinan | Lingayen, Pangasinan | 7888313.2 |  |  | 100% | 7888313.2 |  | fund from the Department of Interior and Local Government-PCF & PLGU Counterpart
Rehabilitation of Malasiqui - Catablan Road, Pangasinan | Malasiqui, Pangasinan | 82640535.64 |  |  | 80% | 66112428.512 |  | fund from the Department of Interior and Local Government-CMGP
Rehabilitation/Improvement/Upgrading of Burgos-Iliw-Iliw Road @ Burgos, Pangasinan | Burgos, Pangasinan | 90037857.42 |  |  | 70% | 63026500.194 |  | fund from the Department of Interior and Local Government-CMGP
Rehabilitation of Banaoang-Mapandan Road @ Sta. Barbara and Mapandan, Pangasinan | Sta. Barbara-Mapandan, Pangasinan | 45009579.52 |  |  | 90% | 40508621.568 |  | fund from the Department of Interior and Local Government-CMGP
7 units Hand Tractor, 7 units Trailer and 7 units Diesel Engine delivered to Mamarlao Multi-Purpose Cooperative under the PRDP-IREAP | Mamarlao, San Carlos City | 872900 |  |  | 60% | 523740 |  | fund from the PRDP-IREAP-LP
650 bags Hybrid yellow corn seeds for use in the subsidy program under Enhancing Hybrid Yellow Corn Production in Pangasinan Phase II (DA) | Sta. Barbara, Pangasinan | 4873700 |  |  | 100% | 4873700 |  | fund from the Department of Agriculture
Improvement / Upgrading of Various Facilities @ Dasol Community Hospital, Dasol, Pangasinan | Dasol, Pangasinan | 11638105.99 |  |  | 15% | 1745715.8985 |  | fund from the Department of Health-HFEP
Improvement / Upgrading of Various Facilities @ Bayambang District Hospital, Bayambang, Pangasinan | Bayambang, Pangasinan | 6181410.34 |  |  | 15% | 927211.551 |  | fund from the Department of Health-HFEP
Improvement / Upgrading of Various Facilities @ Manaoag Community Hospital, Manaoag, Pangasinan | Manaoag, Pangasinan | 7916247.81 |  |  | 15% | 1187437.1715 |  | fund from the Department of Health-HFEP
Construction of Additional Ward at 2nd Floor @ Umingan Community Hospital, Umingan, Pangasinan | Umingan, Pangasinan | 9981138.81 |  |  | 15% | 1497170.8215 |  | fund from the Department of Health-HFEP
Improvement / Upgrading of Various Facilities @ Lingayen District Hospital, Lingayen, Pangasinan | Lingayen, Pangasinan | 9978865.34 |  |  | 15% | 1496829.801 |  | fund from the Department of Health-HFEP
Improvement / Upgrading of Various Facilities @ Asingan Community Hospital, Asingan, Pangasinan | Asingan, Pangasinan | 2158913.43 |  |  | 15% | 323837.0145 |  | fund from the Department of Health-HFEP
Improvement / Upgrading of Various Facilities @ Urdaneta District Hospital, Urdaneta City, Pangasinan | Urdaneta City, Pangasinan | 19850760.7 |  |  | 15% | 2977614.105 |  | fund from the Department of Health-HFEP
Rehabilitation of Urbiztondo-Basista Road @ Urbiztondo and Basista, Pangasinan | Urbiztondo-Basista, Pangasinan | 37338032.56 |  |  | 55% | 20535917.908 |  | fund from the Department of Interior and Local Government-CMGP
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor

## UNLIQUIDATED
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of March 31, 2018
Province, City or Municipality: | PANGASINAN
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Advances for Officers and Employees
Vlady E. Yarisantos | 23780 | 2018-03-22 | cash advance to defray expenses in connection with her attendance to the PHILLBO National Convention April 10-13, 2018 | 23780
Rominda C. Alcantara | 26240 | 2018-03-19 | cash advance to defray expenses in connection with her attendance to the PHILLBO National Convention April 10-13, 2018 | 26240
Elizabeth C. Ramos | 23780 | 2018-03-19 | cash advance to defray expenses in connection with her attendance to the PHILLBO National Convention April 10-13, 2018 | 23780
Hilaria J. Claveria | 23780 | 2018-03-19 | cash advance to defray expenses in connection with her attendance to the PHILLBO National Convention April 10-13, 2018 | 23780
Dolores U. Vinuya | 7460 | 2018-03-16 | cash advance for registration fee, traveling expenses, per diems, and other incidental expenses in connection with her attendance to the Training for the city/municpality roll-out of the LGU Integrated Financial Tools (LIFT) March 22-24, 2018 | 7460
Iris Mischelle J. Campoamor | 7460 | 2018-03-16 | cash advance for registration fee, traveling expenses, per diems, and other incidental expenses in connection with her attendance to the Training for the city/municpality roll-out of the LGU Integrated Financial Tools (LIFT) March 22-24, 2018 | 7460
Binky P. Sajonas | 3200 | 2018-03-08 | pymt of cash advance for his attendance to the Civil Service Commission Regional I Training Program on Leave Administration Course for effectiveness March 20-21, 2018 | 3200
Paul B. Lamsen | 3200 | 2018-03-08 | pymt of cash advance for his attendance to the Civil Service Commission Regional I Training Program on Leave Administration Course for effectiveness March 20-21, 2018 | 3200
Jeanne R. Evangelista | 3200 | 2018-03-08 | pymt of cash advance for her attendance to the Civil Service Commission Regional I Training Program on Leave Administration Course for effectiveness March 20-21, 2018 | 3200
Michelle Anne R. Baniqued | 3200 | 2018-03-08 | pymt of cash advance for her attendance to the Civil Service Commission Regional I Training Program on Leave Administration Course for effectiveness March 20-21, 2018 | 3200
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Sub-total | 192900 |  |  | 125300 | 0 | 0 | 0 | 0 | 67600
Advances to Special Disbursing
Orpheus M. Velasco | 13000 | 2018-03-27 | cash advance the records and meals for Agew na Pangasinan 2018 celebration | 13000
Ellsworth G. Gonzales | 514600 | 2018-03-26 | cash advance to defray expenses for the Limgas na Pangasinan 2018 | 514600
Marife P. Acerit | 110000 | 2018-03-23 | cash advance to defray expenses during the "Kidiyam Variety Show April 5, 2018 | 110000
Ma. Luisa A. Elduayan | 25000 | 2018-03-21 | cash advance top defray expenses for the Abong na Dayew Blessing & Opening of the Hall of Fame Exhibit Apirl 5, 2018 | 25000
Ellsworth G. Gonzales | 60000 | 2018-03-14 | cash advance to defray expenses of Snacks & Lunch to be served during the Screening of Limgas na Pangasinan March 10, 11, 17, & 18, 2018 | 60000
Emilio P. Samson Jr. | 147000 | 2018-03-12 | pymt of cash advances for the prizes, tokens & training materials re: prov'l Womens Convention CY 2018 at Prov'l Training Center, Capitol Compound Lingayen, Pangasinan March 21-22, 2018 | 147000
Marife P. Acerit | 120000 | 2018-03-12 | cash advance to defray expenses for the Commemorative Program Agew na Pangasinan April 5, 2018 | 120000
Orpheus M. Velasco | 177320 | 2018-03-09 | cash advance for publicity and promotions of Umaani Expo 2018 | 177320
Dalisay A. Moya | 488410 | 2018-03-08 | pymt of cash advance to defray expenses of Pangasinan Umaani Expo 2018 March 15-23, 2018 | 488410
Rommel L. Cardinoza | 132000 | 2018-03-06 | cash advance to defray expenses in the conduct of Buntis Congress ast Malasiqui, Pangasinan | 132000
Ma. Luisa A. Elduayan | 25000 | 2018-03-01 | cash advance to defray expenses to Media Assistance for ABS-CBN MagTV Na Atin to 2 day trip in Pangasinan | 25000
Merle Carriaga | 275175 | 2018-02-26 | cash advance to defray expenses for the Set-up of the Pasyar Ed Uma Villa-Farm Exposure, a major component of the Agri-Industrial Trade Fair and Exhibit and major tour destination of the Agew na Saray Ugogaw-Children's Day March 15-24, 2018 |  | 275175
Rodolfo M. Cortez | 300000 | 1997-04-10 | [6 empty] | 300000
Rodolfo M. Cortez | 55800 | 1996-06-20 | [6 empty] | 55800
Sub-total | 2443305 |  |  | 1812330 | 275175 | 0 | 0 | 0 | 355800
GRAND TOTAL | 2636205 |  |  | 1937630 | 275175 |  |  |  | 423400
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor