## 1QTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2021
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Proposed extension of covered court | Brgy. Asan Sur, Sison | 1907572
Extension of Covered court | Brgy. Poblacion Central, Sison | 939003
Completion of Multi-Purpose Bldg., (Gymnasium) | Brgy. Bersamin, Alcala | 1620698
Construction of covered court (Phase 1) | Brgy. Tampog, Bayambang | 740397 |  |  | 100% | 738428.32
Construction of covered court (Gymnasium) | Brgy. Bical Norte (Phase 1), Bayambang | 999883
Construction of stage | Brgy. Duera, Bayambang | 999982 |  |  | 100% | 996994.2
Construction of Multi-purpose Bldg. | Brgy. Perez Riverside, San Carlos City | 1000000
Construction/installation of 29 units Solar streetlights | Brgy. San Gabriel 2nd, Bayambang | 929764 |  |  | 100% | 928788.2
Construction/installation of 29 units Solar streetlights | Brgy. Banaban, Bayambang | 929764 |  |  | 100% | 928788.2
Construction of Library Building Phase 1 | Poblacion, Lingayen | 7000000
Completion of 2-storey Muti-Purpose Bldg., (Brgy. Hall) | Brgy. Magallanes (Phase II), Tayug | 2354780
Construction of covered court (Gymnasium) | Brgy. San Gabriel 1st (Phase 1), Bayambang | 990181
Construction of covered court (Gymnasium) | Brgy. Tamaro (Phase 1), Bayambang | 1040305
Construction of covered court (Phase 1) | Brgy. Darawey, Bayambang | 1040307
Construction of 2-storey Multi-Purpose Hall (Health Center) Phase 1 | Brgy. Manambong Parte, Bayambang | 991902
Construction of Multi-purpose covered court (gymnasium) | Brgy. Palong, Malasiqui | 3234916
Construction of 2-storey Multi-Purpose Brgy. Hall Phase 1 | Brgy. Tambac, Bayambang | 1000000
Construction/installation of 29 units solar streetlights | Brgy. Sanlibo, Bayambang | 929764
Construction/installation of 29 units solar streetlight | Brgy. Paragos, Bayambang | 929764
Repair/improvement of 2-storey Brgy. Hall | Brgy. Bedania, Mangatarem | 985821
Repair/improvement of Bureau of Fire Protection at Manaoag Fire Station | Poblacion, Manaoag | 857551
Rappelling Tower for BFP | Urdaneta City | 2568077
Repair of Imelda Bridge (Last span) at | Mangatarem | 1654613
Rehabilitation of Bayaoas Bridge (Superstructure) | Urdaneta City | 3040565
Labor, materials, incidentals for proposed masonry | Brgy. Sta. Catuna, Binalonan | 1147764
Repair/maintenance of various provincial roads & Bridges with the Province | Pangasinan | 6996000
200 units engine and pump engine set 7 HP to be distributed to the farmers | Pangasinan | 4200000
Various fruit trees seedlings for rural based organizations and other stakeholders of the agri-fishery sector | Pangasinan | 855000
Construction of 1 unit level II Water System | Brgy. Gayaman, Binmaley | 452000
Construction of 1 unit deep well source and instrallation of motor pump with accessories |  | 521000
Construction of 1 unit level II Water System | Brgy. Lomboy, Binmaley | 149144
Construction of 1 unit level II Water System | Brgy. San Isidro Sur, Binmaley | 468500
Construction of 5 units dug well | Brgy. San Juan, San Manuel | 405000
3000 sq.m. Enbankment/common borrow for the backfilling of housing/tenement project | Brgy. Libsong Bliss, Lingayen | 750000
Economic Development
207 MT Pre-mix, 9 drums Emulsified asphalt blocktopping | Brgy. Bued Road, Binalonan | 1485000
Asphalting of Maawi Road | Alaminos City | 1446000
Asphalting of Tangcarang Road, Alaminos City | Alaminos City | 786000
Asphalting of Amangbangan Road, Alaminos City | Alaminos City | 1446000
Concreting of Barangay Road | Brgy. Pogonsili, Aguilar | 1547862
Riprapping/approach of RCBC | Sitio Apoler, Tubuan, Labrador | 1377581
Concreting of Barangay Road | Brgy. Iton, Bayambang | 1000000
Concreting of Farm to Market Road | Brgy. Pugo, Bayambang | 999838
Concreting of Bartolome Junio Road | Brgy. Nalsian Norte, Bayambang | 1000000
Concreting of pathwalk | Brgy. Nalsian Sur, Bayambang | 651073
Concreting of Barangay Road | Brgy. Pinmilapil, Sison | 2632579
Livelihood Projects - Loans Granted to various Associations and MPC's |  | 3680000
Environmental Development
50000 pcs mangrove propagules and 10000 pcs nipa seedlings at the OPAG Provincial Mangrove Nursery, Arnedo, Bolinao |  | 232500
Note on A47: My Lenovo:

## 2QTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2021
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Labor, materials, incidentals for proposed masonry, Brgy. Sta. Catuna, Binalonan | Brgy. Sta. Catuna, Binalonan | 1017634.04 |  |  | 100% | 1017634.04
207 MT Pre-mix, 9 drums Emulsified asphalt blocktopping of Brgy. Bued Road, Binalonan | Brgy. Bued Road, Binalonan | 1481760 |  |  | 100% | 1481760
Concreting of Barangay Road , Brgy. Pogonsili, Aguilar | Brgy. Pogonsili, Aguilar | 1545720.71 |  |  | 100% | 1545720.71
Concreting of pathwalk at Brgy. Nalsian Sur, Bayambang | Brgy. Nalsian Sur, Bayambang | 2626210.36 |  |  | 80% | 2100968.29
Construction of covered court (gymnasium) at Nalsian-Tomling E/S, Malasiqui | Nalsian-Tomling E/S, Malasiqui | 3303836
Construction of sewage Treatment Plant (STP) & installation of swerage Distribution pipline, Mangatarem District Hospital, Mangatarem | Mangatarem District Hospital, Mangatarem | 5564360 |  |  | 90% | 1915857.67
Concreting of Angel Estrellas and Don Pio Road at Brgy. Caloocan Sur, Binmaley | Brgy. Caloocan Sur, Binmaley | 2128730.74 |  |  |  | 2179230
Asphalt for the blocktopping of Brgy. Road at Brgy. Umanday, Bugallon | Brgy. Umanday, Bugallon | 2179230 |  |  |  | 2014590
Blocktopping of Brgy. Road at Purok Birds and Riverside Road, Brgy. Lokeb Este, Malasiqui | Brgy. Lokeb Este, Malasiqui | 2014590 |  |  |  | 3457440
Blocktopping of Agbayani Road, Poblacion, Laoac | Poblacion, Laoac | 3457440
Improvement (Concreting with stone masonry) of Moronong-Sonquil Road, Sta. Barbara (E.W. 2021-8917-1-5-12130, PR#3031, 83099.7) | Moronong-Sonquil Road, Sta. Barbara | 7116654.56 |  |  | 100% | 7033554.86
Rehabilitation of Drainage Canal w/ slope protection along Guesang-Estanza Provincial Road, Lingayen | Guesang-Estanza Provincial Road, Lingayen | 998444.21 |  |  | 100% | 998444.21
Installation of solar street lights at Carusucan Sur, Asingan | Carusucan Sur, Asingan | 461346.08
Fabrication/installation of streetlights at Turho, Laoac | Turho, Laoac | 997225
Expansion of covered court at Artacho, Bautista | Artacho, Bautista | 999735
Asphalting of parking area at Bolinao Community Hospital | Bolinao Community Hospital | 232500
Construction of MP Building (Phase 1) Cabangaran, San Quintin | Cabangaran, San Quintin | 513097
Construction of covered court at Pago, Bautista | Pago, Bautista | 3195024
Installation of 3-100 KVA DX Transformer & Electrical Services at Legislative Bldg., Capitol Cmpd., Lingayen | Capitol Cmpd., Lingayen | 2405875
Installation of 3.75 KVA DX-transformer & Electrical Services at PEO Bldg., Capitol Bldg., Lingayen | Capitol Cmpd., Lingayen | 2893477
Upgrading of distribution transformer & MTS panel at PDRRMO Bldg., & 2-storey Bldg. for Basic Sector at Lingayen | Lingayen | 987935.04
Ground improvement for parking lot of training Center a & 2 at Capitol Cmpd., Lingayen | Capitol Cmpd., Lingayen | 2346874
Construction of 2 MDRRMO Bldg., at Brgy. Poblacion, Sto. Tomas | Brgy. Poblacion, Sto. Tomas | 4430747.6
Construction of perimeter Fence w/ steel gate at Alvear St., Lingayen | Alvear St., Lingayen | 361291
Repair of roofing of main bldg. (OR Section) (Phase 1) at Bayambang District Hospital | Bayambang | 964045
Proposed extension of covered court at Brgy. Sagundo, Sison | Brgy. Sagundo, Sison | 1297483
Improvement of Muti-Purpose Bldg. (Brgy. Hall) Ground Floor at Brgy. Zone III, Villasis | Brgy. Zone III, Villasis | 931765
Asphalting/blocktopping of Pathway w/in OPAG Field Office, Brgy. Arnedo, Bolinao | Brgy. Arnedo, Bolinao | 1130500
Construction/repair/renovation of variouis facilities at Pago, Brgy. Bobonot, Dasol | Brgy. Bobonot, Dasol | 2790534
Replacement of 50 units Solar Street lights at Brgy. Poblacion West and East, Bautista | Brgy. Poblacion West and East, Bautista | 994000
Installation of Enclosure and Cubicles at EPDH covered court for use as temporary facility for Covid-19 patients, Tayug | EPDH, Tayug | 1706737.87
Installation and enclosure of 4 units G.I. Tents as Temporary Isolation area for covid patients at EPDH, Tayug | EPDH, Tayug | 955257
Renovation/repair works for the proposed hemodialysis Bldg. (Phase 1) at WPDH, Alaminos City | WPDH, Alaminos City | 3000000
Construction of ambulance garage and provision/installation of steel gate and grills at Dasol Com. Hospital, Dasol | Dasol Com. Hospital, Dasol | 1847498
Construction of covered court (gymnasium) at Brgy. Rizal, Rosales | Brgy. Rizal, Rosales | 3195024
Repair/improvement of Municipal Circuit Trial Court at Labrador-Sual, Brgy. Poblacion, Labrador | Brgy. Poblacion, Labrador | 1106748
Construction of 2-storey MP Bldg., at Calunetan, Sison | Calunetan, Sison | 2598460
Extra Work Order No. 1 in the rappling tower of BFP, Urdaneta City | Urdaneta City | 243961.34
Solar streetlights for Paponto & Primicias, Bautista | Paponto & Primicias, Bautista | 2367120
Sakoline & modular tents for the isolation, PPH | PPH, San Carlos City | 206992.5
Solar streetlights for Nandacan, Cacandungan, Ketegan, Bautista | Nandacan, Cacandungan, Ketegan, Bautista | 954240
Installation of solar street lights at Pangasinan Reformation Center, Burgos | Pangasinan Reformation Center, Burgos | 572054
Rehabilitation of Barangay Wharf at Siapar North, Brgy. Siapar, Anda | Siapar, Anda | 3909580
Repair/construction of cyclone wire perimeter fence w/ steel gate at Dairy Farm, Laoac | Laoac | 951731
Improvement of Health Center at Canarem, Natividad | Canarem, Natividad | 432311
Repair/rehabilitation of Sison Auditorium at Lingayen | Lingayen | 1861650
Repair/rehabilitation of sweimming pool at CRH, Cpitol Cmpd., Lingayen | Capitol Cmpd., Lingayen | 2595760
Drilling of 2-unit Point Source & Installation of Wter System at Farmer's Training Center, Sta. Barbara | Sta. Barbara | 302700.6
Completion of RHU Bldg., II at Villanueva, Bautista | Villanueva, Bautista | 2293202
Construction of covered court at brgy. Pilar, Bolinao | Pilar, Bolinao | 3707520
Completion/ extension of Multi-Purpose Bldg., at Brgy. Quibaol, Lingayen | Quibaol, Lingayen | 93291
Preventive maintenance/ pallative repair at WPDH, Alaminos City | Alaminos City | 416583
Preventive maintenance/pallative repair of Asingan Com. Hospital | Asingan | 997534
Construction of covered court (gymnasium) at Brgy. Baluyot, Bautista | Baluyot, Bautista | 2440827
Preventive maintenance/pallative repair at Bayambang Dist. Hos. , Bayambang | Bayambang | 755379
Construction of Multi-Purpose Hall (Brgy. Hall) at Brgy. Maigpa, Bayambang | Bayambang | 907550
Construction of Day Care Center (Phase II) at Zone V, Bayambang | Bayambang | 998241
Construction of stage at Brgy. Caturay, Bayambang | Bayambang | 931557
Construction of covered court (gymnasium) at Brgy. Pantol, Bayambang | Bayambang | 999804
Construction of bleachers (phase 1) at Brgy. Buayaen, Bayambang | Buayaen, Bayambang | 999630
Preventive maintenance/pallative repair at Dasol Com. Hospital, Brgy. Bobonot, Dasol | Bobonot, Dasol | 448648
Construction of covered court (gymnasium at Brgy. Batang, Infanta | Batang, Infanta | 1000000
Construction of comfort room at BFP, Lingayen | BFP, Lingayen | 351710
Asphalting/blocktopping of road inside the compound of TESDA, Lingayen | TESDA, Lingayen | 840500
Construction of slope protection along Bantungan Rd., Pozorrubio | Bantungan Rd., Pozorrubio | 198162
Preventive maintenance /pallative repair of roof eaves and ceiling of various Bldgs., at EPDH, Tayug | EPDH, Tayug | 139786
Construction of pedestal & ground improvement of ASNA Monument | Lingayen | 741440
Rehabilitation of Drainage Canal w/ slope protection along Guesang-Estanza Provincial Road, Lingayen | Guesang-Estanza Provincial Road, Lingayen | 998444.21
Concreting of Brgy. Road at Brgy. Tanolong, Bayambang | Tanolong, Bayambang | 1000000
Concreting of Brgy. San Jose-Brgy. Laois Baybay road w/ RCPC, Labrador | Labrador | 1000000
Concreting of FMR, Brgy. Viga, Dasol | Brgy. Viga, Dasol | 1500000
Concreting of pathwalk at Brgy. San Vicente, Bayambang | San Vicente, Bayambang | 1000000
Construction of irrigation canal/sideslope protection along Catblan-Labit-Cabaruan Road, Urdaneta City | Catblan-Labit-Cabaruan Road, Urdaneta City | 5994160.64
Improvement/blocktopping along San Jacinto-San Fabian Rd., San Fabian | San Jacinto-San Fabian Rd., San Fabian | 4950000
Improvement of Brgy. San Juan Road, Agno | San Juan Road, Agno | 1515029
Concreting of Cabaruan Road, Asingan | Asingan | 500000
Concreting of Casilan Road, Asingan | Asingan | 500000
Concreting of pathway at Malilion, San Nicolas | San Nicolas | 487084
Concreting of Cablnongan Road, Rosales | Rosales | 1000000
Concreting of pathwalk, Galdin, Mangaldan | Mangaldan | 499340
Variation Order/extra Work Order No. 1 (upgrading of Urdaneta Asingan via Calipaan Rd., Urdaneta & Asingan) | Urdaneta & Asingan | 3970220.39
Proposed reconstruction of Maambal Bridge, Pozorrubio | Pozorrubio | 8540579
Blocktopping of Casampagaan-Anis Road, Laoac | Laoac | 2494500
Rehabilitation of Bataquil Junction Sison Road, Sison | Sison | 10000000
Improvement(concreting and raising w/ stone masonry) of Poblacion-Dalongue Road., Sta. Barbara | Sta. Barbara | 10000000
Blocktopping at Artacho St., Pozorrubio | Artacho St., Pozorrubio | 2866000
Blocktopping at Penoy St., Pozorrubio | Penoy St., Pozorrubio | 1795500
Concreting of Brgy. Pita Road, Infanta | Pita Road, Infanta | 1000000
Asphalting of Brgy. Road at Brgy. Nayom, Infanta | Nayom, Infanta | 896500
Concreting of Brgy. Maya Road, Infanta | Maya Road, Infanta | 1000000
Asphalting of Brgy. Road at Brgy. Potol, Infanta | Potol, Infanta | 896500
Asphalting of Brgy. Road at Brgy. Fatima, Infanta | Fatima, Infanta | 232500
Asphalting of Brgy. Babuyan Road, Infanta | Babuyan Road, Infanta | 1000000
Asphalting of Brgy. Bambam Road, Infanta | Bambam Road, Infanta | 896500
Asphalting of Brgy. Road, Poblacion, Infanta | oblacion, Infanta | 896500
Asphalting of Brgy. Road, Bayambang, Infanta | Bayambang, Infanta | 896500
Asphalting of Brgy. Road, Nangalisan, Infanta | Nangalisan, Infanta | 896500
Asphalting of Brgy. Road, Tombor, Infanta | Tombor, Infanta | 2499624
Repair/improvement of San carlos Road dike along Agno River | Agno River | 5996000
Construction of 1 unit level II Water System at Brgy. Gayaman, Binmaley | Gayaman, Binmaley | 450703.38 |  |  | 100% | 450703.38
Construction of 1 unit deep well source and installation of motor pump with accessories | Pangasinan | 519520.81 |  |  | 100% | 519520.81
Construction of 1 unit level II Water System at Brgy. Lomboy, Binmaley | Lomboy, Binmaley | 132374 |  |  | 100% | 132374
Construction of 1 unit level II Water System at Brgy. San Isidro Sur, Binmaley | San Isidro Sur, Binmaley | 467204.7 |  |  | 100% | 467204.7
Various materials for the ocnstruction of 4 units shallow well at Gayaman Elem. Sch., Binmaley | Gayaman Elem. Sch., Binmaley | 38562
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Decreto, Umingan | Decreto, Umingan | 47874
Various materials for the construction of 3 units Artesian Well at Brgy. Labuan, Umingan | Labuan, Umingan | 52892
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Carayungan Sur, Umingan | Carayungan Sur, Umingan | 85106
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Casanestebanan, Laoac | Casanestebanan, Laoac | 71693
Various materials for the ocnstruction of 5 units Artesian Well at Brgy. Calmay, Laoac | Calmay, Laoac | 116200
Various material for the construction of 3 units water system and three units artesian well at Brgy. Lasip, Malasiqui | Lasip, Malasiqui | 235350
Labor, materials, equipment and other incidentals for the construction of 1 unit level II Water system at Brgy. Buenlag, Binmaley | Buenlag, Binmaley | 480315
Labor, materials, equipment and other incidentals for the construction of 3 units Artesian Well at Brgy. Tamayo, San Carlos City | Tamayo, San Carlos City | 515700
Various materials for the provision of waterline Network at Sito Tambobong, Villacorta, Mabini | Tambobong, Villacorta, Mabini | 664740
2000 cu.m. enbankment/common borrow for the backfilling of Housing Tenement Project in Libsong Bliss, Lingayen | Bliss, Lingayen | 500000
Economic Development
Water pumps to be distributed to different fisherfolk associations in the Philippines |  |  | 420000
Shallow tubewell irrigation projects for farmers association in the province |  |  | 2870000
Livelihood Projects - Loans Granted to various Associations and MPC's |  |  | 10400000 |  |  | 10400000
Coconut seedling to be distributed to various vegetable growers association |  |  | 225000
Various fruit trees seedlings for rural based organizations and other stakeholders of the agri-fishery sector |  |  | 854200
Amortization of Principal and Interest on Loan to the LBP |  |  | 16332930.41 |  | 100% | 16332930.41
Environmental Development
Note on A127: My Lenovo:

## UNLIQUIDATED CA
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of September 30, 2021
Province, City or Municipality: |  | PANGASINAN
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Advances for Officers and Employees
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Sub-total | 67600 |  |  | 0 | 0 | 0 | 0 | 0 | 67600
Advances to Special Disbursing
Emilio P. Samson, Jr. | 300000 | 2021-09-30 | Payment of cash advance re: Abig Pangasinan Cash for work | 300000
CHRISTINA C. ALCANTARA | 150000 | 2021-09-06 | Cash advance Food & Gasoline of the Hospital Isolation Extension (Halfway house) at Sta. Barbara,Pangasinan | 150000
Evan Gladish P. Domalanta | 100000 | 2021-08-27 | Payment cash advance for expenses to be incurred for tipping fees |  | 100000
Emilio P. samson, Jr. | 200000 | 2021-08-25 | Payment of cash advance re: Abig Pangasinan |  | 200000
Alex T. Sevilla, JR. | 750000 | 2021-08-13 | Payment of cash advance for the purchase of PYPP product |  | 750000
Maria Luisa A. Elduayan | 30000 | 2021-08-10 | Cash advance |  | 30000
Alex F. Ferrer | 97700 | 2021-08-05 | Cash advance |  | 97700
Ms. Rachel Jose | 99350 | 2021-08-05 | Cash advance to defray expenses for the meals & snacks, training kit, misc during the conduct of MSTP training |  | 99350
Jessieca A. Rosario | 750000 | 2021-07-21 | Payment of cash advance for the purchased of PYPP product |  | 750000
Christopher L. Dioquino | 108250 | 2021-07-19 | Cash advance |  | 108250
Josephine L. Bonifacio | 115200 | 2021-07-07 | Cash advance of meals and snacks in the conduct of Abig Pangasinan Tulong Pangkabuhayan |  | 115200
Joan Paulyn Patron | 103100 | 2021-07-06 | Cash advance |  | 103100
Ma. Richelle M. Raguindin | 115200 | 2021-06-17 | Cash advance to defray expenses for the meals and snacks, misc for use at PESO in the conduct of Abig pangasinan Tulong Pangkabuhayan |  | 115200
Marife P. Acerit | 110400 | 2021-06-16 | Cash advance of expenses for Casal Real Building |  | 110400
Maria Luisa A. Elduayan | 50000 | 2021-05-27 | Cash advance to defray expenses for the Ocular Inspection & site validation for Tourism Product and circuit development |  |  | 50000
Alex T. Sevilla, Jr. | 750000 | 2021-05-11 | Payment of cash advance for the purchased of various product to be used for the Pamanang Yaman Produktong Pangasinan project |  |  | 750000
Atty. Verna T. Nava-Perez | 500000 | 2019-04-01 | Cash advance of Talent fee and miscellanoeus for the Agew Na Pangasinan on April 5, 2019 at the Capitol Plaza Lingayen Pangasinan |  |  |  |  | 500000 |  | 1043556
Rodolfo M. Cortez | 20000 | 1997-04-10 | [6 empty] | 20000
Rodolfo M. Cortez | 30000 | 1996-06-20 | [6 empty] | 30000
Sub-total | 4379200 |  |  | 450000 | 2579200 | 800000 | 0 | 500000 | 50000
GRAND TOTAL | 4446800 |  |  | 450000 | 2579200 | 800000 | 0 | 500000 | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO III
Provincial Accountant | [5 empty] | Governor

## TrustFund
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE JULY - SEPTEMBER QUARTER, CY 2021
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Upgrading of Urdaneta - Asingan Road via Calepaan Road @ Urdaneta City and Asingan Pangasinan | Urdaneta City, Pangasinan | 73827936.39 |  |  | 94.62% | 69842525.37 |  | Funds from DILG - CMGP 2020
Rehabilitation of Gonzales-San Juan Farm to Market Road at Umingan Pangasinan | Umingan, Pangasinan | 119270614.79 |  |  | 99.44% | 111215016.13 |  | Funds from DA - PRDP - IBUILD
Construction of Isolation Facility (Phase 1) at PPH, San Carlos City Pangasinan | San Carlos City, Pangasinan | 10000000 |  |  | 65% | 6500000 |  | Funds from DOH
Construction of Tomato Trading Post Facility at Brgy. Tugui Grande for Tugui Grande Fresh Products Farmer's Association, Inc. At Bani, Pangasinan | Bani, Pangasinan | 2885843.5 |  |  | 96% | 2770409.76 |  | Funds from DA - PRDP - IREAP
Construction of 2-Storey Hospital Building (Medical Ward w/ Diagnostic & ER) Phase I, LDH Lingayen, Pangasinan | Lingayen, Pangasinan | 28283445.42 |  |  | 90% | 25455100.88 |  | Funds from DOE-Sual RWMHEEF
TOTAL |  | 234267840.1 |  |  |  | 215783052.14
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO III
Provincial Accountant | [5 empty] | Governor

## CASH FLOW
PROVINCE OF PANGASINAN
GENERAL FUND (100)
Statement of Cash Flows
For the Month-Ended September 30,2021
Cash Flows from Operating Activities:
Cash Inflows:
|  |  | Collection from Taxpayers |  | 6302891.78
|  |  | Share from Internal Revenue Allotment |  | 347754122
|  |  | Receipts from business/service income |  | 30618919.52
|  |  | Interest Income |  | 188895.8
|  |  | Other Receipts |  | 49786154.52
|  |  | Total Cash Inflow |  | 434650983.62
Cash Outflows:
|  |  | Payment of expenses |  | 134928460.5914
|  |  | Payment to suppliers and creditors |  | 51384501.8086
|  |  | Payment to employees |  | 95774941.79
|  |  | Interest Expenses |  | 5703332.37
|  |  | Other Expenses |  | 36051603.56
|  |  | Total Cash Outflow |  | 323842840.12
|  | Net Cas Flows from Operating Activities |  |  | 110808143.5
Cash Flows from Investing Activities:
Cash Inflows:
|  |  | Proceeds from Sale of Investment Property |  | 0
|  |  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 0
|  |  | Proceeds from the Variation Order of Property, Plant and Equipment |  | 37306.07
|  |  | Proceeds from Insurance Claim |  | 0
|  |  | Proceeds from Sale of Biological Assets |  | 0
|  |  | Collection of Principal on Loans to other Entities |  | 1668450
|  |  | Total Cash Inflow |  | 1705756.07
Cash Outflows:
|  |  | Purchase / Construction of Investment Property |  | 0
|  |  | Purchase / Construction of Property, Plant and Equipment |  | 69397406.11
|  |  | Purchase of Bearer Biological Assets |  | 0
|  |  | Grant of Loans |  | 100000
|  |  | Total Cash Outflow |  | 69497406.11
|  | Net Cash Flows from Investing Activities |  |  | -67791650.04
Cash Flows from Financing Activities:
Cash Inflows:
|  |  | Proceeds from Loans |  | 17694669.94
|  |  | Total Cash Inflow |  | 17694669.94
Cash Outflows:
|  |  | Payment of Long-Term Liabilities |  | 0
|  |  | Payment of Loan Amortization |  | 37821872.02
|  |  | Total Cash Outflow |  | 37821872.02
|  | Net Cash Flows from Financing Activities |  |  | -20127202.08
Total Cash Provided by Operating,Investing and
|  |  | Financing Activities |  | 22889291.38
| Add:Cash at Beginning of the month |  |  |  | 2743807919.84
| Cash at the End of the month |  |  |  | 2766697211.22
Certified Correct:
ARTURO V. SORIANO, CPA
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending September 30, 2021
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 177728714.28
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
193817438.72
Capital Outlay
29484927.57
Financial Expenses
-0-
Sub-total |  |  |  | 223302366.29
Balance |  |  |  | -45573652.01
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
HON. AMADO I. ESPINO III
Governor
Note on I11: Pangasinan Accounting:

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
As of September 2021
Province of Pangasinan
LDRRMF
Particulars | Quick Response Fund (QRF) | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| 30% | 70%
A. Sources of Funds:
Current Appropriation | 72491542.5 | 169146932.5 |  |  |  | 241638475
Continuing Appropriation |  | 191080422.68 |  |  |  | 191080422.68
Previous Year's Appropriation transferred to the Special Trust Fund |  | 176795515.09 |  |  |  | 176795515.09
Others Interest Income(Trust Fund) |  | 36558.54 |  |  | 0 | 36558.54
Transfers/Grants |  | 0 | 60678504 |  | 0 | 60678504
Others Interest Income (Trust Fund) | [5 empty] | 0
Total Funds Available | 72491542.5 | 537059428.81 | 60678504 | 0 | 0 | 670229475.31
B. Utilization
Medicines |  | 0 |  |  |  | 0
Medical Supplies |  | 0 |  |  |  | 0
Food Supplies | 42681500 | 29678900 |  |  |  | 72360400
Office Supplies |  | 180140 |  |  |  | 180140
Repair of Evacuation Center |  | 0 |  |  |  | 0
Disaster Response & Rescue Equipment |  | 0 |  |  |  | 0
Institutional/Capacity Development (Ex. Trainings, environmental assessment & other related activities) |  | 0 |  |  |  | 0
Construction of Evacuation Center |  | 0 |  |  |  | 0
Capital Outlay - Equipment |  | 0 |  |  |  | 0
Transfer to other LGUs |  | 0 |  |  |  | 0
Flood Control Systems |  | 0 |  |  |  | 0
Other Maintenance and Operating Expenses |  | 13009060.96 |  |  |  | 13009060.96
Traveling Expense |  | 0 |  |  |  | 0
Training Expense |  | 0 |  |  |  | 0
IT Equipment & Software |  | 1150242 |  |  |  | 1150242
Motor Vehicles |  | 0 |  |  |  | 0
Other Machinery and Equipment |  | 4004280 |  |  |  | 4004280
Watercrafts |  | 0 |  |  |  | 0
Other Property, Plant and Equipment |  | 0 |  |  |  | 0
Roads, Highways and Bridges |  | 0 |  |  |  | 0
Communication Equipment |  | 1174264 |  |  |  | 1174264
Gasoline, Oil, Lubricants |  | 595547.46 |  |  |  | 595547.46
Drugs and Medicines |  | 1500000 |  |  |  | 1500000
Repair & Maintenance-Machinery & Equipment |  | 0 |  |  |  | 0
Repair & Maintenance-Motor Vehicles |  | 2455157 |  |  |  | 2455157
Construction & Heavy Equipment |  | 0 |  |  |  | 0
Office Equipment |  | 1012000 |  |  |  | 1012000
Medical Equipment |  | 176000 |  |  |  | 176000
Furnitures & Fixtures |  | 995800 |  |  |  | 995800
Other Structures |  | 10000000 |  |  |  | 10000000
Other Transportation Equipment |  | 0 |  |  |  | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. (Trust Fund) | [5 empty] | 0
Repair & Maintenance - Building & Other Structures (Trust Fund) | [5 empty] | 0
Bank Charges (Trust Fund) | [5 empty] | 0
Total Utilization (Current Appropriation) | 42681500 | 65931391.42 | 0 | 0 | 0 | 108612891.42
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
COVID-19 Related Expenses |  | 62506750.97 | 0 | 0 | 0 | 62506750.97
Total Utilization (Trust Fund) (Current Appropriation & Trust Fund) | 42681500 | 128438142.39 | 0 | 0 | 0 | 171119642.39
Unutilized Balance | 29810042.5 | 408621286.42 | 60678504 | 0 | 0 | 499109832.92
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Noted by:
ARTURO V. SORIANO, CPA |  |  |  |  | HON. AMADO I. ESPINO III
Provincial Accountant |  |  |  |  | Governor
[7 empty] | 16224466 | Local Budget Circular 130 (LGSF DRMM FY2020)
[7 empty] | 44454038 | Local Budget Circular 134 FY2021 LGSF Disaster Reduction & Rehabilitation Assistance Program FY2021 GAA RA11518
60678504

## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2021
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Construction of drainage canal, Libsong East, Lingayen | Lingayen | 3173176 | [5 empty] | nys
cement & jetmatic pumps for distribution | Pangasinan | 3000375
10,000 bags of cement | Pangasinan | 3000000
10,000 bags of cement | Pangasinan | 3000000
cement & jetmatic pumps | Pangasinan | 3000000
cement, jetmatic pumps; knapsack sprayer | Pangasinan | 1499250
installation of fire detection & alarm system, Asingan Comm. Hospital | Asingan | 2867305 | [5 empty] | nys
installation of fire detection & alarm system, Dasol Comm. Hospital | Dasol | 3339621 | 2021-09-10 | on-going |  |  |  | on-going
installation of fire detection & alarm system, Mapandan Comm, Hospital | Mapandan | 2996387 | [5 empty] | nys
installation of fire detection & Alarm system, Manaoag Comm. Hospital | Manaoag | 3030440 | [5 empty] | nys
Construction of public market, (Phase II), San Nicolas, Pangasinan | San Nicolas | 2847602 | on-going |  | 15.99% | 455331.5598 |  | on-going
Construction of covered court (gymnasium) Pilar, Sta. Maria | Sta. Maria | 2530859 | 2021-09-10 | 2021-11-22 | 75.42% | 1908773.8578 |  | on-going
construction of covered court Antipangol E/S, San Carlos City | San Carlos City | 2514059 | 2021-09-10 | 2022-01-28 | 32.87% | 826371.1933 |  | on-going
Asphalting of reclamation area, Poblacion, Lingayen | Lingayen | 1496000 | 2021-01-27 | 2021-02-04 | 100% | 1496000 |  | completed
Construction of covered court at Sabangan Norte, Boboy, Agno | Agno | 3651571 |  |  |  | 0 |  | nys
Construction of CRH Wellness Building at CRH Compound | Lingayen | 5706103 | 2021-09-24 | on-going |  |  |  | on-going
22 units solar street ligHts at Nibaliw Norte and Sur, Bautista | Bautista | 437360 |  |  |  | 0 |  | nys
15,000 bags of cement for distribution to various barangays | Pangasinan | 4500000 |  |  |  | 0
10,000 bags of cement for distribution to various barangays | Pangasinan | 3000000 |  |  |  | 0
10,000 bags of cement for distribution to various barangays | Pangasinan | 3000000 |  |  |  | 0
10,000 bags of cement for distribution to various barangays | Pangasinan | 3000000 |  |  |  | 0
10,000 bags of cement for distribution to various barangays | Pangasinan | 3000000 |  |  |  | 0
10,000 bags of cement | Pangasinan | 3000000 |  |  |  | 0
cement; jetmatic pumps; GI pipies;knapsack sprayer for distribution to diff. bargy. | Pangasinan | 2973752 |  |  |  | 0
Construction of stage at Brgy. Duera, Bayambang | Bayambang | 996994.2 | 2021-03-12 | 2021-06-15 | 100% | 996994.2 |  | completed
Construction of covered court (Gymnasium) at Brgy. San Gabriel 1st (Phase 1), Bayambang | Bayambang | 987066.5 | 2021-03-12 | 2021-05-24 | 100% | 987066.5 |  | completed
Construction of 2-storey Multi-Purpose Brgy. Hall Phase 1, at Brgy. Tambac, Bayambang | Bayambang | 996695.7 | 2021-03-22 | 2021-06-17 | 100% | 996695.7 |  | completed
Construction/installation of 29 units solar streetlights at Brgy. Sanlibo, Bayambang | Bayambang | 926694.69 | 2021-03-12 | 2021-04-30 | 100% | 926694.69 |  | completed
Construction/installation of 29 units solar streetlight at Brgy. Paragos, Bayambang | Bayambang | 926812.79 | 2021-03-22 | 2021-04-30 | 100% | 926812.79 |  | completed
Installation of solar street lights at Carusucan Sur, Asingan | Asingan | 461346.08 | 2021-05-26 | 2021-06-17 | 100% | 461346.08 |  | completed
Construction of MP Building (Phase 1) Cabangaran, San Quintin | San Quintin | 510992.66 | 2021-05-26 | 2021-07-27 | 100% | 510992.66 |  | completed
Upgrading of distribution transformer & MTS panel at PDRRMO Bldg., & 2-storey Bldg. for Basic Sector at Lingayen | Lingayen | 987935.04 | 2021-05-26 | 2021-07-18 | 100% | 987935.04 |  | completed
Construction of 2 MDRRMO Bldg., at Brgy. Poblacion, Sto. Tomas | Sto. Tomas | 4430747.6 | 2021-06-14 | 2022-04-28 | 80% | 3544598.08 |  | on-going
Repair of roofing of main bldg. (OR Section) (Phase 1) at Bayambang District Hospital | Bayambang | 960876.4 | 2021-06-22 | 2021-07-26 | 100% | 960876.4 |  | completed
Improvement of Muti-Purpose Bldg. (Brgy. Hall) Ground Floor at Brgy. Zone III, Villasis | Villasis | 928397.94 | 2021-06-22 | on-going | 85% | 789138.249 |  | on-going
Replacement of 50 units Solar Street lights at Brgy. Poblacion West and East, Bautista | Bautista | 993500 | Not Stated |  | 100% | 993500 |  | completed
Construction of 1 unit level II water system @ Camaley, Binmaley. | Binmaley | 527485 | 2021-08-11 | 2021-10-15 | 100% | 527485 |  | completed
Rehabilitation of sewage treatment plant - Dasol Community Hospital | Dasol | 1113788 | 2021-09-02 |  |  | #VALUE! |  | nys
Repair of Municipal Slaughterhouse, Bugallon. | Bugallon | 1260632 |  |  |  | 0 |  | nys
Rehabilitation of sewage treatmemnt plant - Bolinao Community Hospital | Bolinao | 1113788 | 2021-09-02 | on-going | 23.71% | 264079.1348 |  | on-going
Drilling, installation of water system at Buneg, Pozorrubio | Pozorrubio | 799659 |  |  |  | 0 |  | nys
Completion of 3 storey PASER C3 Bldg at Lingayen. | Lingayen | 2785886 |  |  |  | 0 |  | nys
Construction of 2 storey multi-purpose building (Phase I), Biec, Binmaley | Binmaley | 1500000 | 2021-09-10 | on-going | 65% | 975000 |  | on-going
Construction of Medicine warehouse - EPDH | Tayug | 3733394.99 | 2021-09-10 | on-going | 92% | 3434723.3908 |  | on-going
Rehabilitation of sewage treatment plant - Pozorrubio Comm. Hosp. | Pozorrubio | 1314668 | 2021-09-10 | on-going | 62.17% | 817329.0956 |  | on-going
Rehabilitation of sewage treatment plant - Asingan Comm. Hosp. | Asingan | 1295708 | 2021-09-10 | on-going | 78% | 1010652.24 |  | on-going
Construction of generator set housing at Pangasinan Reformation Center, San Vicente, Burgos | Burgos | 361040 | on-going |  | 32.14% | 116038.256 |  | on-going
Completion Multi-purpose Hall, Camanggaan, San Nicolas | San Nicolas | 1047020 |  |  |  | 0 |  | nys
Preventive maintenance/pallative repair 2021 at PAgO Nursery, Sta. Barbara | Sta. Barbara | 857916.5 | 2021-03-12 | 2021-04-07 | 100% | 857916.5 |  | completed
Preventive maintenance/pallative repair of Capitol Resort, Lingayen | Lingayen | 497828.05 | 2021-03-12 | 2021-03-29 | 100% | 497828.05 |  | completed
Repair/improvement of 2-storey Brgy. Hall at Brgy. Bedania, Mangatarem | Mangatarem | 982450.13 | 2021-03-12 | 2021-07-09 | 100% | 982450.13 |  | completed
Repair/improvement of Bureau of Fire Protection at Manaoag Fire Station, Poblacion, Manaoag | Manaoag | 854329.49 | 2021-03-12 | 2021-06-03 | 100% | 854329.49 |  | completed
Preventive maintenance/pallative repair at Urdanet District Hospital, Urdaneta City | Urdaneta City | 922149.67 | 2021-03-12 | 2021-04-22 | 100% | 922149.67 |  | completed
Construction of walkway at Western Pangasinan District Hospital (WPDH), Alaminos City | Alaminos City | 281329.26 | 2021-03-12 | 2021-04-06 | 100% | 281329.26 |  | completed
Construction of waiting area at Western Pangasinan District Hospital, (WPDH), Alaminos City | Alaminos City | 301191.2 | 2021-03-12 | 2021-04-08 | 100% | 301191.2 |  | completed
Construction of Comfort Room for the Staff of Isolation Room at Manaoag Community Hospital, Manaoag | Manaoag | 205096.14 | 2021-03-12 | 2021-07-28 | 100% | 205096.14 |  | completed
Various materials for the tapping of waterline and pressure tank for Administrative and OR Building at Bayambang Dist. Hospital, Bayambang | Bayambang | 182685 | 2021-07-28 | 2021-07-30 | 100% | 182685 |  | completed
Construction of 3 units artesian well at Baybay Sur, Sual | Sual | 311024 | 2021-08-11 | 2021-10-22 | 100% | 311024 |  | completed
15 units jetmatic handpump for Nibaliw, San Fabian | San Fabian | 66825 |  |  |  | 0
Construction of 3 units artesian well, Lapalo, San Manuel | San Manuel | 385381 |  |  |  | 0 |  | nys
Construction of 3 units artesian well, Pogo, Bautista | Bautista | 586800 | 2021-08-29 | on-going | 15% | 88020 |  | on-going
Construction of 3 units artesian well, Macabit, Bani | Bani | 46278 |  |  |  | 0 |  | nys
Construction of 3 units artesian well, Capantolan, Sual | Sual | 49089 |  |  |  | 0 |  | nys
Construction of 3 units artesian well, Barat, Umingan | Umingan | 73197 |  |  |  | 0 |  | nys
Construction of 3 units deepwell, Abot Molina, Umingan | Umingan | 63138 |  |  |  | 0 |  | nys
construction of 3 units artesian wells, Tomling, Rosales | Rosales | 171264 |  |  |  | 0 |  | nys
construction of 3 units artesian wells at Lelemaan, Manaoag | Manaoag | 98438 |  |  |  | 0 |  | nys
PR#2035 (4/7/2021) - 1 unit grundos stainless submersible pump with motor, for use at the material assistance for water system, Tambobong, Dasol | Dasol | 114450 |  |  |  | 0
Labor, materials, equipment and other incidentals for the construction of 3 units Artesian Well at Brgy. Tamayo, San Carlos City | San Carlos City | 513623.61 | 2021-05-12 | 2021-07-28 | 100% | 513623.61 |  | completed
Various material for the construction of 3 units water system and three units artesian well at Brgy. Lasip, Malasiqui | Malasiqui | 235150 | 2021-10-04 | 2021-10-04 | 100% | 235150 |  | completed
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Carayungan Sur, Umingan | Umingan | 85006 | 2021-09-27 | 2021-10-22 | 100% | 85006 |  | completed
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Casanestebanan, Laoac | Laoac | 73283 | 2021-05-31 | 2021-07-16 | 100% | 73283 |  | completed
Various materials for the ocnstruction of 5 units Artesian Well at Brgy. Calmay, Laoac | Laoac | 116000 | 2021-07-19 | 2021-09-03 | 100% | 116000 |  | completed
Various materials for the ocnstruction of 4 units shallow well at Gayaman Elem. Sch., Binmaley | Binmaley | 38522 | 2021-05-12 | 2021-04-14 | 100% | 38522 |  | completed
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Decreto, Umingan | Umingan | 47775 | 2021-09-06 | 2021-09-24 | 100% | 47775 |  | completed
Various materials for the construction of 3 units Artesian Well at Brgy. Labuan, Umingan | Umingan | 51192 | 2021-09-13 | 2021-10-01 | 100% | 51192 |  | completed
Construction of 5 units dug well at Brgy. San Juan, San Manuel | San Manuel | 403338.98 | 2021-03-12 | 2021-03-25 | 100% | 403338.98 |  | completed
Provision of Additional Materials & labor for the construction of 3-units Artesian Well at Brgy. San Bonifacio, San Manuel | San Manuel | 299488.86 | Not Stated |  | 100% | 299488.86 |  | completed
3000 sq.m. Enbankment/common borrow for the backfilling of housing/tenement project in Brgy. Libsong Bliss, Lingayen | Lingayen | 749400 | Not Stated |  | 100% | 749400 |  | completed
2000 cu.m. enbankment/common borrow for the backfilling of Housing Tenement Project in Libsong Bliss, Lingayen | Lingayen | 499600 | Not Stated |  | 100% | 499600 |  | completed
Payment of various Medical equipment and Supplies for use of 14 Government Hospitals | Pangasinan | 18751000 |  |  |  | 0
Payment of variousMedical equipment and Supplies for use of 14 Government Hospitals | Pangasinan | 16498000 |  |  |  | 0
Payment of various Medical Supplies and Equipment | Pangasinan | 8469900 |  |  |  | 0
Payment of various Med. Equipment | Pangasinan | 10000600 |  |  |  | 0
Payment of various Medical Equipment for use of various hospitals | Pangasinan | 60600000 |  |  |  | 0
Payment of various Medical Equipment for use at Mangatarem & Bayambang District Hospital | Pangasinan | 44000000 |  |  |  | 0
Payment of various Medical Equipment for use of 14 Government Hospitals | Pangasinan | 19965000 |  |  |  | 0
Upgrading of WPDH & LDH on Fire Detection and Alarm System Sprinkle | Pangasinan | 34839093 |  |  |  | 0 |  | nys
Construction of Diagnostics Center at PPH, San Carlos City (Phase I) | San Carlos City | 36177827 |  |  |  | 0 |  | on-going
Construction of 2 storey Rehab. Building at PPH, San Carlos City (Phase I) | San Carlos City | 60000000 |  |  |  | 0 |  | on-going
Payment of various medical equipment for Pangasinan Molecular Diagnostic Laboratory Reagerts and Kits for Pangasinan Molecular Diagnostics Laboratory, 157 Sars Cov PCR Reagents (96 PCR Reactions), etc. | Pangasinan | 40000000 |  |  |  | 0
Payment of Pick-up truck for use of service vehicle for disease surveilance & contact tracing at PHO | Pangasinan | 1700000 |  |  |  | 0
Payment of 2 units passenger van for use of logistics & laboratory specimen at PHO | Pangasinan | 3000000 |  |  |  | 0
Payment of 3 units equipped ambulance for use of Mangatarem DH, Bayambang DH & PPH | Pangasinan | 11100000 |  |  |  | 0
Payment of 3 units mobile kitchen for use of Nutrition Program of the Province. | Pangasinan | 20913500 |  |  |  | 0
0
0
Blocktopping of Brgy. Alitaya Road, Mangaldan | Mangaldan | 2146000 | 2021-09-07 | 2021-09-14 | 100% | 2146000 |  | completed
FMR w/stone masonry at Bued, Calasiao | Calasiao | 2593588 | 2021-09-02 |  | 31.46% | 815942.7848 |  | on-going
Concreting of Cabaruan Road, Umingan | Umingan | 500000 | 2021-05-26 | 2021-06-08 | 100% | 500000 |  | completed
Concreting of Poblacion - Malimpin Road, Poblacion, Dasol | Dasol | 5000000 | 2021-09-02 | on-going | 57.47% | 2873500 |  | on-going
Concreting of pathwalk, Poblacion, Umingan | Umingan | 500000 |  |  |  | 0
Reconstruction of Imos Bridge, Balungao | Balungao | 5251946 | 2021-09-10 | on-going | 19.35% | 1016251.551 |  | on-going
Blocktopping in Sta. Maria, San Jacinto | San Jacinto | 1588500 | 2021-11-03 | on-going | 45% | 714825 |  | on-going
Blocktopping of brgy. Road in Asinan, Bugallon | Bugallon | 1588500 | 2021-10-01 | 2021-10-07 | 100% | 1588500 |  | completed
Blocktopping of brgy. Road in Nancayasan, Urdaneta City | Urdaneta City | 1765000 | 2021-06-26 | 2021-07-03 | 100% | 1765000 |  | completed
Blocktopping of Lebueg Road Loaoc, Pang. | Laoac | 2668500 | 2021-09-17 | 2021-09-24 | 100% | 2668500 |  | completed
Blocktopping of Cabueldaton road, Malasiqui | Malasiqui | 1059000 |  |  |  | 0 |  | nys
Concreting of Sta. Rosa Road, Umingan | Umingan | 500000 | 2021-08-27 | 2021-08-27 | 100% | 500000 |  | completed
Concreting of Brgy. Cadiz Road, Umingan | Umingan | 500000 | 2021-08-27 | 2021-08-27 | 100% | 500000 |  | completed
Reconstruction of Labit Bridge, Urdaneta City | Urdaneta City | 14986494.26 | 2021-08-27 | 2021-08-27 | 15% | 2247974.139 |  | on-going
Asphalting of San Vicente Road, Bani | Bani | 1335000 | 2021-08-20 | 2021-09-04 | 100% | 1335000 |  | completed
PR#(7/12/2021) - widening of Las Vegas Bridge, Nilombot, Mapandan | Mapandan | 1932993 |  |  |  | 0 |  | nys
1 unit 1 barrel RCBC at Malakiat, Pozorrubio | Pozorrubio | 1671983 | 2021-09-10 | on-going | 30% | 501594.9 |  | on-going
Blocktopping of Lokal Norte Road, Malasiqui | Malasiqui | 1585260 | 2021-11-03 | on-going | 36% | 570693.6 |  | on-going
Concreting of pathwalk, Cabangunan, Umingan | Umingan | 500000 | 2021-08-27 | on-going | 100% | 500000 |  | completed
Concreting of farm to market road, Don Mariano, Umingan | Umingan | 500000 | 2021-08-27 | 2021-09-08 | 100% | 500000 |  | completed
Concreting of Conception road, Umingan | Umingan | 500000 | 2021-08-27 | 2021-09-08 | 100% | 500000 |  | completed
Concreting of pathwalk, Amaronan, Umingan | Umingan | 500000 | 2021-08-27 | 2021-08-27 | 100% | 500000 |  | completed
Concreting of farm to market road Carayungan, Umingan | Umingan | 500000 | 2021-08-27 | 2021-09-08 | 100% | 500000 |  | completed
Concreting of FMR, Cabatuan, Umingan | Umingan | 500000 | 2021-08-27 | 2021-08-27 | 100% | 500000 |  | completed
Blocktopping of Lumbang, Calasiao | Calasiao | 996000 | 2021-10-08 | 2021-10-09 | 100% | 996000 |  | completed
Blocktopping of Longos, Calasiao | Calasiao | 996000 |  |  |  | 0 |  | nys
R/M of roads/bridges w/in the province | Pangasinan | 7000000 |  |  |  | 0
Concreting of FMR, Pampano, Mangatarem, Pang. | Mangatarem | 660000 | 2021-09-13 | on-going | 50% | 330000 |  | on-going
Asphalt for Nibaliw Norte, Bautista, Pang. | Bautista | 734000 | 2021-09-01 | 2021-09-01 | 100% | 734000 |  | completed
Construction of shape protection with concrete barrier along Talog-Pasima Rd., Malasiqui | Malasiqui | 264677 |  |  |  | 0 |  | nys
Construction of drainage canal at Brgy. B. Tayug | Tayug | 994487 |  |  |  | 0 |  | nys
Concreting of Arinaan Road with Stone Masonry and RCCP Nomatucan, Agno | Agno | 6000000 |  |  |  | 0 |  | nys
Rehabilitation of Bataquil Junction Sison Road, Sison | Sison | 9993215.26 | 2021-06-14 | on-going | 15% | 1498982.289 |  | on-going
Concreting of pathwalk, Galdin, Mangaldan | Mangaldan | 498138.18 | 2021-05-26 | 2021-06-09 | 100% | 498138.18 |  | completed
Concreting of Cabalaoangan Road, Rosales | Rosales | 996154.5 | 2021-05-26 | 2021-06-08 | 100% | 996154.5 |  | completed
Concreting of pathway at Malilion, San Nicolas | San Nicolas | 485214.54 | 2021-05-26 | 2021-06-05 | 100% | 485214.54 |  | completed
Concreting of Casilan Road | Umingan | 498022.28 | 2021-05-26 | 2021-06-05 | 100% | 498022.28 |  | completed
Construction of irrigation canal/sideslope protection along Catblan-Labit-Cabaruan Road, Urdaneta City | Urdaneta City | 5994160.64 | 2021-05-28 | on-going | 40% | 2397664.256 |  | on-going
Rehabilitation of Drainage Canal w/ slope protection along Guesang-Estanza Provincial Road, Lingayen | Lingayen | 998444.21 | 2021-05-12 | 2021-07-16 | 100% | 998444.21 |  | completed
Concreting of Brgy. Road at Brgy. Tanolong, Bayambang | Bayambang | 997060.14 | 2021-05-12 | 2021-06-28 | 100% | 997060.14 |  | completed
194 units water pumps & engine set; 5 units flow pumps w/ engine for farmer & fisherfolk association | Pangasinan | 4494000
Various Fishing paraphernalia for farmers assns; irrigators assns; fisherfolk assns & cooperatives | Pangasinan | 2117000
Various free seedlings for farmer, ownerm irrigators assns. & cooperatives | Pangasinan | 1314000
Amortization of Principal and Interest on Loan to the LBP | Pangasinan |  | 74357367.86 |  | 100% | 74357367.86
Environmental Development |  | 111969023.49 |  |  |  | 66684295.3769
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA |  |  |  |  | HON. AMADO I. ESPINO III
Provincial Accountant |  |  |  |  | Governor