## 1QTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2021
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Proposed extension of covered court | Brgy. Asan Sur, Sison | 1907572
Extension of Covered court | Brgy. Poblacion Central, Sison | 939003
Completion of Multi-Purpose Bldg., (Gymnasium) | Brgy. Bersamin, Alcala | 1620698
Construction of covered court (Phase 1) | Brgy. Tampog, Bayambang | 740397 |  |  | 100% | 738428.32
Construction of covered court (Gymnasium) | Brgy. Bical Norte (Phase 1), Bayambang | 999883
Construction of stage | Brgy. Duera, Bayambang | 999982 |  |  | 100% | 996994.2
Construction of Multi-purpose Bldg. | Brgy. Perez Riverside, San Carlos City | 1000000
Construction/installation of 29 units Solar streetlights | Brgy. San Gabriel 2nd, Bayambang | 929764 |  |  | 100% | 928788.2
Construction/installation of 29 units Solar streetlights | Brgy. Banaban, Bayambang | 929764 |  |  | 100% | 928788.2
Construction of Library Building Phase 1 | Poblacion, Lingayen | 7000000
Completion of 2-storey Muti-Purpose Bldg., (Brgy. Hall) | Brgy. Magallanes (Phase II), Tayug | 2354780
Construction of covered court (Gymnasium) | Brgy. San Gabriel 1st (Phase 1), Bayambang | 990181
Construction of covered court (Gymnasium) | Brgy. Tamaro (Phase 1), Bayambang | 1040305
Construction of covered court (Phase 1) | Brgy. Darawey, Bayambang | 1040307
Construction of 2-storey Multi-Purpose Hall (Health Center) Phase 1 | Brgy. Manambong Parte, Bayambang | 991902
Construction of Multi-purpose covered court (gymnasium) | Brgy. Palong, Malasiqui | 3234916
Construction of 2-storey Multi-Purpose Brgy. Hall Phase 1 | Brgy. Tambac, Bayambang | 1000000
Construction/installation of 29 units solar streetlights | Brgy. Sanlibo, Bayambang | 929764
Construction/installation of 29 units solar streetlight | Brgy. Paragos, Bayambang | 929764
Repair/improvement of 2-storey Brgy. Hall | Brgy. Bedania, Mangatarem | 985821
Repair/improvement of Bureau of Fire Protection at Manaoag Fire Station | Poblacion, Manaoag | 857551
Rappelling Tower for BFP | Urdaneta City | 2568077
Repair of Imelda Bridge (Last span) at | Mangatarem | 1654613
Rehabilitation of Bayaoas Bridge (Superstructure) | Urdaneta City | 3040565
Labor, materials, incidentals for proposed masonry | Brgy. Sta. Catuna, Binalonan | 1147764
Repair/maintenance of various provincial roads & Bridges with the Province | Pangasinan | 6996000
200 units engine and pump engine set 7 HP to be distributed to the farmers | Pangasinan | 4200000
Various fruit trees seedlings for rural based organizations and other stakeholders of the agri-fishery sector | Pangasinan | 855000
Construction of 1 unit level II Water System | Brgy. Gayaman, Binmaley | 452000
Construction of 1 unit deep well source and instrallation of motor pump with accessories |  | 521000
Construction of 1 unit level II Water System | Brgy. Lomboy, Binmaley | 149144
Construction of 1 unit level II Water System | Brgy. San Isidro Sur, Binmaley | 468500
Construction of 5 units dug well | Brgy. San Juan, San Manuel | 405000
3000 sq.m. Enbankment/common borrow for the backfilling of housing/tenement project | Brgy. Libsong Bliss, Lingayen | 750000
Economic Development
207 MT Pre-mix, 9 drums Emulsified asphalt blocktopping | Brgy. Bued Road, Binalonan | 1485000
Asphalting of Maawi Road | Alaminos City | 1446000
Asphalting of Tangcarang Road, Alaminos City | Alaminos City | 786000
Asphalting of Amangbangan Road, Alaminos City | Alaminos City | 1446000
Concreting of Barangay Road | Brgy. Pogonsili, Aguilar | 1547862
Riprapping/approach of RCBC | Sitio Apoler, Tubuan, Labrador | 1377581
Concreting of Barangay Road | Brgy. Iton, Bayambang | 1000000
Concreting of Farm to Market Road | Brgy. Pugo, Bayambang | 999838
Concreting of Bartolome Junio Road | Brgy. Nalsian Norte, Bayambang | 1000000
Concreting of pathwalk | Brgy. Nalsian Sur, Bayambang | 651073
Concreting of Barangay Road | Brgy. Pinmilapil, Sison | 2632579
Livelihood Projects - Loans Granted to various Associations and MPC's |  | 3680000
Environmental Development
50000 pcs mangrove propagules and 10000 pcs nipa seedlings at the OPAG Provincial Mangrove Nursery, Arnedo, Bolinao |  | 232500

## 2QTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2021
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Labor, materials, incidentals for proposed masonry, Brgy. Sta. Catuna, Binalonan | Brgy. Sta. Catuna, Binalonan | 1017634.04 |  |  | 100% | 1017634.04
207 MT Pre-mix, 9 drums Emulsified asphalt blocktopping of Brgy. Bued Road, Binalonan | Brgy. Bued Road, Binalonan | 1481760 |  |  | 100% | 1481760
Concreting of Barangay Road , Brgy. Pogonsili, Aguilar | Brgy. Pogonsili, Aguilar | 1545720.71 |  |  | 100% | 1545720.71
Concreting of pathwalk at Brgy. Nalsian Sur, Bayambang | Brgy. Nalsian Sur, Bayambang | 2626210.36 |  |  | 80% | 2100968.29
Construction of covered court (gymnasium) at Nalsian-Tomling E/S, Malasiqui | Nalsian-Tomling E/S, Malasiqui | 3303836
Construction of sewage Treatment Plant (STP) & installation of swerage Distribution pipline, Mangatarem District Hospital, Mangatarem | Mangatarem District Hospital, Mangatarem | 5564360 |  |  | 90% | 1915857.67
Concreting of Angel Estrellas and Don Pio Road at Brgy. Caloocan Sur, Binmaley | Brgy. Caloocan Sur, Binmaley | 2128730.74 |  |  |  | 2179230
Asphalt for the blocktopping of Brgy. Road at Brgy. Umanday, Bugallon | Brgy. Umanday, Bugallon | 2179230 |  |  |  | 2014590
Blocktopping of Brgy. Road at Purok Birds and Riverside Road, Brgy. Lokeb Este, Malasiqui | Brgy. Lokeb Este, Malasiqui | 2014590 |  |  |  | 3457440
Blocktopping of Agbayani Road, Poblacion, Laoac | Poblacion, Laoac | 3457440
Improvement (Concreting with stone masonry) of Moronong-Sonquil Road, Sta. Barbara (E.W. 2021-8917-1-5-12130, PR#3031, 83099.7) | Moronong-Sonquil Road, Sta. Barbara | 7116654.56 |  |  | 100% | 7033554.86
Rehabilitation of Drainage Canal w/ slope protection along Guesang-Estanza Provincial Road, Lingayen | Guesang-Estanza Provincial Road, Lingayen | 998444.21 |  |  | 100% | 998444.21
Installation of solar street lights at Carusucan Sur, Asingan | Carusucan Sur, Asingan | 461346.08
Fabrication/installation of streetlights at Turho, Laoac | Turho, Laoac | 997225
Expansion of covered court at Artacho, Bautista | Artacho, Bautista | 999735
Asphalting of parking area at Bolinao Community Hospital | Bolinao Community Hospital | 232500
Construction of MP Building (Phase 1) Cabangaran, San Quintin | Cabangaran, San Quintin | 513097
Construction of covered court at Pago, Bautista | Pago, Bautista | 3195024
Installation of 3-100 KVA DX Transformer & Electrical Services at Legislative Bldg., Capitol Cmpd., Lingayen | Capitol Cmpd., Lingayen | 2405875
Installation of 3.75 KVA DX-transformer & Electrical Services at PEO Bldg., Capitol Bldg., Lingayen | Capitol Cmpd., Lingayen | 2893477
Upgrading of distribution transformer & MTS panel at PDRRMO Bldg., & 2-storey Bldg. for Basic Sector at Lingayen | Lingayen | 987935.04
Ground improvement for parking lot of training Center a & 2 at Capitol Cmpd., Lingayen | Capitol Cmpd., Lingayen | 2346874
Construction of 2 MDRRMO Bldg., at Brgy. Poblacion, Sto. Tomas | Brgy. Poblacion, Sto. Tomas | 4430747.6
Construction of perimeter Fence w/ steel gate at Alvear St., Lingayen | Alvear St., Lingayen | 361291
Repair of roofing of main bldg. (OR Section) (Phase 1) at Bayambang District Hospital | Bayambang | 964045
Proposed extension of covered court at Brgy. Sagundo, Sison | Brgy. Sagundo, Sison | 1297483
Improvement of Muti-Purpose Bldg. (Brgy. Hall) Ground Floor at Brgy. Zone III, Villasis | Brgy. Zone III, Villasis | 931765
Asphalting/blocktopping of Pathway w/in OPAG Field Office, Brgy. Arnedo, Bolinao | Brgy. Arnedo, Bolinao | 1130500
Construction/repair/renovation of variouis facilities at Pago, Brgy. Bobonot, Dasol | Brgy. Bobonot, Dasol | 2790534
Replacement of 50 units Solar Street lights at Brgy. Poblacion West and East, Bautista | Brgy. Poblacion West and East, Bautista | 994000
Installation of Enclosure and Cubicles at EPDH covered court for use as temporary facility for Covid-19 patients, Tayug | EPDH, Tayug | 1706737.87
Installation and enclosure of 4 units G.I. Tents as Temporary Isolation area for covid patients at EPDH, Tayug | EPDH, Tayug | 955257
Renovation/repair works for the proposed hemodialysis Bldg. (Phase 1) at WPDH, Alaminos City | WPDH, Alaminos City | 3000000
Construction of ambulance garage and provision/installation of steel gate and grills at Dasol Com. Hospital, Dasol | Dasol Com. Hospital, Dasol | 1847498
Construction of covered court (gymnasium) at Brgy. Rizal, Rosales | Brgy. Rizal, Rosales | 3195024
Repair/improvement of Municipal Circuit Trial Court at Labrador-Sual, Brgy. Poblacion, Labrador | Brgy. Poblacion, Labrador | 1106748
Construction of 2-storey MP Bldg., at Calunetan, Sison | Calunetan, Sison | 2598460
Extra Work Order No. 1 in the rappling tower of BFP, Urdaneta City | Urdaneta City | 243961.34
Solar streetlights for Paponto & Primicias, Bautista | Paponto & Primicias, Bautista | 2367120
Sakoline & modular tents for the isolation, PPH | PPH, San Carlos City | 206992.5
Solar streetlights for Nandacan, Cacandungan, Ketegan, Bautista | Nandacan, Cacandungan, Ketegan, Bautista | 954240
Installation of solar street lights at Pangasinan Reformation Center, Burgos | Pangasinan Reformation Center, Burgos | 572054
Rehabilitation of Barangay Wharf at Siapar North, Brgy. Siapar, Anda | Siapar, Anda | 3909580
Repair/construction of cyclone wire perimeter fence w/ steel gate at Dairy Farm, Laoac | Laoac | 951731
Improvement of Health Center at Canarem, Natividad | Canarem, Natividad | 432311
Repair/rehabilitation of Sison Auditorium at Lingayen | Lingayen | 1861650
Repair/rehabilitation of sweimming pool at CRH, Cpitol Cmpd., Lingayen | Capitol Cmpd., Lingayen | 2595760
Drilling of 2-unit Point Source & Installation of Wter System at Farmer's Training Center, Sta. Barbara | Sta. Barbara | 302700.6
Completion of RHU Bldg., II at Villanueva, Bautista | Villanueva, Bautista | 2293202
Construction of covered court at brgy. Pilar, Bolinao | Pilar, Bolinao | 3707520
Completion/ extension of Multi-Purpose Bldg., at Brgy. Quibaol, Lingayen | Quibaol, Lingayen | 93291
Preventive maintenance/ pallative repair at WPDH, Alaminos City | Alaminos City | 416583
Preventive maintenance/pallative repair of Asingan Com. Hospital | Asingan | 997534
Construction of covered court (gymnasium) at Brgy. Baluyot, Bautista | Baluyot, Bautista | 2440827
Preventive maintenance/pallative repair at Bayambang Dist. Hos. , Bayambang | Bayambang | 755379
Construction of Multi-Purpose Hall (Brgy. Hall) at Brgy. Maigpa, Bayambang | Bayambang | 907550
Construction of Day Care Center (Phase II) at Zone V, Bayambang | Bayambang | 998241
Construction of stage at Brgy. Caturay, Bayambang | Bayambang | 931557
Construction of covered court (gymnasium) at Brgy. Pantol, Bayambang | Bayambang | 999804
Construction of bleachers (phase 1) at Brgy. Buayaen, Bayambang | Buayaen, Bayambang | 999630
Preventive maintenance/pallative repair at Dasol Com. Hospital, Brgy. Bobonot, Dasol | Bobonot, Dasol | 448648
Construction of covered court (gymnasium at Brgy. Batang, Infanta | Batang, Infanta | 1000000
Construction of comfort room at BFP, Lingayen | BFP, Lingayen | 351710
Asphalting/blocktopping of road inside the compound of TESDA, Lingayen | TESDA, Lingayen | 840500
Construction of slope protection along Bantungan Rd., Pozorrubio | Bantungan Rd., Pozorrubio | 198162
Preventive maintenance /pallative repair of roof eaves and ceiling of various Bldgs., at EPDH, Tayug | EPDH, Tayug | 139786
Construction of pedestal & ground improvement of ASNA Monument | Lingayen | 741440
Rehabilitation of Drainage Canal w/ slope protection along Guesang-Estanza Provincial Road, Lingayen | Guesang-Estanza Provincial Road, Lingayen | 998444.21
Concreting of Brgy. Road at Brgy. Tanolong, Bayambang | Tanolong, Bayambang | 1000000
Concreting of Brgy. San Jose-Brgy. Laois Baybay road w/ RCPC, Labrador | Labrador | 1000000
Concreting of FMR, Brgy. Viga, Dasol | Brgy. Viga, Dasol | 1500000
Concreting of pathwalk at Brgy. San Vicente, Bayambang | San Vicente, Bayambang | 1000000
Construction of irrigation canal/sideslope protection along Catblan-Labit-Cabaruan Road, Urdaneta City | Catblan-Labit-Cabaruan Road, Urdaneta City | 5994160.64
Improvement/blocktopping along San Jacinto-San Fabian Rd., San Fabian | San Jacinto-San Fabian Rd., San Fabian | 4950000
Improvement of Brgy. San Juan Road, Agno | San Juan Road, Agno | 1515029
Concreting of Cabaruan Road, Asingan | Asingan | 500000
Concreting of Casilan Road, Asingan | Asingan | 500000
Concreting of pathway at Malilion, San Nicolas | San Nicolas | 487084
Concreting of Cablnongan Road, Rosales | Rosales | 1000000
Concreting of pathwalk, Galdin, Mangaldan | Mangaldan | 499340
Variation Order/extra Work Order No. 1 (upgrading of Urdaneta Asingan via Calipaan Rd., Urdaneta & Asingan) | Urdaneta & Asingan | 3970220.39
Proposed reconstruction of Maambal Bridge, Pozorrubio | Pozorrubio | 8540579
Blocktopping of Casampagaan-Anis Road, Laoac | Laoac | 2494500
Rehabilitation of Bataquil Junction Sison Road, Sison | Sison | 10000000
Improvement(concreting and raising w/ stone masonry) of Poblacion-Dalongue Road., Sta. Barbara | Sta. Barbara | 10000000
Blocktopping at Artacho St., Pozorrubio | Artacho St., Pozorrubio | 2866000
Blocktopping at Penoy St., Pozorrubio | Penoy St., Pozorrubio | 1795500
Concreting of Brgy. Pita Road, Infanta | Pita Road, Infanta | 1000000
Asphalting of Brgy. Road at Brgy. Nayom, Infanta | Nayom, Infanta | 896500
Concreting of Brgy. Maya Road, Infanta | Maya Road, Infanta | 1000000
Asphalting of Brgy. Road at Brgy. Potol, Infanta | Potol, Infanta | 896500
Asphalting of Brgy. Road at Brgy. Fatima, Infanta | Fatima, Infanta | 232500
Asphalting of Brgy. Babuyan Road, Infanta | Babuyan Road, Infanta | 1000000
Asphalting of Brgy. Bambam Road, Infanta | Bambam Road, Infanta | 896500
Asphalting of Brgy. Road, Poblacion, Infanta | oblacion, Infanta | 896500
Asphalting of Brgy. Road, Bayambang, Infanta | Bayambang, Infanta | 896500
Asphalting of Brgy. Road, Nangalisan, Infanta | Nangalisan, Infanta | 896500
Asphalting of Brgy. Road, Tombor, Infanta | Tombor, Infanta | 2499624
Repair/improvement of San carlos Road dike along Agno River | Agno River | 5996000
Construction of 1 unit level II Water System at Brgy. Gayaman, Binmaley | Gayaman, Binmaley | 450703.38 |  |  | 100% | 450703.38
Construction of 1 unit deep well source and installation of motor pump with accessories | Pangasinan | 519520.81 |  |  | 100% | 519520.81
Construction of 1 unit level II Water System at Brgy. Lomboy, Binmaley | Lomboy, Binmaley | 132374 |  |  | 100% | 132374
Construction of 1 unit level II Water System at Brgy. San Isidro Sur, Binmaley | San Isidro Sur, Binmaley | 467204.7 |  |  | 100% | 467204.7
Various materials for the ocnstruction of 4 units shallow well at Gayaman Elem. Sch., Binmaley | Gayaman Elem. Sch., Binmaley | 38562
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Decreto, Umingan | Decreto, Umingan | 47874
Various materials for the construction of 3 units Artesian Well at Brgy. Labuan, Umingan | Labuan, Umingan | 52892
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Carayungan Sur, Umingan | Carayungan Sur, Umingan | 85106
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Casanestebanan, Laoac | Casanestebanan, Laoac | 71693
Various materials for the ocnstruction of 5 units Artesian Well at Brgy. Calmay, Laoac | Calmay, Laoac | 116200
Various material for the construction of 3 units water system and three units artesian well at Brgy. Lasip, Malasiqui | Lasip, Malasiqui | 235350
Labor, materials, equipment and other incidentals for the construction of 1 unit level II Water system at Brgy. Buenlag, Binmaley | Buenlag, Binmaley | 480315
Labor, materials, equipment and other incidentals for the construction of 3 units Artesian Well at Brgy. Tamayo, San Carlos City | Tamayo, San Carlos City | 515700
Various materials for the provision of waterline Network at Sito Tambobong, Villacorta, Mabini | Tambobong, Villacorta, Mabini | 664740
2000 cu.m. enbankment/common borrow for the backfilling of Housing Tenement Project in Libsong Bliss, Lingayen | Bliss, Lingayen | 500000
Economic Development
Water pumps to be distributed to different fisherfolk associations in the Philippines |  |  | 420000
Shallow tubewell irrigation projects for farmers association in the province |  |  | 2870000
Livelihood Projects - Loans Granted to various Associations and MPC's |  |  | 10400000 |  |  | 10400000
Coconut seedling to be distributed to various vegetable growers association |  |  | 225000
Various fruit trees seedlings for rural based organizations and other stakeholders of the agri-fishery sector |  |  | 854200
Amortization of Principal and Interest on Loan to the LBP |  |  | 16332930.41 |  | 100% | 16332930.41
Environmental Development

## 3QTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2021
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Construction of drainage canal, Libsong East, Lingayen | Lingayen | 3173176
cement & jetmatic pumps for distribution | Pangasinan | 3000375
10,000 bags of cement | Pangasinan | 3000000
10,000 bags of cement | Pangasinan | 3000000
cement & jetmatic pumps | Pangasinan | 3000000
cement, jetmatic pumps; knapsack sprayer | Pangasinan | 1499250
installation of fire detection & alarm system, Asingan Comm. Hospital | Asingan | 2867305
installation of fire detection & alarm system, Dasol Comm. Hospital | Dasol | 3339621
installation of fire detection & alarm system, Mapandan Comm, Hospital | Mapandan | 2996387
installation of fire detection & Alarm system, Manaoag Comm. Hospital | Manaoag | 3030440
Construction of public market, (Phase II), San Nicolas, Pangasinan | San Nicolas | 2847602
Construction of covered court (gymnasium) Pilar, Sta. Maria | Sta. Maria | 2530859
construction of covered court Antipangol E/S, San Carlos City | San Carlos City | 2514059
Asphalting of reclamation area, Poblacion, Lingayen | Lingayen | 1496000
Construction of covered court at Sabangan Norte, Boboy, Agno | Agno | 3651571
Construction of CRH Wellness Building at CRH Compound | Lingayen | 5706103
22 units solar street ligHts at Nibaliw Norte and Sur, Bautista | Bautista | 437360
15,000 bags of cement for distribution to various barangays | Pangasinan | 4500000
10,000 bags of cement for distribution to various barangays | Pangasinan | 3000000
10,000 bags of cement for distribution to various barangays | Pangasinan | 3000000
10,000 bags of cement for distribution to various barangays | Pangasinan | 3000000
10,000 bags of cement for distribution to various barangays | Pangasinan | 3000000
10,000 bags of cement | Pangasinan | 3000000
cement; jetmatic pumps; GI pipies;knapsack sprayer for distribution to diff. bargy. | Pangasinan | 2973752
Construction of stage at Brgy. Duera, Bayambang | Bayambang | 996994.2 |  |  | 100% | 996994.2
Construction of covered court (Gymnasium) at Brgy. San Gabriel 1st (Phase 1), Bayambang | Bayambang | 987066.5 |  |  | 100% | 987066.5
Construction of 2-storey Multi-Purpose Brgy. Hall Phase 1, at Brgy. Tambac, Bayambang | Bayambang | 996695.7 |  |  | 100% | 996695.7
Construction/installation of 29 units solar streetlights at Brgy. Sanlibo, Bayambang | Bayambang | 926694.69 |  |  | 100% | 926694.69
Construction/installation of 29 units solar streetlight at Brgy. Paragos, Bayambang | Bayambang | 926812.79 |  |  | 100% | 926812.79
Installation of solar street lights at Carusucan Sur, Asingan | Asingan | 461346.08 |  |  | 100% | 461346.08
Construction of MP Building (Phase 1) Cabangaran, San Quintin | San Quintin | 510992.66 |  |  | 100% | 510992.66
Upgrading of distribution transformer & MTS panel at PDRRMO Bldg., & 2-storey Bldg. for Basic Sector at Lingayen | Lingayen | 987935.04 |  |  | 100% | 987935.04
Construction of 2 MDRRMO Bldg., at Brgy. Poblacion, Sto. Tomas | Sto. Tomas | 4430747.6 |  |  | 80% | 3544598.11
Repair of roofing of main bldg. (OR Section) (Phase 1) at Bayambang District Hospital | Bayambang | 960876.4 |  |  | 100% | 960876.4
Improvement of Muti-Purpose Bldg. (Brgy. Hall) Ground Floor at Brgy. Zone III, Villasis | Villasis | 928397.94 |  |  | 85% | 789138.25
Replacement of 50 units Solar Street lights at Brgy. Poblacion West and East, Bautista | Bautista | 993500 |  |  | 100% | 993500
Construction of 1 unit level II water system @ Camaley, Binmaley. | Binmaley | 527485
Rehabilitation of sewage treatment plant - Dasol Community Hospital | Dasol | 1113788
Repair of Municipal Slaughterhouse, Bugallon. | Bugallon | 1260632
Rehabilitation of sewage treatmemnt plant - Bolinao Community Hospital | Bolinao | 1113788
Drilling, installation of water system at Buneg, Pozorrubio | Pozorrubio | 799659
Completion of 3 storey PASER C3 Bldg at Lingayen. | Lingayen | 2785886
Construction of 2 storey multi-purpose building (Phase I), Biec, Binmaley | Binmaley | 1500000
Construction of Medicine warehouse - EPDH | Tayug | 3733394.99
Rehabilitation of sewage treatment plant - Pozorrubio Comm. Hosp. | Pozorrubio | 1314668
Rehabilitation of sewage treatment plant - Asingan Comm. Hosp. | Asingan | 1295708
Construction of generator set housing at Pangasinan Reformation Center, San Vicente, Burgos | Burgos | 361040
Completion Multi-purpose Hall, Camanggaan, San Nicolas | San Nicolas | 1047020
Preventive maintenance/pallative repair 2021 at PAgO Nursery, Sta. Barbara | Sta. Barbara | 857916.5 |  |  | 100% | 857916.5
Preventive maintenance/pallative repair of Capitol Resort, Lingayen | Lingayen | 497828.05 |  |  | 100% | 497828.05
Repair/improvement of 2-storey Brgy. Hall at Brgy. Bedania, Mangatarem | Mangatarem | 982450.13 |  |  | 100% | 982450.13
Repair/improvement of Bureau of Fire Protection at Manaoag Fire Station, Poblacion, Manaoag | Manaoag | 854329.49 |  |  | 100% | 854329.49
Preventive maintenance/pallative repair at Urdanet District Hospital, Urdaneta City | Urdaneta City | 922149.67 |  |  | 100% | 922149.67
Construction of walkway at Western Pangasinan District Hospital (WPDH), Alaminos City | Alaminos City | 281329.26 |  |  | 100% | 281329.26
Construction of waiting area at Western Pangasinan District Hospital, (WPDH), Alaminos City | Alaminos City | 301191.2 |  |  | 100% | 301191.2
Construction of Comfort Room for the Staff of Isolation Room at Manaoag Community Hospital, Manaoag | Manaoag | 205096.14 |  |  | 100% | 205096.14
Various materials for the tapping of waterline and pressure tank for Administrative and OR Building at Bayambang Dist. Hospital, Bayambang | Bayambang | 182685 |  |  | 100% | 182685
Construction of 3 units artesian well at Baybay Sur, Sual | Sual | 311024
15 units jetmatic handpump for Nibaliw, San Fabian | San Fabian | 66825
Construction of 3 units artesian well, Lapalo, San Manuel | San Manuel | 385381
Construction of 3 units artesian well, Pogo, Bautista | Bautista | 586800
Construction of 3 units artesian well, Macabit, Bani | Bani | 46278
Construction of 3 units artesian well, Capantolan, Sual | Sual | 49089
Construction of 3 units artesian well, Barat, Umingan | Umingan | 73197
Construction of 3 units deepwell, Abot Molina, Umingan | Umingan | 63138
construction of 3 units artesian wells, Tomling, Rosales | Rosales | 171264
construction of 3 units artesian wells at Lelemaan, Manaoag | Manaoag | 98438
PR#2035 (4/7/2021) - 1 unit grundos stainless submersible pump with motor, for use at the material assistance for water system, Tambobong, Dasol | Dasol | 114450
Labor, materials, equipment and other incidentals for the construction of 3 units Artesian Well at Brgy. Tamayo, San Carlos City | San Carlos City | 513623.61 |  |  | 100% | 513623.61
Various material for the construction of 3 units water system and three units artesian well at Brgy. Lasip, Malasiqui | Malasiqui | 235150 |  |  | 100% | 235150
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Carayungan Sur, Umingan | Umingan | 85006 |  |  | 100% | 85006
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Casanestebanan, Laoac | Laoac | 73283 |  |  | 100% | 73283
Various materials for the ocnstruction of 5 units Artesian Well at Brgy. Calmay, Laoac | Laoac | 116000 |  |  | 100% | 116000
Various materials for the ocnstruction of 4 units shallow well at Gayaman Elem. Sch., Binmaley | Binmaley | 38522 |  |  | 100% | 38522
Various materials for the ocnstruction of 3 units Artesian Well at Brgy. Decreto, Umingan | Umingan | 47775 |  |  | 100% | 47775
Various materials for the construction of 3 units Artesian Well at Brgy. Labuan, Umingan | Umingan | 51192 |  |  | 100% | 51192
Construction of 5 units dug well at Brgy. San Juan, San Manuel | San Manuel | 403338.98 |  |  | 100% | 403338.98
Provision of Additional Materials & labor for the construction of 3-units Artesian Well at Brgy. San Bonifacio, San Manuel | San Manuel | 299488.86 |  |  | 100% | 299488.86
3000 sq.m. Enbankment/common borrow for the backfilling of housing/tenement project in Brgy. Libsong Bliss, Lingayen | Lingayen | 749400 |  |  | 100% | 749400
2000 cu.m. enbankment/common borrow for the backfilling of Housing Tenement Project in Libsong Bliss, Lingayen | Lingayen | 499600 |  |  | 100% | 499600
Payment of various Medical equipment and Supplies for use of 14 Government Hospitals | Pangasinan | 18751000
Payment of variousMedical equipment and Supplies for use of 14 Government Hospitals | Pangasinan | 16498000
Payment of various Medical Supplies and Equipment | Pangasinan | 8469900
Payment of various Med. Equipment | Pangasinan | 10000600
Payment of various Medical Equipment for use of various hospitals | Pangasinan | 60600000
Payment of various Medical Equipment for use at Mangatarem & Bayambang District Hospital | Pangasinan | 44000000
Payment of various Medical Equipment for use of 14 Government Hospitals | Pangasinan | 19965000
Upgrading of WPDH & LDH on Fire Detection and Alarm System Sprinkle | Pangasinan | 34839093
Construction of Diagnostics Center at PPH, San Carlos City (Phase I) | San Carlos City | 36177827
Construction of 2 storey Rehab. Building at PPH, San Carlos City (Phase I) | San Carlos City | 60000000
Payment of various medical equipment for Pangasinan Molecular Diagnostic Laboratory Reagerts and Kits for Pangasinan Molecular Diagnostics Laboratory, 157 Sars Cov PCR Reagents (96 PCR Reactions), etc. | Pangasinan | 40000000
Payment of Pick-up truck for use of service vehicle for disease surveilance & contact tracing at PHO | Pangasinan | 1700000
Payment of 2 units passenger van for use of logistics & laboratory specimen at PHO | Pangasinan | 3000000
Payment of 3 units equipped ambulance for use of Mangatarem DH, Bayambang DH & PPH | Pangasinan | 11100000
Payment of 3 units mobile kitchen for use of Nutrition Program of the Province. | Pangasinan | 20913500
Economic Development
Blocktopping of Brgy. Alitaya Road, Mangaldan | Mangaldan | 2146000
FMR w/stone masonry at Bued, Calasiao | Calasiao | 2593588
Concreting of Cabaruan Road, Umingan | Umingan | 500000
Concreting of Poblacion - Malimpin Road, Poblacion, Dasol | Dasol | 5000000
Concreting of pathwalk, Poblacion, Umingan | Umingan | 500000
Reconstruction of Imos Bridge, Balungao | Balungao | 5251946
Blocktopping in Sta. Maria, San Jacinto | San Jacinto | 1588500
Blocktopping of brgy. Road in Asinan, Bugallon | Bugallon | 1588500
Blocktopping of brgy. Road in Nancayasan, Urdaneta City | Urdaneta City | 1765000
Blocktopping of Lebueg Road Loaoc, Pang. | Laoac | 2668500
Blocktopping of Cabueldaton road, Malasiqui | Malasiqui | 1059000
Concreting of Sta. Rosa Road, Umingan | Umingan | 500000
Concreting of Brgy. Cadiz Road, Umingan | Umingan | 500000
Reconstruction of Labit Bridge, Urdaneta City | Urdaneta City | 14986494.26 |  |  | 15% | 2247974.14
Asphalting of San Vicente Road, Bani | Bani | 1335000
PR#(7/12/2021) - widening of Las Vegas Bridge, Nilombot, Mapandan | Mapandan | 1932993
1 unit 1 barrel RCBC at Malakiat, Pozorrubio | Pozorrubio | 1671983
Blocktopping of Lokal Norte Road, Malasiqui | Malasiqui | 1585260 |  |  |  | 0
Concreting of pathwalk, Cabangunan, Umingan | Umingan | 500000
Concreting of farm to market road, Don Mariano, Umingan | Umingan | 500000
Concreting of Conception road, Umingan | Umingan | 500000
Concreting of pathwalk, Amaronan, Umingan | Umingan | 500000
Concreting of farm to market road Carayungan, Umingan | Umingan | 500000
Concreting of FMR, Cabatuan, Umingan | Umingan | 500000
Blocktopping of Lumbang, Calasiao | Calasiao | 996000
Blocktopping of Longos, Calasiao | Calasiao | 996000
R/M of roads/bridges w/in the province | Pangasinan | 7000000
Concreting of FMR, Pampano, Mangatarem, Pang. | Mangatarem | 660000
Asphalt for Nibaliw Norte, Bautista, Pang. | Bautista | 734000
Construction of shape protection with concrete barrier along Talog-Pasima Rd., Malasiqui | Malasiqui | 264677
Construction of drainage canal at Brgy. B. Tayug | Tayug | 994487
Concreting of Arinaan Road with Stone Masonry and RCCP Nomatucan, Agno | Agno | 6000000
Rehabilitation of Bataquil Junction Sison Road, Sison | Sison | 9993215.26 |  |  | 15% | 1498982.29
Concreting of pathwalk, Galdin, Mangaldan | Mangaldan | 498138.18 |  |  | 100% | 498138.18
Concreting of Cabalaoangan Road, Rosales | Rosales | 996154.5 |  |  | 100% | 996154.5
Concreting of pathway at Malilion, San Nicolas | San Nicolas | 485214.54 |  |  | 100% | 485214.54
Concreting of Casilan Road, Asingan | Asingan | 498022.28 |  |  | 100% | 498022.28
Construction of irrigation canal/sideslope protection along Catblan-Labit-Cabaruan Road, Urdaneta City | Urdaneta City | 5994160.64 |  |  | 40% | 2937138.72
Rehabilitation of Drainage Canal w/ slope protection along Guesang-Estanza Provincial Road, Lingayen | Lingayen | 998444.21 |  |  | 100% | 998444.21
Concreting of Brgy. Road at Brgy. Tanolong, Bayambang | Bayambang | 997060.14 |  |  | 100% | 997060.14
194 units water pumps & engine set; 5 units flow pumps w/ engine for farmer & fisherfolk association | Pangasinan | 4494000
Various Fishing paraphernalia for farmers assns; irrigators assns; fisherfolk assns & cooperatives | Pangasinan | 2117000
Various free seedlings for farmer, ownerm irrigators assns. & cooperatives | Pangasinan | 1314000
Amortization of Principal and Interest on Loan to the LBP | Pangasinan |  | 74357367.86 |  | 100% | 74357367.86
Environmental Development

## UNLIQUIDATED CA
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of December 2021
Province, City or Municipality: |  | PANGASINAN
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Advances for Officers and Employees
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Sub-total | 67600 |  |  | 0 | 0 | 0 | 0 | 0 | 67600
Advances to Special Disbursing
Rodolfo M. Cortez | 20000 | 1997-04-10 | [6 empty] | 20000
Rodolfo M. Cortez | 30000 | 1996-06-20 | [6 empty] | 30000
Sub-total | 50000 |  |  | 0 | 0 | 0 | 0 | 0 | 50000
GRAND TOTAL | 117600 |  |  | 0 | 0 | 0 | 0 | 0 | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO III
Provincial Accountant | [5 empty] | Governor

## TRUSTFUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE OCTOBER - DECEMBER QUARTER, CY 2021
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Upgrading of Poblacion-Cabalaoangan-Guiling Road Rosales, Pangasinan | Rosales, Pangasinan | 43041790 |  |  | 90% | 38737611 |  | Funds from DILG - CMGP 2020
Construction of Tomato Trading Post Facility at Brgy. Tugui Grande | Pangasinan | 2885843.5 |  |  | 100% | 2885843.5 |  | Funds from DA - PRDP - IREAP
Construction of Bangus Processing Facility for Integrated Small Fishpond Owners and Lesses | Binmaley, Pangasinan | 3070403.05 |  |  | 100% | 3070403.05 |  | Funds from DA - PRDP - IREAP
Construction of Isolation Facility (Phase 1) at PPH, San Carlos City Pangasinan | San Carlos City, Pangasinan | 10000000 |  |  | 85% | 8500000 |  | Funds from DOH
Medical Assistance for Indigent People | Pangasinan |  |  |  |  | 1252037 |  | Funds from DOH
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor

## CASH FLOW
PROVINCE OF PANGASINAN
GENERAL FUND
Statement of Cash Flows
For the Year Ended December 31,2021
Cash Flows from Operating Activities:
Cash Inflows:
|  |  | Collection from Taxpayers |  | 211351331.32
|  |  | Share from Internal Revenue Allotment |  | 4173049464
|  |  | Receipts from business/service income |  | 279601732.31
|  |  | Interest Income |  | 3659304.93
|  |  | Other Receipts |  | 454087918.87
|  |  | Total Cash Inflow |  | 5121749751.43
Cash Outflows:
|  |  | Payment of expenses |  | 1540758280.0314
|  |  | Payment to suppliers and creditors |  | 756895984.3686
|  |  | Payment to employees |  | 1374016016.89
|  |  | Interest Expenses |  | 57585107.38
|  |  | Other Expenses |  | 250302405.45
|  |  | Total Cash Outflow |  | 3979557794.12
|  | Net Cas Flows from Operating Activities |  |  | 1142191957.31
Cash Flows from Investing Activities:
Cash Inflows:
|  |  | Proceeds from Sale of Investment Property |  | 0
|  |  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 0
|  |  | Proceeds from the refund of Property, Plant and Equipment |  | 1959682.69
|  |  | Proceeds from Insurance Claim |  | 0
|  |  | Proceeds from Sale of Biological Assets |  | 0
|  |  | Collection of Principal on Loans to other Entities |  | 33484755
|  |  | Total Cash Inflow |  | 35444437.69
Cash Outflows:
|  |  | Purchase / Construction of Investment Property |  | 0
|  |  | Purchase / Construction of Property, Plant and Equipment |  | 1276509894.88
|  |  | Purchase of Bearer Biological Assets |  | 4520440
|  |  | Grant of Loans |  | 40148000
|  |  | Total Cash Outflow |  | 1321178334.88
|  | Net Cash Flows from Investing Activities |  |  | -1285733897.19
Cash Flows from Financing Activities:
Cash Inflows:
|  |  | Proceeds from Loans |  | 741313862.19
|  |  | Total Cash Inflow |  | 741313862.19
Cash Outflows:
|  |  | Payment of Long-Term Liabilities |  | 0
|  |  | Payment of Loan Amortization |  | 280405523.66
|  |  | Total Cash Outflow |  | 280405523.66
|  | Net Cash Flows from Financing Activities |  |  | 460908338.53
Total Cash Provided by Operating,Investing and
|  |  | Financing Activities |  | 317366398.65
| Add:Cash at Beginning of the Year (restated ) |  |  |  | 2314723462.16
| Cash at the End of the year |  |  |  | 2632089860.81
Certified Correct:
ARTURO V. SORIANO, CPA
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending December 31, 2021
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 221359886.09
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
181607710
Capital Outlay
Financial Expenses
-0-
Sub-total |  |  |  | 181607710
Balance |  |  |  | 39752176.09
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
HON. AMADO I. ESPINO III
Governor
Note on I11: Pangasinan Accounting:

## LDRMM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
As of December 2021
Province of Pangasinan
LDRRMF
Particulars | Quick Response Fund (QRF) | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| 30% | 70%
A. Sources of Funds:
Current Appropriation | 72491542.5 | 169146932.5 |  |  |  | 241638475
Continuing Appropriation |  | 192190522.68 |  |  |  | 192190522.68
Previous Year's Appropriation transferred to the Special Trust Fund | 4810042.5 | 102184537.42 |  |  |  | 106994579.92
Others Interest Income(Trust Fund) |  | 48255.59 |  |  | 0 | 48255.59
Transfers/Grants |  | 0 | 16224466 |  | 0 | 16224466
Others Interest Income (Trust Fund) | [5 empty] | 0
Total Funds Available | 77301585 | 463570248.19 | 16224466 | 0 | 0 | 557096299.19
B. Utilization
Medicines |  | 0 |  |  |  | 0
Medical Supplies |  | 0 |  |  |  | 0
Food Supplies | 67681500 | 64733900 |  |  |  | 132415400
Office Supplies |  | 180140 |  |  |  | 180140
Repair of Evacuation Center |  | 0 |  |  |  | 0
Disaster Response & Rescue Equipment |  | 3060500 |  |  |  | 3060500
Institutional/Capacity Development (Ex. Trainings, environmental assessment & other related activities) |  | 0 |  |  |  | 0
Construction of Evacuation Center |  | 0 |  |  |  | 0
Capital Outlay - Equipment |  | 0 |  |  |  | 0
Transfer to other LGUs |  | 0 |  |  |  | 0
Flood Control Systems |  | 0 |  |  |  | 0
Other Maintenance and Operating Expenses |  | 38107687.96 |  |  |  | 38107687.96
Traveling Expense |  | 0 |  |  |  | 0
Training Expense |  | 0 |  |  |  | 0
IT Equipment & Software |  | 1150242 |  |  |  | 1150242
Motor Vehicles |  | 0 |  |  |  | 0
Other Machinery and Equipment |  | 4004280 |  |  |  | 4004280
Watercrafts |  | 0 |  |  |  | 0
Other Property, Plant and Equipment |  | 0 |  |  |  | 0
Roads, Highways and Bridges |  | 0 |  |  |  | 0
Communication Equipment |  | 2660587 |  |  |  | 2660587
Gasoline, Oil, Lubricants |  | 1078181.76 |  |  |  | 1078181.76
Drugs and Medicines |  | 1500000 |  |  |  | 1500000
Repair & Maintenance-Machinery & Equipment |  | 5912091.5 |  |  |  | 5912091.5
Repair & Maintenance-Motor Vehicles |  | 2455157 |  |  |  | 2455157
Construction & Heavy Equipment |  | 0 |  |  |  | 0
Office Equipment |  | 1012000 |  |  |  | 1012000
Medical Equipment |  | 176000 |  |  |  | 176000
Furnitures & Fixtures |  | 995800 |  |  |  | 995800
Other Structures |  | 10000000 |  |  |  | 10000000
Other Transportation Equipment |  | 0 |  |  |  | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. (Trust Fund) | [5 empty] | 0
Repair & Maintenance - Building & Other Structures (Trust Fund) | [5 empty] | 0
Bank Charges (Trust Fund) | [5 empty] | 0
Total Utilization (Current Appropriation) | 67681500 | 137026567.22 | 0 | 0 | 0 | 204708067.22
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
COVID-19 Related Expenses |  | 44623750.97 | 0 | 0 | 0 | 44623750.97
Current Year's Appropriation transferred to the Special Trust Fund | 4810042.5 | 6179774.28 | 0 | 0 | 0 | 10989816.78
Total Utilization (Trust Fund) (Current Appropriation & Trust Fund) | 72491542.5 | 187830092.47 | 0 | 0 | 0 | 260321634.97
Unutilized Balance | 4810042.5 | 275740155.72 | 16224466 | 0 | 0 | 296774664.22
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Noted by:
ARTURO V. SORIANO, CPA |  |  |  | HON. AMADO I. ESPINO III
Provincial Accountant |  |  |  |  | Governor

## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2021
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Proposed extension of covered court | Brgy. Asan Sur, Sison | 1901718.83 | 2021-03-22 |  | 100% | 1901718.83 |  | COMPLETED
Completion of Multi-Purpose Bldg., (Gymnasium) | Brgy. Bersamin, Alcala | 1616667.01 | 2021-03-22 | 2021-08-20 | 100% | 1616667.01 |  | COMPLETED
Construction of Multi-purpose Bldg. | Brgy. Perez Riverside, San Carlos City | 998719.69 | 2021-03-22 | 2021-07-05 | 100% | 998719.69 |  | COMPLETED
Completion of 2-storey Muti-Purpose Bldg., (Brgy. Hall) | Brgy. Magallanes (Phase II), Tayug | 2349533.92 | 2021-03-22 | ON-GOING | 85% | 1997103.83 |  | ON-GOING
Construction of covered court (Gymnasium) | Brgy. Tamaro (Phase 1), Bayambang | 1038086.26 | 2021-03-22 | 2021-06-09 | 100% | 1038086.26 |  | COMPLETED
Construction of 2-storey Multi-Purpose Hall (Health Center) Phase 1 | Brgy. Manambong Parte, Bayambang | 988553.35 | 2021-03-12 | 2021-08-24 | 100% | 988553.35 |  | COMPLETED
Construction of Multi-purpose covered court (gymnasium) | Brgy. Palong, Malasiqui | 3221956.7 | 2021-03-22 | 2021-10-05 | 100% | 3221956.7 |  | COMPLETED
Construction of sewage Treatment Plant (STP) & installation of swerage Distribution pipline, Mangatarem District Hospital | Mangatarem | 5557773.34 | 2021-05-28 | ON-GOING | 60% | 3334664 |  | ON-GOING
Fabrication/installation of streetlights | Turho, Laoac | 995444.28 | 2021-06-02 | 2021-09-14 | 100% | 995444.28 |  | COMPLETED
Installation of 3-100 KVA DX Transformer & Electrical Services at Legislative Bldg., Capitol Cmpd. | Lingayen | 2401625.89 | 2021-06-14 | 2021-09-11 | 100% | 2401625.89 |  | COMPLETED
Installation of 3.75 KVA DX-transformer & Electrical Services at PEO Bldg., Capitol Bldg., Lingayen | Lingayen | 2888427.38 | 2021-06-14 | 2021-10-18 | 100% | 2888427.38 |  | COMPLETED
Ground improvement for parking lot of training Center a & 2 at Capitol Cmpd., Lingayen | Lingayen | 2343076.18 | 2021-06-14 | ON-GOING | 55% | 1288691.9 |  | ON-GOING
Construction of 2 MDRRMO Bldg., at Brgy. Poblacion, | Sto. Tomas | 4430747.6 | 2021-06-14 |  | 80% | 3544598.11 |  | ON-GOING
Improvement of Muti-Purpose Bldg. (Brgy. Hall) Ground Floor | Brgy. Zone III, Villasis | 928397.94 | 2021-06-22 | 2021-11-06 | 100% | 928397.94 |  | COMPLETED
Asphalting/blocktopping of Pathway w/in OPAG Field Office, | Brgy. Arnedo, Bolinao | 1128205 | 2021-09-30 | 2021-10-01 | 100% | 1128205 |  | COMPLETED
Installation of Enclosure and Cubicles at EPDH covered court for use as temporary facility for Covid-19 patients | Tayug | 1705031.55 | 2022-01-08 | 2022-01-15 | 100% | 1705031.55 |  | COMPLETED
Renovation/repair works for the proposed hemodialysis Bldg. (Phase 1) at WPDH | Alaminos City | 2995690.58 | 2021-07-22 | ON-GOING | 40% | 1198276.23 |  | ON-GOING
Blocktopping of Brgy. Alitaya Road | Mangaldan | 2141560 | 2021-09-07 | 2021-09-14 | 100% | 2141560 |  | COMPLETED
Construction of covered court (gymnasium) Pilar | Sta. Maria | 2525363.21 | 2021-09-10 | 2021-11-26 | 100% | 2525363.21 |  | COMPLETED
Construction of various projects, Salomague Norte, | Bugallon | 690295.52 | 2021-09-20 | 2021-11-23 | 100% | 690295.52 |  | COMPLETED
Const. of dranage canal at the Public Market, | Pob. Bautista | 623987.17 | 2021-11-11 | 2021-11-29 | 100% | 623987.17 |  | COMPLETED
Const. of covered court @ Mabini Central School, , Pangasinan | Mabini | 3474123 | 2021-12-17 | ON-GOING | 17% | 590600.91 |  | ON-GOING
Const. of covered court @ Namagbagan E/S, , Pangasinan | Anda | 3023377 | 2021-12-17 | ON-GOING | 9.5% | 287220.815 |  | ON-GOING
Const. of roofing of covered court @ Brgy. Ambangat, , Pangasinan | Bayambang | 1000000 | [5 empty] | NYS
Const. of bleacher & concrete pavement of covered court, , Pangasinan | Urdaneta City | 1535237 | [5 empty] | NYS
Const. of wharf @ Silaki Island, , Pangasinan | Bolinao | 2203668 | [5 empty] | NYS
Completion of covered court @ , Pang. | Brgy. Salingcob, San Nicolas | 2706331 | 2021-12-17 | ON-GOING | 24% | 649519.44 |  | ON-GOING
Asphalting of Praking aRea At Traiing Center 1 & 2, Capitol Compound, | Lingayen | 3149000 | 2022-01-18 | 2022-01-27 | 100% | 3149000 |  | COMPLETED
Construction of covered court (gymnasium) at Brgy. Capataan, | San Carlos City | 2682924 | [5 empty] | NYS
Construction of 2-storey Multi-Purpose Bldg. at Brgy. Cacaoiten, Mangatarem | Mangatarem | 2767051 | 2021-12-22 | ON-GOING | 18% | 498069.18 |  | ON-GOING
Construction/installation of Sewerage Treatment Plant (Sequential Patch Reactor Technology SBR) at NRSCC, | Lingayen | 8100000 | [5 empty] | NYS
Improvement of Legislative Bldg., (Session Hall at Lingayen) | Lingayen | 11494993 | [5 empty] | NYS
Proposed Improvement/ Asphalting of Parking Area @ San Carlos City, Pangasinan | San Carlos City | 5994000 | [5 empty] | NYS
Repair/ Extension of Kitchen @ CIDG Building, PPPO Compound, Lingayen, Pangasinan | Lingayen | 1335448 | [5 empty] | NYS
Blocktopping of Brgy. Pogomboa Proper Road @ Aguilar, Pangasinan | Aguilar | 1588500 | [5 empty] | NYS
Asphalting/ Blocktopping of Pathwalk @ Brgy. Bacabac, Bugalllon, Pangasinan | Bugalllon | 522500 | [5 empty] | NYS
Improvement/ Blocktopping of the existing Asphalt Pavement located inside the PAgO Compound @ Alminos City, Pangasinan | Alaminos City | 311000 | [5 empty] | NYS
Blocktopping of Balungao-Sta. Maria Road @ Balungao & Sta. Maria | Balungao & Sta. Maria | 5295000 | [5 empty] | NYS
Asphalting/blocktopping along Buenlag-Polong Road (Buenlag Section) and Pathwalk infront of Buenlag E/S @ Brgy. Buenlag, Bugallon | Bugallon | 1447000 | [5 empty] | NYS
Blocktopping of Sitio Taloy Road @ Brgy. Papagueyan, Binmaley | Binmaley | 1588500 | [5 empty] | NYS
Blocktopping of Brgy. Road @ Brgy. Cayanga, Bugallon | Bugallon | 1588500 | [5 empty] | NYS
Concreting of Brgy Roads/ Pathwalk FMR @ various Barangays, Basista | Basista | 5000000 | [5 empty] | NYS
Concreting of Farm to Market Road @ various barangays, Sual | Sual | 5000000 | [5 empty] | NYS
Concreting of Pathwalk & Construction/ Installation of Solar Street Lights @ various Barangays, Alaminos City | Alaminos City | 3000000 | [5 empty] | NYS
Rappelling Tower for BFP, Urdaneta City | Urdaneta City | 2567259.84 | 2021-03-22 | 2021-10-09 | 100% | 2567259.84 |  | COMPLETED
Preventive maintenance/pallative repair of Asingan Com. Hospital | Asingan | 994010.78 | 2021-06-28 | 2021-09-18 | 100% | 994010.78 |  | COMPLETED
Construction of Multi-Purpose Hall (Brgy. Hall) at Brgy. Maigpa, Bayambang | Bayambang | 904606.37 | 2021-06-28 | 2021-09-21 | 100% | 904606.37 |  | COMPLETED
Construction of 1 unit level II water system @ Camaley, Binmaley. | Binmaley | 525032.57 | 2021-08-11 | 2021-09-11 | 100% | 525032.57 |  | COMPLETED
Construction of Medicine warehouse - EPDH | Tayug | 3729102.81 | 2021-09-10 | 2021-11-11 | 100% | 3729102.81 |  | COMPLETED
Backfilling of relocation area at Sitio Balingkaging, Baay, Lingayen | Lingayen | 500000 | [5 empty] | NYS
Renovation works for the proposed Hemodialysis Bldg (phase II) @ Alaminos City, Pang. | Alaminos City | 1921975 | 2021-12-01 | ON-GOING | 40% | 768790 |  | ON-GOING
Completion of 2 storey Multi-purpose bldg @ Brgy. Poblacion West, Natividad, Pang | Natividad | 1261421 | 2021-12-17 | ON-GOING | 22.6% | 285081.146 |  | ON-GOING
Repair/Rehab. Of Bliss Multi-purpose Bldg @ Brgy. Libsong East, Lingayen | Lingayen | 1302094 | 2021-12-17 | ON-GOING | 50.33% | 655343.9102 |  | ON-GOING
Repair/improvement of Base Armory at Camp Tito B. Abat, Manaoag | Manaoag | 705275 | [5 empty] | NYS
Construction of Medical Records Bldg., at Pozorrubio Community Hospital, Pozorrubio | Pozorrubio | 1222684 | 2021-12-22 | ON-GOING | 12.72% | 155525.4048 |  | ON-GOING
(part of 6,900,000) Construction of Permiter Fence @ Public Park Brgy, Libsong East, Lingayen Pangasinan (Pangasinan Tenement Housing Project 6511-112-34987, 5M) | Lingayen | 1900000
Repair of Imelda Bridge (Last span) at Mangatarem | Mangatarem | 1646172.51 | 2017-03-26 | 2021-08-07 | 100% | 1646172.51 |  | COMPLETED
Rehabilitation of Bayaoas Bridge (Superstructure) at Urdaneta City | Urdaneta City | 3038985 | 2021-03-26 |  | 82.44% | 2505335.09 |  | COMPLETED
Riprapping/approach of RCBC at Sitio Apoler, Tubuan, Labrador | Labrador | 1374989.35 | 2021-03-22 | 2021-10-08 | 100% | 1374989.35 |  | COMPLETED
Concreting of Bartolome Junio Road, at Brgy. Nalsian Norte, Bayambang | Bayambang | 996368.63 | 2021-03-22 | 2021-04-09 | 100% | 996368.63 |  | COMPLETED
Concreting of Pathwal at Brgy. Paitan, Sta. Maria | Sta. Maria | 1494557.15 | 2021-03-22 | 2021-07-09 | 100% | 1494557.15 |  | COMPLETED
Concreting of Brgy. San Jose-Brgy. Laois Baybay road w/ RCPC, Labrador | Labrador | 998674.07 | 2021-05-12 | 2021-07-31 | 100% | 998674.07 |  | COMPLETED
Concreting of pathwalk at Brgy. San Vicente, Bayambang | Bayambang | 997752.88 | 2021-05-12 | 2021-06-01 | 100% | 997752.88 |  | COMPLETED
Construction of irrigation canal/sideslope protection along Catblan-Labit-Cabaruan Road, Urdaneta City | Urdaneta City | 5994160.64 | 2021-05-28 | ON-GOING | 70% | 4196073.54 |  | ON-GOING
Proposed reconstruction of Maambal Bridge, Pozorrubio | Pozorrubio | 8534046.36 | 2021-06-14 | ON-GOING | 90% | 7680641.72 |  | ON-GOING
Blocktopping of Casampagaan-Anis Road, Laoac | Laoac | 2489055 | 2021-06-09 | 2021-09-17 | 100% | 2489055 |  | COMPLETED
Rehabilitation of Bataquil Junction Sison Road, Sison | Sison | 9993215.26 | 2022-06-14 | ON-GOING | 60% | 5995929.16 |  | ON-GOING
Improvement(concreting and raising w/ stone masonry) of Poblacion-Dalongue Road., Sta. Barbara | Sta. Barbara | 9984297.78 | 2021-06-29 | 2021-10-05 | 100% | 9984297.78 |  | COMPLETED
Blocktopping at Artacho St., Pozorrubio | Pozorrubio | 2859760 | 2021-07-31 | 2021-08-25 | 100% | 2859760 |  | COMPLETED
Blocktopping at Penoy St., Pozorrubio | Pozorrubio | 1791585 | 2021-07-08 | 2021-07-13 | 100% | 1791585 |  | COMPLETED
Concreting of Brgy. Pita Road, Infanta | Infanta | 995695.34 | 2021-07-22 | 2021-10-06 | 100% | 995695.34 |  | COMPLETED
Concreting of Brgy. Maya Road, Infanta | Infanta | 996197.48 | 2021-07-22 | 2021-08-31 | 100% | 996197.48 |  | COMPLETED
Asphalting of Brgy. Road, Tombor | bINMALEY | 2494943.72 | 2021-07-21 | 2021-11-23 | 100% | 2494943.72 |  | COMPLETED
FMR w/stone masonry at Bued, Calasiao | Calasiao | 2587999.65 | 2021-09-02 | 2021-11-12 | 100% | 2587999.65 |  | COMPLETED
Blocktopping in Sta. Maria, San Jacinto | San Jacinto | 1585260 | 2021-11-03 | 2021-11-09 | 100% | 1585260 |  | COMPLETED
Blocktopping of brgy. Road in Asinan, Bugallon | Bugallon | 1585260 | 2021-10-01 | 2021-10-07 | 100% | 1585260 |  | COMPLETED
Blocktopping of brgy. Road in Nancayasan, Urdaneta City | Urdaneta City | 1761400 | 2021-06-26 | 2021-07-03 | 100% | 1761400 |  | COMPLETED
Blocktopping of Lebueg Road Loaoc, Pang. | Laoac | 2663055 | 2021-09-17 | 2021-09-24 | 100% | 2663055 |  | COMPLETED
Asphalting of San Vicente Road, Bani | Bani | 1332285 | 2021-08-20 | 2021-09-04 | 100% | 1332285 |  | COMPLETED
1 unit 1 barrel RCBC at Malakiat, Pozorrubio | Pozorrubio | 1667580.35 | 2021-09-10 | ON-GOING | 60% | 1000548.21 |  | ON-GOING
Blocktopping of Lokal Norte Road, Malasiqui | Malasiqui | 1585260 | 2021-11-03 | 2021-11-12 | 100% | 1585260 |  | COMPLETED
R/M of roads/bridges w/in the province | Pangasinan | 6985000 |  |  | 100% | 6985000
Concreting of FMR, Pampano, Mangatarem, Pang. | Mangatarem | 657163.3 | 2021-09-13 | 2021-09-28 | 100% | 657163.3 |  | COMPLETED
Various fruit tree seedlings to be distributed to farmers and mango growers associations in support to the Food Production and Lowland Reforestation Program in the Province of Pangasinan | Pangasinan | 286500
Various fruit tree seedlings for awarding and distribution to various rural-breed organization and institution as part of the interventions under the ABIG Pangasinan Program | Pangasinan | 1035000
Labor, materials, equipment and other incidentals for the construction of 1 unit level II Water system at Brgy. Buenlag, Binmaley | Binmaley | 478004.01 | 2021-05-12 | 2021-08-13 | 100% | 478004.01 |  | COMPLETED
PR#4811(7/9/2021) - Construction of 3 units artesian well at Baybay Sur, Sual | Sual | 309483.48 | 2021-08-11 | 2021-10-02 | 100% | 309483.48 |  | COMPLETED
PR#7377 (10/5/2021) - Maintenance of various waterworks project w/in the prov. | Pangasinan | 278295
PR#7377(10/5/2021) - Construction of 1 unit water well source with water system @ OPVET, Malabobo, Mangatarem, Pangasinan | Mangatarem | 184876.5
PR#7779 (10/18/2021) - Upgrading of water system @ OPAg Prov'l Mangrove Information Center & Nursery, Bolinao Fish Farm @ Brgy. Arnedo, Bolinao, Pangasinan | Bolinao | 102814
PR#7986 (10/21/2021) - Const. of 7 units Artesian well @ Brgy. Balligi, Laoac | Laoac | 126237 | [5 empty] | NYS
(part of 6,900,000) Construction of Permiter Fence @ Public Park Brgy, Libsong East, Lingayen Pangasinan (Pangasinan Tenement Housing Project- 2021-6911-2-12-34988- 1.9M) | Lingayen | 5000000
PR#5248 (7/23/2021) - Payment of various Medical Equipment for use of various hospitals | Pangasinan | 60589338 |  |  |  | 60589338
PR#5285 (7/26/2021) - Payment of various Medical Equipment for use of 14 Government Hospitals | Pangasinan | 19959952.5 |  |  |  | 19245317.5
PR#5247 (7/23/2021) - Payment of various medical equipment for Pangasinan Molecular Diagnostic Laboratory Reagerts and Kits for Pangasinan Molecular Diagnostics Laboratory, 157 Sars Cov PCR Reagents (96 PCR Reactions), etc. | Pangasinan | 40000000 |  |  | 100% | 40000000
Economic Development
Amortization of Principal and Interest on Loan to the LBP |  | 241523640.63
20 units waterpump and engine set | Pangasinan | 1717000
75 units waterpump and engine set | Pangasinan | 1575000
12 units axial pump w/ engine | Pangasinan | 1008000
Fishery paraphernalia for distribution to the marginalized fisherfolk associations in the coastal area of Pangasinan in support to Coastal Resource Management | Pangasinan | 429100
Repair of various Prov'l Roads & Bridges | Pangasinan | 6065000
Concreting of Arinaan Road with Stone Masonry and RCCP Nomatucan, Agno | Agno | 5994040 | 2021-11-04 | ON-GOING | 80% | 4795232 |  | ON-GOING
Improvement @ Brgy. Cabuan - Brgy. Poblacion East Road, Bautista, Pangasinan | Bautista | 575579 | 2021-11-22 | 2021-12-05 | 100% | 575579 |  | COMPLETED
Regravelling of Brgy. Imbo Road @ Anda, Pangasinan | Anda | 250000 | [5 empty] | NYS
Blocktopping w/patching of Brgy. Silang Road @ Natividad, Pangasinan | Natividad | 826500 | [5 empty] | NYS
Concreting of pathwalk @ Brgy. Palina West, Purok I, Urdaneta City, Pangasinan | Urdaneta City | 1274111 | 2021-12-17 |  |  |  |  | ON-GOING
Blocktopping of Brgy. Road @ Brgy. San Macario Sur, Natividad, Pangasinan | Natividad | 1765000 | [5 empty] | NYS
Asphalting of Brgy. Road @ Brgy. San Miguel, Natividad, Pangasinan | Natividad | 1335000 | [5 empty] | NYS
Blocktopping with Patching of Brgy. Barangobong Sitio Nining Rd @ Natividad, Pangasinan | Natividad | 947000 | 2022-01-18 | 2022-01-22 | 100% | 947000 |  | COMPLETED
Concreting of farm to market Rd @ Brgy. Gumot, San Fabian, Pangasinan | San Fabian | 999998.75 | 2021-11-22 | deC. 2021 | 100% | 999998.75 |  | COMPLETED
Concreting of pathwalk @ Brgy. Bongato East, Bayambang, Pangasinan | Bayambang | 999953 | 2021-11-22 |  |  |  |  | ON-GOING
Concreting of farm to market rd @ Brgy. Bical Sur, Bayambang, Pangasinan | Bayambang | 1000000 | 2021-12-17 |  |  |  |  | ON-GOING
Concreting of Brgy. Centro Toma Purok 4&7 @ Bani, Pangasinan | Bani | 2639523 | [5 empty] | NYS
Concreting of farm to market rd @ Brgy. Macayocayo, Bayambang, Pangasinan | Bayambang | 999963 | 2021-11-22 | deC. 2021 | 100% | 999963 |  | COMPLETED
Blocktopping of Brgy. Road @ Brgy Luna, Natividad, Pangasinan | Natividad | 1588500 |  |  |  | 0 |  | NYS
Asphalting of Bargy. Catuday, Bolinao, Pangasinan | Bolinao | 1765000 | 2021-12-03 | 2021-12-03 | 100% | 1765000 |  | COMPLETED
Construction of drainage canal @ Brgy. Poblacion, Dasol, Pangasinan | Dasol | 2700314 | 2021-12-17 |  |  | 0 |  | ON-GOING
Blocktopping of pathwalk @ Brgy. Tempra, Guilig, San Fabian, Pangasinan | San Fabian | 734000 | 2021-12-28 | 2022-01-04 | 100% | 734000 |  | COMPLETED
Concreting of Panfilo Lopez West St. @ Poblacion, Lingayen, Pangasinan | Lingayen | 3777355 | 2021-12-17 |  |  | 0 |  | ON-GOING
Asphalting of Brgy. Namolan Road, Lingayen, Pangasinan | Lingayen | 996000 | 2021-12-11 | 2021-12-14 | 100% | 996000 |  | COMPLETED
Asphalting of pathwalk @ Brgy. Luciente II, Bolinao, Pangasinan | Bolinao | 1256500 | 2021-12-28 | 2022-01-11 | 100% | 1256500 |  | COMPLETED
Construction of 1 unit, 2 barrel RCBC @ Brgy. De Guzman, Mabini, Pangasinan | Mabini | 2000000 | 2021-12-17 |  |  |  |  | ON-GOING
Blocktopping w/ patching of Brgy. San Maximo, Natividad, Pangasinan | Natividad | 1300000 | 2022-01-25 | 2022-01-26 | 100% | 1300000 |  | COMPLETED
Blocktopping of Brgy. Road @ Brgy. Anonang, San Fabian, Pangasinan | San Fabian | 2471000 |  |  |  | 0 |  | NYS
Blocktopping of Brgy. Dulag Rd, Lingayen, Pangasinan | Lingayen | 2132000 | 2021-11-27 | 2021-12-01 | 100% | 2132000 |  | COMPLETED
Proposed blocktopping of Palina East Rd @ Urdaneta City, Pangasinan | Urdaneta City | 1335000 | 2021-11-16 | 2021-11-17 | 100% | 1335000 |  | COMPLETED
Blocktopping of Brgy. Rd @ Bgry. Inmalog Sur, San Fabian, Pangasinan | San Fabian | 1765000 |  |  |  | 0 |  | NYS
Blocktopping of Nagsaag Rd @ San Manuel, Pangasinan | San Manuel | 1999000 | 2021-12-03 | 2021-12-15 | 100% | 1999000 |  | COMPLETED
Blocktopping with patching of Brgy Salud RD, Natividad, Pangasinan | Natividad | 1490500 | 2022-01-11 | 2022-01-12 | 100% | 1490500 |  | COMPLETED
Concreting of Brgy. Mabilao Road with Drainage Canal @ San Fabian, Pangasinan | San Fabian | 2424131 | 2021-12-17 |  |  |  |  | ON-GOING
Const. of slope Protection along Mabilao-Binday Road, san Fabian | San Fabian | 1748676 | 2021-12-17 |  |  |  |  | ON-GOING
Concreting of Brgy Road, Pugot, Sta. Maria | Sta. Maria | 1971181 | [5 empty] | NYS
Proposed Embankment of Access Roads at PAgO, Tebag East, Sta. Barbara | Sta. Barbara | 2070696 | [5 empty] | NYS
Improvement fo Bantog Brgy. Road at Asingan | Asingan | 784000 | [5 empty] | NYS
Asphalting/ blocktopping of Lebueg- Casantiagoan Road @ Laoac, Pangasinan | Laoac | 2810000 | [5 empty] | NYS
Blocktopping of Brgy. Lipit Norte Road @ Manaoag, Pangasinan | Manaoag | 3439000 | [5 empty] | NYS
Total - Social Development |  | 642487272.11 |  |  |  | 266105712.346
Environmental Development
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO III
Provincial Accountant | [5 empty] | Governor